## GCs n GRs
Client | DPR & DGS |  | Total GSF: | 20000 | <-- ALL PULLED FROM "BID SHEET"
Project | Jelleff Recreation Center |  |  |  | <-- ALL PULLED FROM "BID SHEET"
Location | 3265 S St NW, Washington, DC 20007 |  |  |  | <-- ALL PULLED FROM "BID SHEET"
Architect | DLR Group |  | Weeks: | 78 | <-- ALL PULLED FROM "BID SHEET"
Engineer | Various |  | Months: | 18 | <-- ALL PULLED FROM "BID SHEET"
General Conditions and General Requirements - SUMMARY |  |  | Calculated | Override |  |  |  | Total | Notes
| Field and Office Personnel |  | 1625000 | 0 |  |  |  | 0
| Close Out |  | 0 |  |  |  |  | 0
[7 empty] | General Conditions - Personnel | 0
| Building Clean Up |  | 0 |  |  |  |  | 0
| Field Office Expenses |  | 0 |  |  |  |  | 0
| Trailer Expenses |  | 0 |  |  |  |  | 0
| Project Expenses |  | 0 |  |  |  |  | 0
[7 empty] | General Conditions - Non-Personnel | 0
| Temp Constcrution & OSHA |  | 924946.2 | 0 |  |  |  | 0
| Temporary Building Utilities |  | 0 |  |  |  |  | 0
| Temporary Heat & Weather Protection |  | 0 |  |  |  |  | 0
| Material and Personnel Hoisting |  | 0 |  |  |  |  | 0
| Engineering, testing, Inspection |  | 0 |  |  |  |  | 0
| Miscellaneous Provsions |  | 0 |  |  |  |  | 0
| Insurance, Taxes, Permit |  | 0 |  |  |  |  | 0
[7 empty] | General Requirements | 0
Field and Office Personnel
Cost Code | Description | Hrs/Wk | Rate | Unit | Ext. Rate | Quantity |  | Total | Notes
01-005 | Field Superintendent - BWS | 0 | 75 | Weeks | 0 | wks |  | 0
01-010 | Assistant Field Superintendent - BWS | 0 | 65 | Weeks | 0 | wks |  | 0
01-030 | Project Manager | 0 | 85 | Weeks | 0 | wks |  | 0
01-035 | Project Engineer | 0 | 65 | Weeks | 0 | wks |  | 0
01-040 | Close Out Engineer | 0 | 54.36 | Weeks | 0 | wks |  | 0
01-045 | Field Accountant | 0 | 27.65 | Weeks | 0 | wks |  | 0
01-048 | Laborer Allowance |  | 50000 | ls | 50000 | enter ---> |  | 0
01-050 | Testing Engineer & Commissiong Agent |  | 40000 | ls | 40000 | enter ---> |  | 0
01-051 | Project Mechanical / Electrical Estimator | 0 | 2800 | Weeks | 0 | wks |  | 0
01-052 | Preconstruction Fee / Expenses |  | 400 | Lump Sum | 400 | enter ---> | 0 | 0
01-053 | Scheduling Engineer |  | 425 | Days | 425 | enter ---> |  | 0
01-055 | Safety Manager Meetings |  | 600 | Days | 600 | enter ---> |  | 0
01-060 | Safety Coordinator (On Site) | 0 | 54.36 | Weeks | 0 | wks |  | 0
01-061 | Enviro Management System Auditor |  | 500 | Days | 500 | enter ---> |  | 0
01-065 | Secretary | 0 | 31.875 | Weeks | 0 | wks |  | 0
01-070 | Office Clerk | 0 | 800 | Weeks | 0 | wks |  | 0
01-071 | Contract Administrator |  | 800 | Days | 800 | enter ---> |  | 0
01-075 | Travel Allowance |  | 0 | Weeks | 0 | wks |  | 0
01-076 | Truck Allowance |  | 0 | Months | 0 | mos |  | 0
01-080 | Out of Town Travel |  | 0 | Trips | 0 | enter ---> |  | 0
01-081 | Out of Town Living Expenses |  | 0 | MONTHS | 0 | mos | 0 | 0
01-085 | Project Executive |  | 4200 | Weeks | 0 | wks |  | 0
01-090 | Project Principal |  | 5000 | Weeks | 0 | wks |  | 0
01-095 | Cost Engineer |  | 300 | Days | 300 | enter ---> | 0 | 0
01-096 | Main Office Support / M.I.S. |  | 400 | Days | 400 | enter ---> |  | 0
01-099 | Quality Control Manager |  | 600 | Days | 600 | enter ---> |  | 0
[6 empty] | enter ---> |  | 0
| Site from budget |  |  | ls | 150000 | enter ---> | 1 | 150000
| Historic From Budget |  |  | ls | 325000 | enter ---> | 1 | 325000
| 1950's from Budget |  |  | ls | 250000 | enter ---> | 1 | 250000
| Addition from Budget |  |  | ls | 789899 | enter ---> | 1 | 789899
| Letter contract from budget |  |  | ls | 110101 | enter ---> | 1 | 110101
[6 empty] | enter ---> |  | 0
[6 empty] | enter ---> |  | 0
[6 empty] | enter ---> |  | 0
[6 empty] | Subtotal |  | 1625000
[6 empty] | Escalation | 0% | 0
Field and Office Personnel | [5 empty] | Total |  | 1625000
Close Out
Cost Code | Description | Hrs/Wk | Rate | Unit | Ext. Rate | Quantity |  | Total | Notes
01-005 | Field Superintendent - BWS | 0 | 0 | Weeks | 0 | wks |  | 0
01-030 | Project Manager | 0 | 65 | Weeks | 0 | wks |  | 0
01-035 | Project Engineer | 0 | 85 | Weeks | 0 | wks |  | 0
01-065 | Secretary | 0 | 65 | Weeks | 0 | wks |  | 0
01-085 | Project Executive | 0 | 54.36 | Weeks | 0 | wks |  | 0
01-090 | Project Principal | 0 | 27.65 | Weeks | 0 | wks |  | 0
01-095 | Cost Engineer |  | 50000 | Days | 50000 | enter ---> |  | 0
01-096 | Main Office Support / M.I.S. | 0 | 40000 | Weeks | 0 | wks |  | 0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Close Out | [5 empty] | Total |  | 0
Building Clean Up
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-100 | General Clean-Up - Laborer |  |  |  | 78 | Weeks | 0 | 0
| General Clean-Up - Material / Equipment |  |  |  | 18 | Months | 0 | 0
01-105 | Final Clean-Up |  |  |  | 20000 | gsf | 0 | 0
01-110 | Window Cleaning |  |  |  | 0 | sf | 0.75 | 0
01-115 | Trash Containers - (City of Phila.) |  |  |  | 0 | Each | 400 | 0
| Trash Containers - (Phila. Suburbs) |  |  |  | 0 | Each | 450 | 0
| Trash Containers - (South Jersey) |  |  |  | 0 | Each | 800 | 0
| Trash Containers - (Central Jersey) |  |  |  | 0 | Each | 600 | 0
| Trash Containers - (North Jersey) |  |  |  | 0 | Each | 800 | 0
| Trash Containers - (Delaware) |  |  |  | 0 | Each | 800 | 0
| Trash Containers - (Harrisburg) |  |  |  | 0 | Each | 800 | 0
| Trash Containers - (Washington, D.C.) |  |  |  | 0 | Each | 400 | 0
01-120 | Trash Chutes (Delivery/Install/Remove) |  |  |  | 0 | Set | 7000 | 0
01-121 | Trash Chutes (Rental) |  |  |  | 0 | Months | 750 | 0
01-125 | Dumpster Enclosure (Labor) |  |  |  | 0 | M.D. | 500 | 0
| Dumpster Enclosure (Material) |  |  |  | 0 | Each | 2500 | 0
01-127 | Pest Control |  |  |  | 0 | Months | 275 | 0
01-130 | Street Cleaning |  |  |  | 0 | Days | 1000 | 0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Building Clean Up | [5 empty] | Total |  | 0
Field Office Expenses
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-200 | Office Equipment & Supplies |  |  |  | 18 | Months | 600
01-205 | Water Cooler |  |  |  | 18 | Months | 200
01-210 | Telephone Line Connection Fees |  |  |  | 2 | Each | 250
01-211 | Telephone Rental & Usage Costs |  |  |  | 18 | Months | 600
01-215 | Fax Line Connection Fees |  |  |  | 2 | Each | 250
01-216 | Fax Line Rental & Usage Costs |  |  |  | 18 | Months | 200
01-220 | Public Telephones |  |  |  | 18 | Months | 150
01-225 | Nextel Phones |  |  |  | 18 | Months | 110
01-230 | Copy Machine (Small) |  |  |  | 2 | Each | 1200
01-235 | Copy Machine (Large) |  |  |  | 18 | Months | 250
01-240 | Computers / Printers |  |  |  | 2 | Each | 1000
01-241 | Wide Area Network Hardware |  |  |  | 2 | Lump Sum | 3000
01-242 | Wide Area Network Usage |  |  |  | 18 | Months | 850
01-243 | Project Talk Costs |  |  |  | 2 | Lump Sum | 2
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Field Office Expenses | [5 empty] | Total |  | 0
Trailer Expenses
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-250 | Office Trailer Rental Costs |  |  |  | 18 | Months | 400
01-251 | Block & Level Trailer |  |  |  | 0 | Each | 175
| Delivery & Pick Up of Trailer |  |  |  | 0 | Each | 250
| Trailer Relocation |  |  |  | 0 | Each | 750
01-255 | Trailer Set-Up & Furnishings |  |  |  | 0 | Each | 1000
01-260 | Electrical Service for Trailer |  |  |  | 0 | Each | 2500
01-265 | Plumbing Service for Trailer |  |  |  | 0 | Each | 2500
01-270 | Storage Trailers |  |  |  | 18 | Months | 150
01-275 | Trailer Alarm System - Monthly Cost |  |  |  | 18 | Months | 250
01-276 | Trailer Alarm System - Installation |  |  |  | 0 | Each | 7500
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Trailer Expenses | [5 empty] | Total |  | 0
Project Expenses
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-300 | U. S. Postage |  |  |  | 0 | Months | 175
01-305 | Federal Express |  |  |  | 18 | Months | 400
01-315 | Reproduction Costs - Allowance |  |  |  | 0 | ls | 20000
01-316 | Reproduction Costs - Construction |  |  |  | 0 | Months | 750
01-320 | Temporary Toilets |  |  |  | 0 | Months | 150
01-325 | Rental Equipment |  |  |  | 18 | Months | 750
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Project Expenses | [5 empty] | Total |  | 0
Temp Constcrution & OSHA
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-400 | Temporary Stairs |  |  |  | 405 | Riser | 100 |  | W/Trades
01-405 | Temporary Railings |  |  |  | 300 | L. Ft. | 5 |  | W/Trades
01-410 | Temporary Toe Guards |  |  |  | 2500 | L. Ft. | 6.5 |  | W/Trades
01-415 | Temporary Floor Enclosures |  |  |  | 50 | Each | 125 |  | W/Trades
01-420 | Temporary Floor Protection |  |  |  | 59617 | Sq. Ft. | 1.5 |  | W/Trades
01-425 | Temporary Tread Protection |  |  |  | 405 | Riser | 25 |  | W/Trades
01-430 | Temporary Fencing |  |  |  | 650 | L. Ft. | 8 |  | W/Trades
| Temporary Gate for Fence |  |  |  | 4 | Each | 1750 |  | W/Trades
01-435 | Temporary Dust Protection |  |  |  | 0 | L. Ft. | 0
01-440 | Temporary Tunnel (Interior) |  |  |  | 0 | L. Ft. | 200
01-445 | Temporary Sidewalk Protection - Overhead |  |  |  | 100 | L. Ft. | 125 |  | W/Trades
01-450 | Temporary Window Protection |  |  |  | 0 | Sq. Ft. | 5 |  | W/Trades
01-455 | Temporary Drywall Partitions |  |  |  | 0 | L. Ft. | 75
01-465 | Temporary Fire Protection |  |  |  | 0 | Months | 250
01-470 | Temporary Road Stone |  |  |  | 0 | Sq. Ft. | 0.75 |  | W/Trades
01-475 | Safety Issues (Labor) |  |  |  | 0 | M.D. | 500 |  | W/Trades
01-476 | Safety Supplies (Material) |  |  |  | 0 | Lump Sum | 4000
01-480 | Miscellaneous OSHA Requirements (Labor) |  |  |  | 0 | M.D. | 500 |  | W/Trades
01-481 | Miscellaneous OSHA Requirements (Material) |  |  |  | 0 | Lump Sum | 2000
01-485 | Pumping |  |  |  | 0 | Days | 0
01-490 | Safety Netting |  |  |  | 0 | Lump Sum | 0
01-495 | Temporary Elevator Use |  |  |  | 0 | Each | 0 |  | See Below
| Site: | [6 empty] | 0
| Security Cameras for Project Site |  |  |  | 12 | months | 2300 | 27600
| - Personnel security - EXCLUDED |  |  |  |  | Excluded |  | 0
0
| Temporary Toilets (13 months) |  |  |  | 13 | months | 2500 | 32500
0
| Temporary Heat (2 months) |  |  |  | 2 | months | 15000 | 30000
0
| Video/Photo Documentation of Existing Conditions / Progress |  |  |  | 1 | ls | 9500 | 9500
0
| Temporary Protection / Weathertight During Construction |  |  |  | 1 | ls | 30000 | 30000
0
| Miscellaneous Layout for the Work |  |  |  | 1 | ls | 13210 | 13210
| - Building footprint and setbacks, multiple mobilizations for rework |  |  |  |  | Included |  | 0
| - Grading and regrading, depths for footins, slab on grade, etc. |  |  |  |  | Included |  | 0
| - Utility layout |  |  |  |  | Included |  | 0
0
| Archealogical Investigation and Excavation - Allowance |  |  |  | 1 | Allow | 20000 | 20000
| Additional Geotechnical Investigation - Allowance |  |  |  | 1 | Allow | 22000 | 22000
0
| Flush and Cam Existing Sanitary Main - Excluded - Assume New |  |  |  |  | Excluded |  | 0
0
| Temporary Requirements |  |  |  | 1 | ls | 40000 | 40000
| - Temporary Site Construction Fencing |  |  |  |  | Included |  | 0
| - Gates |  |  |  |  | Included |  | 0
0
| Temporary Trailers for Construction |  |  |  | 12 | months | 4250 | 51000
0
| Casual Dewatering (Permanent Dewatering Excluded) |  |  |  | 1 | ls | 15000 | 15000
| - Temporary water removal for rain water events, ponding at excavations |  |  |  |  | Included |  | 0
| Site Winterization/Snow Removal |  |  |  | 1 | ls | 20000 | 20000
| Traffic Control Plan Including Maintenance/Removal |  |  |  | 1 | ls | 30000 | 30000
| - Signage, permits, personnel for lane and sidewalk closures at public areas |  |  |  |  | Included |  | 0
0
| ADDITIONAL ITEMS: | [6 empty] | 0
| - ADD ALTERNATE for WELL GOLD |  |  |  |  | ADD | 175000 | 0
| * Design Fees, excludes modeling |  |  |  |  | ADD | 55000 | 0
| * Increased scope for water testing and increased air capacity (30%) |  |  |  |  | Included |  | 0
| Bond |  |  |  | 340810 | % | 0.02 | 6816.2
| Historiuc | [6 empty] | 0
| Trash Chute |  |  |  | 1 | ea | 10000 | 10000
0
| Material / Man Hoist - included with Addition |  |  |  |  | w/ Addition |  | 0
0
| Additional BIM Requirements - 2" and bigger included |  |  |  |  | Included |  | 0
0
| Tower Crane Requirements - N/A - Not required for this project |  |  |  |  | N/A |  | 0
| - Mobilization and Demobilization |  |  |  |  | N/A |  | 0
| - Power Requirements |  |  |  |  | N/A |  | 0
| - Man-hours for Operation |  |  |  |  | N/A |  | 0
0
| Interior Scaffolding at Double Height Spaces |  |  |  | 1 | ls | 8500 | 8500
| - Dance Floors and Shared Scaffolding |  |  |  |  | Included |  | 0
| - Erection and Dismantling, Maintenance While Onsite |  |  |  |  | Included |  | 0
0
| Additional Consulting Costs |  |  |  |  | Included with Design Fees |  | 0
| - Geotechnical investigations, achealogical investigations, etc. | [6 empty] | 0
0
| Temporary Roofing Systems |  |  |  | 1 | ls | 5500 | 5500
| - Temporary enclosures for weathertight, vertical and horizontal openings |  |  |  |  | Included |  | 0
| - Temporary roofing system at critical areas, electrical room, mechanical rooms, etc. |  |  |  |  | Included |  | 0
0
| Miscellaneous | [6 empty] | 0
| - Dumpsters |  |  |  | 18 | ea | 650 | 11700
| - Final Building Clean |  |  |  | 30250 | sf | 0.35 | 10587.5
| - Window Cleaning |  |  |  | 1 | ls | 8500 | 8500
| - Course of Construction Labor/Clean-Up |  |  |  | 25 | wks | 1250 | 31250
| * One (1) man for 25 weeks ($1,200 per wee per man) or approximately $30/hr | [6 empty] | 0
| * Overtime hours excluded | [6 empty] | 0
0
| Additional testing and inspections to meet Netzero requirements |  |  |  | 1 | ls | 18000 | 18000
| - Façade testing, inspections, air tests, etc. | [6 empty] | 0
0
| Owner Moving Costs - w/ below line items |  |  |  |  | w/ below line |  | 0
0
| Custodial Equipment - Excluded |  |  |  |  | Excluded |  | 0
| Bond |  |  |  | 104037.5 | % | 0.02 | 2080.75
| 1950 | [6 empty] | 0
| Trash Chute |  |  |  | 1 | ea | 5000 | 5000
0
| Material / Man Hoist - included with Addition |  |  |  |  | w/ Addition |  | 0
0
| Additional BIM Requirements - 2" and bigger included |  |  |  |  | Included |  | 0
0
| Tower Crane Requirements - N/A - Not required for this project |  |  |  |  | N/A |  | 0
| - Mobilization and Demobilization |  |  |  |  | N/A |  | 0
| - Power Requirements |  |  |  |  | N/A |  | 0
| - Man-hours for Operation |  |  |  |  | N/A |  | 0
0
| Interior Scaffolding at Double Height Spaces |  |  |  | 1 | ls | 5000 | 5000
| - Dance Floors and Shared Scaffolding |  |  |  |  | Included |  | 0
| - Erection and Dismantling, Maintenance While Onsite |  |  |  |  | Included |  | 0
0
| Additional Consulting Costs |  |  |  |  | Included with Design Fees |  | 0
| - Geotechnical investigations, achealogical investigations, etc. | [6 empty] | 0
0
| Temporary Roofing Systems |  |  |  | 1 | ls | 5500 | 5500
| - Temporary enclosures for weathertight, vertical and horizontal openings |  |  |  |  | Included |  | 0
| - Temporary roofing system at critical areas, electrical room, mechanical rooms, etc. |  |  |  |  | Included |  | 0
0
| Miscellaneous | [6 empty] | 0
| - Dumpsters |  |  |  | 10 | ea | 650 | 6500
| - Final Building Clean |  |  |  | 22875 | sf | 0.35 | 8006.25
| - Window Cleaning |  |  |  | 1 | ls | 5500 | 5500
| - Course of Construction Labor/Clean-Up |  |  |  | 20 | wks | 1250 | 25000
| * One (1) man for 40 weeks ($1,200 per wee per man) or approximately $30/hr | [6 empty] | 0
| * Overtime hours excluded | [6 empty] | 0
0
| Additional testing and inspections to meet Netzero requirements |  |  |  | 1 | ls | 15000 | 15000
| - Façade testing, inspections, air tests, etc. | [6 empty] | 0
0
| Owner Moving Costs - w/ below line items |  |  |  |  | w/ below line |  | 0
0
| Custodial Equipment - Excluded |  |  |  |  | Excluded |  | 0
| Bond |  |  |  | 75506.25 | % | 0.02 | 1510.125
| ADDITION | [6 empty] | 0
| Trash Chute |  |  |  | 1 | ea | 10000 | 10000
0
| Material / Man Hoist |  |  |  | 1 | ea | 20000 | 20000
0
| Additional BIM Requirements - 2" and bigger included |  |  |  |  | Included |  | 0
0
| Tower Crane Requirements - N/A - Not required for this project |  |  |  |  | N/A |  | 0
| - Mobilization and Demobilization |  |  |  |  | N/A |  | 0
| - Power Requirements |  |  |  |  | N/A |  | 0
| - Man-hours for Operation |  |  |  |  | N/A |  | 0
0
| Interior Scaffolding at Double Height Spaces |  |  |  | 1 | ls | 30000 | 30000
| - Dance Floors and Shared Scaffolding |  |  |  |  | Included |  | 0
| - Erection and Dismantling, Maintenance While Onsite |  |  |  |  | Included |  | 0
0
| Additional Consulting Costs |  |  |  |  | Included with Design Fees |  | 0
| - Geotechnical investigations, achealogical investigations, etc. | [6 empty] | 0
0
| Temporary Roofing Systems |  |  |  | 1 | ls | 10000 | 10000
| - Temporary enclosures for weathertight, vertical and horizontal openings |  |  |  |  | Included |  | 0
| - Temporary roofing system at critical areas, electrical room, mechanical rooms, etc. |  |  |  |  | Included |  | 0
0
| Miscellaneous | [6 empty] | 0
| - Dumpsters |  |  |  | 30 | ea | 650 | 19500
| - Final Building Clean |  |  |  | 19875 | sf | 0.35 | 6956.25
| - Window Cleaning |  |  |  | 1 | ls | 12500 | 12500
| - Course of Construction Labor/Clean-Up |  |  |  | 50 | wks | 2350 | 117500
| * Two (2) men for 40 weeks ($1,200 per wee per man) or approximately $30/hr | [6 empty] | 0
| * Overtime hours excluded | [6 empty] | 0
0
| Additional testing and inspections to meet Netzero requirements |  |  |  | 1 | ls | 160000 | 160000
| - Façade testing, inspections, air tests, etc. | [6 empty] | 0
0
| Owner Moving Costs - w/ below line items |  |  |  |  | w/ below line |  | 0
0
| Custodial Equipment - Excluded |  |  |  |  | Excluded |  | 0
| Bond |  |  |  | 386456.25 | % | 0.02 | 7729.125
[6 empty] | Subtotal |  | 924946.2
[6 empty] | Escalation | 0% | 0
Temp Constcrution & OSHA | [5 empty] | Total |  | 924946.2
Temporary Building Utilities
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-500 | Temporary Building Electrical Service |  |  |  | 0 | Each | 2500 | 0
01-501 | Electric Consumption Costs |  |  |  | 0 | Months | 3500 | 0
01-505 | Temporary Building Water Service |  |  |  | 0 | Each | 500 | 0
01-506 | Water Consumption Costs |  |  |  | 0 | Months | 350 | 0
0
0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Temporary Building Utilities | [5 empty] | Total |  | 0
Temporary Heat & Weather Protection
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-515 | Temporary Heat (Set Up & Equipment Rental) |  |  |  | 0 | Months | 10000 | 0
01-516 | Fuel Consumption |  |  |  | 0 | Gallons | 0.75 | 0
01-517 | Temporary Gas Setup |  |  |  | 0 | Each | 10000 | 0
01-520 | Standby Personnel |  |  |  | 0 | Weeks | 0 | 0
01-525 | Building Enclosure |  |  |  | 0 | Lump Sum | 0 | 0
01-530 | Snow Removal |  |  |  | 0 | Each | 750 | 0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Temporary Heat & Weather Protection | [5 empty] | Total |  | 0
Material and Personnel Hoisting
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-600 | Material/Personnel Hoist |  |  |  | 0 | Lump Sum | 75000 | 0
01-601 | Hoist Set-up |  |  |  | 0 | Lump Sum | 5000 | 0
01-602 | Hoist Removal |  |  |  | 0 | Lump Sum | 5000 | 0
01-605 | Rooftop Hoist |  |  |  | 0 | Months | 0 | 0
01-610 | Hoist Platform |  |  |  | 0 | Each | 2500 | 0
01-615 | Hoist Operator |  |  |  | 0 | Weeks | 2800 | 0
01-620 | Elevator Operator |  |  |  | 0 | Weeks | 2800 | 0
01-625 | Hanging Scaffold |  |  |  | 0 | Months | 1000 | 0
01-630 | Crane Rental (80-Ton) |  |  |  | 0 | Days | 2000 | 0
01-630 | Crane Rental (30-Ton) |  |  |  | 0 | Days | 1000 | 0
01-640 | Elevator Usage |  |  |  | 0 | Hours | 75 | 0
01-641 | Master Mechanic |  |  |  | 0 | Weeks | 3000 | 0
0
0
0
0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Material and Personnel Hoisting | [5 empty] | Total |  | 0
Engineering, testing, Inspection
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-700 | Testing (Concrete) |  |  |  | 0 | CY | 0 | 0 | By Owner
01-705 | Testing (Structural Steel) |  |  |  | 0 | Tons | 0 | 0 | By Owner
01-710 | Testing (Soil) |  |  |  | 0 | Lump Sum | 0 | 0 | By Owner
01-715 | Test Borings |  |  |  | 0 | Each | 0 | 0 | By Owner
01-720 | Testing (Roofing) |  |  |  | 0 | Lump Sum | 0 | 0 | By Owner
01-721 | Testing (Other) |  |  |  | 0 | Lump Sum | 25000 | 0 | Allowance Per RFP
01-725 | Engineers Layout |  |  |  | 0 | Crew D. | 1200 | 0
01-730 | Site Survey |  |  |  | 0 | Crew D. | 1500 | 0
01-731 | Interior or Trade Layout |  |  |  | 0 | Weeks | 2100 | 0 | W/Trades
01-735 | Geotechnical Consultant |  |  |  | 0 | Lump Sum | 0 | 0
0
0
0
0
0
0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Engineering, testing, Inspection | [5 empty] | Total |  | 0
Miscellaneous Provsions
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-745 | Progress Photos |  |  |  | 0 | Months | 100 | 0
01-746 | Digital Cameras |  |  |  | 0 | Each | 750 | 0
01-750 | Security Service |  |  |  | 0 | Weeks | 0 | 0
01-751 | I.D. Badges/Personnel Control |  |  |  | 0 | Ls | 0 | 0
01-752 | Temporary Parking |  |  |  | 0 | Ls | 0 | 0
01-753 | Shuttle Service |  |  |  | 0 | Ls | 0 | 0
01-754 | Substance Testing/Control |  |  |  | 0 | Ls | 0 | 0
01-755 | Project Sign |  |  |  | 0 | ls | 3500 | 0
01-760 | Directional Signs |  |  |  | 0 | Each | 200 | 0
01-765 | As-Built Drawings |  |  |  | 0 | Ls | 2500 | 0
01-770 | Consultant Fees |  |  |  | 0 | Ls | 0 | 0
01-775 | Legal Fees |  |  |  | 0 | Ls | 0 | 0
0
0
0
0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Miscellaneous Provsions | [5 empty] | Total |  | 0
Insurance, Taxes, Permit
Cost Code | Description |  |  |  | Quantity | Unit | Rate | Total | Notes
01-800 | Liability Insurance |  |  |  | 0 | MM$ | 7200 | 0 | See Summary
01-805 | Phila. Gross Receipts Tax |  |  |  | 0 | MM$ | 2875 | 0 | See Summary
01-810 | Township Tax |  |  |  | 0 | Lump Sum | 0 | 0
01-815 | State\County Tax |  |  |  | 0 | Lump Sum | 0 | 0
01-820 | Builders Risk Insurance |  |  |  | 0 | Lump Sum | 0 | 0
01-825 | Insurances (Other) |  |  |  | 0 | Lump Sum | 0 | 0
01-830 | Zoning Application Fee |  |  |  | 0 | Lump Sum | 125 | 0
01-835 | Building Permit Application Fee |  |  |  | 0 | Lump Sum | 50 | 0
01-835 | Building Permit |  |  |  | 0 | Const.$ | 0 | 0 | See Summary
01-845 | Contractors License Fee |  |  |  | 0 | Lump Sum | 0 | 0
01-850 | Prothonotary |  |  |  | 0 | Lump Sum | 0 | 0
01-860 | Performance & Payment Bonds |  |  |  | 0 | Lump Sum | 0 | 0
0
0
0
0
[6 empty] | Subtotal |  | 0
[6 empty] | Escalation | 0% | 0
Insurance, Taxes, Permit | [5 empty] | Total |  | 0

## ScopeCrossOver
Item No. | Dwg Reference | Spec Reference | Discipline | Scope Issue | Trade | Allowance | confirmed in budget? | Column1 | Scope With | Confirm In Scope | RFI | Comments
1 | L1.1/L1.5 |  | Steel and Concrete | PV Canopies and concrete foundations to be by concrete and not site concrete - VJ | DIV03
2 | L1.1/S602/S603 |  | Concrete | Reatining walls for bio retention and foundation for pool equipment by Concrete and not site concrete - VJ | DIV03
3 | L3.1 |  | Site Concrete | site concrete to carry all small foundations for items like flagpole, fencing, bike racks, benches, bollards etc. | DIV32
4 | L1.3 |  | Fencing | Relocation of batting cage with fencing | DIV32
5 | A1.0 |  | SS | See Mock-up - include kickers for mockup | DIV05
6 | 11/A9.1 |  | SS&MM | See lintel under Storefront (typ) - see 1/A9.1 and for mockup as well | DIV05
7 | A13.1 |  | Athletic Equip | All Fitness equipment to be with Athletic Equipment | DIV11
8 | 1/A.10 |  | Site Concrete | Mock-up slab | DIV32
9 | A6.1/A1.1 |  | Concrete | Geo vault concrete and waterproofing on interior side by WP. Also, waterproofing on interior side of foundation as shown on A6.1 By WP | DIV03
10 | 3/A6.2 |  | Concrete | Vapor barrier below S.O.G | DIV03
11 | A6.3 |  | Solar racks misc met | Solar racks on rooftop by owner. Get an add alternate pricing for them please including connection to roof deck | DIV05
12 | 3/A4.1 |  | Brick/Drywall | Control joints for brick and inside at drywall expansion joints as needed | DIV04
13 | 3/A6.1 |  | Waterproofing | Waterproofing at interior side of foundation by waterproofing - coordinate with concrete for formwork. | DIV07
14 | 3/A6.1 |  | Waterproofing | Waterproofing at geothermal vault on exterior side by wp - look into doing cyrtalline waterproofing on interior side as a value engineering option | DIV07
15 | Electrical |  | Electrical | Primary and telecom - see old SFD and confirm that vault and all is with us | DIV26/28
16 | 4/MS101 |  | HVAC/Geothermal | There is an exterior underground vault - waterpoofer needs to waterproof, misc metals needs to furnish and install manhole cover and ladder, plumbing to furnish and install sump pump | DIV05/07
17 | 1/MS101 |  | HVAC | Heat tracer wire on laterals - who will be doing that | DIV34/26
18 | 4/MS101 |  | Geothermal | 120V sealed utility light with protective shield and 1" electrical conduiot and boxes to be provided and not wired- By electrician | DIV26
Add above this row

## RFI Log
|  |  |  | Client: | DPR & DGS
|  |  |  | Project: | Jelleff Recreation Center
|  |  |  | Architect: | DLR Group
|  |  |  | Dist. Date/Version: | 2026-01-22
|  |  |  | Latest Resp Date: | mm/dd/yyyy
RFI # | Discipline | Question | Date Submited | Subitted By | Design Team Response | Reponse Date
0001 | AL & GLZ | The curtain wall spec calls for a 4-sidded SSG curtain wall system. BOD: Kawneer Clearwall. However, the elevations and details indicate a 2-sided captured system. Furthermore, the performance requirement requested doesn't appear to be easily attainable with the specified Clearwall. Please confirm if Clearwall is desired or if the 1600UT 2-Sided SSG system is required. | 2026-01-16 | MCN
0002 | AL & GLZ | Please clarify if all doors inside of aluminum storefront should be aluminum. The vast majority of the doors located within the storefront, in particular at the interior, are called out as wood doors in the door schedule. Please confirm if all doors within storefront/curtain wall should be aluminum and full lite doors (not narrow lite as also depicted for some openings in the door schedule). | 2026-01-16 | MCN
0003 | AL & GLZ | Glazing spec mentions performance values. Please provide a specific low-E coating to be priced. | 2026-01-16 | MCN
0004 | AL & GLZ | Please confirm no bird frit is required on the glazing | 2026-01-16 | MCN
0005 | AL & GLZ | Please confirm that storefront and curtain wall movements are to not absorb floor and live load movement. If they are intended to, please confirm amount of deflection in the opening needs to be accounted for. | 2026-01-16 | MCN
0006 | AL & GLZ | Details indicate the need/desire for a head receptor (reference A9.1). Please confirm if this is required for this project. | 2026-01-16 | MCN
0007 | A1.4 | Pool Building shown to be CMU enclosure with cast stone - Please confirm that PV Canopy will act as a roof. - S603 shows pool building to have metal deck roofing. Please confirm. | 2026-01-20 | MCN
0008 | General | Please confirm that no Gas line is required on the job. | 2026-01-20 | MCN
0009 | Landscape | Please provide the detail for delaware blend river rock. Additionally please confirm if needs to include base material, fabric and edgeing. Ref L2.2 | 2026-01-20 | MCN
0010 | Landscape | Please provide the detail for Boulders and confirm if the base material is need. L2.2 | 2026-01-20 | MCN
0011 | Landscape | Please verify and clearly label the circle located adjacent to the Fitness Center, refer L1.1. | 2026-01-20 | MCN
0012 | Civil | Please provide utility profiles for the following: AD1 , AD2, AD3,AD4 to clean out co1, from clean co1 out to manhole D1, from D1 to OD1, D1 to CO1,S1 to OD4, S1 to OD5,AD6 to bio, AD7 to AD5 and others that are not shown on the drawings | 2026-01-21 | MCN
0013 | Window Shades | Specification 122413, 1.1A lists motor-operated roller shades with single and double rollers. 1. Are there any manual roller shades in the scope? 2. Where do the double roller shades go? 3. Does CW-3 get roller shades? It was our understanding that the recreation center would receive manual roller shades through-out except for areas with double height spaces (i.e. gym, lobby) | 2026-01-21 | MCN
0014 | Utilities | Previous Documents had an SFD drawings for the utilties. Will one be provided this round? | 2026-01-21 | MCN
0015 | Athletic Equipment | Confirmed that Gared Performance Sports Systems will be an acceptable manufacturer for Sections 116623 and 116653, a substitution request is attached for reference? | 2026-01-21 | MCN
0016 | Athletic Equipment | Section 116623, paragraph 2.2.E.2. specifies steel uprights for the volleyball equipment, generally 3.5” O.D. aluminum is preferred as it is lighter weight. Will aluminum uprights be acceptable as well? | 2026-01-21 | MCN
0017 | Athletic Equipment | Drawings A10.4 & A10.5 indicate the padding stopping just prior to doors and not located in some areas, can it be confirmed that the wall padding should cover the entire perimeter of each gym with the exception of the doors, bleacher alcove and any exposed switches/outlets/cabinets? | 2026-01-21 | MCN
0018 | Game Clock | Section 116623, paragraph 2.5.J. specifies Daktronics BB-2114 shot clocks, which have only shot clock time and no game time. Since there is only one scoreboard, we would suggest having Daktroincs BB-2115 shot clocks, which also include game time. This would allow the players to have view of gametime and shot clock time while looking at each main court basketball goal. Will shot clocks with shot clock time and game time be desired, which are Daktronics BB-2115 | 2026-01-21 | MCN
0019 | Game Clock | Confirm the shot clocks should be mounted to the main court basketball hoops? | 2026-01-21 | MCN
0020 | Electrical | Confirmed that power supplies will be provided for the (2) shot clocks on drawing E2.1, as none shown? | 2026-01-21 | MCN
0021 | Gym Dividers | Section 116653, paragraph 2.1.A. specifies GYC-01, GYC-02 as indicated on drawing A12.1 but this is not included. Can these be included on drawing A12.1 | 2026-01-21 | MCN
0022 | Divider Curtain | Section 116653, paragraph 2.1.C.3. specifies a cable hoisted divider curtain but drawing A11.1, detail 12 indicates a belt hoisted divider curtain. We would recommend a Center Drive Divider Curtain (product data: https://www.garedperfsports.com/products/center-drive-gymnasium-curtain), as this does not require cables or belts and rolls from the center, which will speed up deployment of the curtain. Can you confirm that a GPSS #4050 Center Drive Curtain would acceptable for use on this project? | 2026-01-21 | MCN
0023 | Divider Curtain | Drawing A11.1, detail 12 indicates the divider curtain being mounted centered between two trusses but drawing S103 indicates the divider curtain less than 1’-0” off a truss and not centered, this brings up the following questions: a. The divider curtain will not be centered as shown on the drawing A11.1, detail 12 and the cross braces will prevent what is shown on this detail. Can the curtain be mounted to the bottom of the trusses, which is more typical with +/- 26’-0” truss height? b. Can it be confirmed that any spanning material needed between the two trusses is to be provided by the manufacturer of the divider curtain? | 2026-01-21 | MCN
0024 | Bleachers | Section 000110-3 includes Section 133416.53 – Bleachers under Division 13 but there is no such specification. Can Section 133416.53 be provided? | 2026-01-21 | MCN
0025 | Aluminum and Glazing | Reviewing the door schedule and Storefront schedule several of the doors in storefront assemblies are called out to be wood doors however details show them as aluminum. Please confirm the following doors as either wood or aluminum; 104 (SF-15), 105 (SF-15A), 106 (SF-17), 110B (SF-7), 111A (SF-18), 210 (SF-20), 211 (SF-21), 213 (SF-22), 215 (SF-24). | 2026-01-21 | MCN
0026 | Railing | Provide missing spec section 055213 METAL HANDRAILS | 2026-01-22 | MCN
0027 | Railing | Provide missing spec section 055213.13 PIPE AND TUBE RAILINGS - INTERIOR | 2026-01-22 | MCN
0028 | Railing | Provide missing spec section 057300 METAL PICKET GUARDRAIL | 2026-01-22 | MCN
0029 | Railing | Provide missing spec section 057300.13 DECORATIVE METAL RAILINGS | 2026-01-22 | MCN
0030 | Railing | Provide missing spec section 057500 DECORATIVE FORMED METAL | 2026-01-22 | MCN
RFI LOG ONE CUT OFF | RFI LOG ONE CUT OFF | RFI LOG ONE CUT OFF | RFI LOG ONE CUT OFF | RFI LOG ONE CUT OFF | RFI LOG ONE CUT OFF
ADD ABOVE

## SOWTemplate
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | TEMPLATE | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Scope | Y |  |  |  |  | 0
3 | Scope | Y |  |  |  |  | 0
4 | Scope | Y |  |  |  |  | 0
5 | Scope | Y |  |  |  |  | 0
6 | Scope | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## VEs
#ERROR!
#ERROR!
#ERROR!
#ERROR!
Value Engineering Summary
V.E. | Item Description |  |  | Cost | Cost Impact | Notes
No. |  |  |  | Impact
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
|  |  | Potential V.E.Total | 0 | 0
Cost impact Less 10%

## MCN Summary
DPR & DGS
Jelleff Recreation Center
3265 S St NW, Washington, DC 20007
Date | mm/dd/yyy | Area: | 20000 |  | Architect: | DLR Group
Rev. | V0 | Estimator(s): | MK, Trade Estimators |  | Engineer: | Various
CSI | Description |  |  |  |  | Total Cost | Cost / GSF | 1 | 1
10000 | General Requirements |  |  |  |  | 416160 | 20.808 | 1 | 2 |  | GENERAL REQUIREMENTS
24100 | Building Demolition |  |  |  |  | 315180 | 15.759 | 1 | 3 |  | BUILDING DEMOLITION
33000 | Cast-In-Place Concrete |  |  |  |  | 1546885.61 | 77.3443 | 1 | 4 |  | CAST-IN-PLACE CONCRETE
34000 | Precast Concrete |  |  |  |  | 0 | 0 | 1 | 5 |  | PRECAST CONCRETE
42000 | Masonry |  |  |  |  | 1427888.82 | 71.3944 | 1 | 6 |  | MASONRY
44000 | Stone |  |  |  |  | 0 | 0 | 1 | 7 |  | STONE
51000 | Structural Steel |  |  |  |  | 1808970 | 90.4485 | 1 | 8 |  | STRUCTURAL STEEL
55000 | Miscellaneous Metals |  |  |  |  | 0 | 0 | 1 | 9 |  | MISCELLANEOUS METALS
61000 | Rough Carpentry |  |  |  |  | 145656 | 7.2828 | 1 | 10 |  | ROUGH CARPENTRY
62000 | Finish Carpentry |  |  |  |  | 0 | 0 | 1 | 11 |  | FINISH CARPENTRY
64000 | Architectural Millwork |  |  |  |  | 110399.7 | 5.52 | 1 | 12 |  | ARCHITECTURAL MILLWORK
71000 | Waterproofing/Dampproofing |  |  |  |  | 353474.88 | 17.6737 | 1 | 13 |  | WATERPROOFING/DAMPPROOFING
72400 | Eifs/Stucco |  |  |  |  | 0 | 0 | 1 | 14 |  | EIFS/STUCCO
72700 | Air Barrier |  |  |  |  | 0 | 0 | 1 | 15 |  | AIR BARRIER
78000 | Spray Applied Fireproofing |  |  |  |  | 0 | 0 | 1 | 16 |  | SPRAY APPLIED FIREPROOFING
74000 | Siding And Wall Panels |  |  |  |  | 194004 | 9.7002 | 1 | 17 |  | SIDING AND WALL PANELS
75000 | Roofing |  |  |  |  | 901053.0176 | 45.0527 | 1 | 18 |  | ROOFING
79000 | Joint Sealants |  |  |  |  | 50184 | 2.5092 | 1 | 19 |  | JOINT SEALANTS
81000 | Doors, Frames, & Hardware |  |  |  |  | 155478.192 | 7.7739 | 1 | 20 |  | DOORS, FRAMES, & HARDWARE
83000 | Special Doors |  |  |  |  | 17229.84 | 0.86149 | 1 | 21 |  | SPECIAL DOORS
84000 | Glass & Glazing |  |  |  |  | 639450.24 | 31.9725 | 1 | 22 |  | GLASS & GLAZING
92000 | Drywall And Ceilings |  |  |  |  | 1207715.7 | 60.3858 | 1 | 23 |  | DRYWALL AND CEILINGS
92400 | Plaster |  |  |  |  | 0 | 0 | 1 | 24 |  | PLASTER
93000 | Tile |  |  |  |  | 66059.28 | 3.303 | 1 | 25 |  | TILE
96000 | Flooring |  |  |  |  | 221540.94 | 11.077 | 1 | 26 |  | FLOORING
99000 | Painting & Wall Covering |  |  |  |  | 113230.2 | 5.6615 | 1 | 27 |  | PAINTING & WALL COVERING
100000 | Specialties |  |  |  |  | 370199.82 | 18.51 | 1 | 28 |  | SPECIALTIES
110000 | Equipment |  |  |  |  | 0 | 0 | 1 | 29 |  | EQUIPMENT
120000 | Furnishings |  |  |  |  | 187204.272 | 9.3602 | 1 | 30 |  | FURNISHINGS
123000 | Casework & Countertops |  |  |  |  | 0 | 0 | 1 | 31 |  | CASEWORK & COUNTERTOPS
140000 | Elevators |  |  |  |  | 344148 | 17.2074 | 1 | 32 |  | ELEVATORS
210000 | Fire Protection |  |  |  |  | 0 | 0 | 1 | 33 |  | FIRE PROTECTION
220000 | Plumbing |  |  |  |  | 983280 | 49.164 | 1 | 34 |  | PLUMBING
230000 | H.V.A.C. |  |  |  |  | 1857313.92 | 92.8657 | 1 | 35 |  | H.V.A.C.
260000 | Electrical |  |  |  |  | 2827110.132 | 141.3555 | 1 | 36 |  | ELECTRICAL
270000 | Low Voltage |  |  |  |  | 428816.16 | 21.4408 | 1 | 37 |  | LOW VOLTAGE
310000 | Earthwork |  |  |  |  | 640382.52 | 32.0191 | 1 | 38 |  | EARTHWORK
320000 | Site Improvements |  |  |  |  | 1047698.039 | 52.3849 | 1 | 39 |  | SITE IMPROVEMENTS
330000 | Site Utilities |  |  |  |  | 1833210.565 | 91.6605 | 1 | 40 |  | SITE UTILITIES
[5 empty] | Total Trades Cost | 20209923.85 | 1010.4962 | 1 | 41 | CHECK | FALSE | 20936943.13 | <---- FROM BID SHEET
| PERSONNEL GENERAL CONDITIONS |  |  | 6.284% |  | 1270000 | 63.5 | 1 | 2 |  | PERSONNEL GENERAL CONDITIONS
| GENERAL CONDITIONS-NON PERSONNEL |  |  |  |  | 0 | 0 | 1 | 3 |  | GENERAL CONDITIONS-NON PERSONNEL
| PUBLIC SPACE IMPROVEMENTS (BY OWNER) |  |  |  |  | 0 | 0 | 1 | 4 |  | PUBLIC SPACE IMPROVEMENTS (BY OWNER)
| ESCALATION |  |  |  |  | 0 | 0 | 1 | 5 |  | ESCALATION
| PERFORMANCE & PAYMENT BOND |  |  |  |  | 324450.7439 | 16.2225 | 1 | 6 |  | PERFORMANCE & PAYMENT BOND
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 7 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 8 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 9 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 10 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  |  |  | #ERROR! |  | 1 | 11 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 12 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 13 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 14 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 15 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 16 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 17 |  | #ERROR!
| #ERROR! |  |  | #ERROR! |  | #ERROR! |  | 1 | 18 |  | #ERROR!
[5 empty] | Construction Cost | #ERROR! | #ERROR! | 1 | 19
| GC/CM Fee |  |  | #ERROR! |  | 825000 | 41.25 |  |  |  | GC/CM FEE
[5 empty] | Total Cost | #ERROR! | #ERROR! |  |  | CHECK | #ERROR! | 26107200.28 | <---- FROM BID SHEET
Alt | Description |  |  |  |  | Total Cost |  |  |  | Alternate Tab
1 | Text |  |  |  |  | 0
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
[5 empty] | Total Cost of Alternates | 0

## Bid Sheet
| Client | DPR & DGS |  |  |  |  | Total GSF: | 20000 | Bid Date: | 2026-02-01
| Project | Jelleff Recreation Center |  |  |  |  | Weeks: | 78 | Estimators: | MK, Trade Estimators
| Location | 3265 S St NW, Washington, DC 20007 |  |  |  |  | ^^^ drop down - weeks or mos |  | Revision: | V0
| Architect | DLR Group |  |  |  |  | Weeks: | 78
| Engineer | Various |  |  |  |  | Months: | 18
[7 empty] | Bidders | [7 empty] | Certitifcation
Est. | CSI for Summary | Trade | Previous Budget | Total (GMP 2026) | Delta (New-old) | Cost / GSF | 1 | 2 | 3 | 4 | 5 | 6 | 7 | $ PARTICIPATING | 1 | 2 | 3 | 4 | 5 | 6 | 7
MK | 10000 | GENERAL REQUIREMENTS | 416160 | 416160 | 0 | 20.808
| 61000 | 01 - FINAL CLEANING |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 61000 | 01 - SURVEY |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Berg Demo | Marc's Demo | D&H | Celtic Demo
SK | 24100 | 02 - DEMOLITION | 448800 | 244800 | -204000 | 12.24 | 157922.52 | 244800 | 260100 | 295800 |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | Incl above |  |  |  | D&H - Completed
SK | 24100 | 02 - ABATEMENT | 0 | 70380 | 70380 | 3.519 | 70380 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Alcoa | LA Howard | Blackwood of DC
VJ | 33000 | 03 - CONCRETE | 1867154.88 | 1546885.61 | -320269.2696 | 77.3443 | 1546885.61 | 1793764.86 | 1833576.48 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
| 33000 | 03 - GYP UNDERLAYMENT |  |  | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 34000 | 03 - PRECAST |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Forsythe DC | Hammer Masonry | JPN Masonry
NT | 42000 | 04 - MASONRY | 1578348 | 1427888.82 | -150459.18 | 71.3944 | 1383999.24 | 1427888.82 | 1491087 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
| 44000 | 04 - STONE |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | East Coast | Iron Fab | BOLDMARK??
VJ | 51000 | 05 - SS & MM | 2231250 | 1808970 | -422280 | 90.4485 | 1808970 | 1882308 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 55000 | 05 - MISC METALS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 55000 | 05 - EXTERIOR RAILINGS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 61000 | 06 - FIBER REINFORCED PLASTICS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
MCN Build
MK | 61000 | 06 - ROUGH CARPENTRY | 189210 | 145656 | -43554 | 7.2828 | 145656 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 61000 | 06 - WOOD FRAMING |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 62000 | 06 - FINISH CARPENTRY |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Biltco LLC | Columbia Woodworking | Arch wood??
NT | 64000 | 06 - MILLWORK | 173279.64 | 110399.7 | -62879.94 | 5.52 | 102000 | 110399.7 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 71000 | 07 - BUILDING INSULATION |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/roofing |  |  |  | Davenport TruTeam | HRGM | Forsythe | LP
JC | 71000 | 07 - WP & AB |  | 353474.88 | 353474.88 | 17.6737 | 265967.346 | 343474.086 | 353474.88 | 413506.062 |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
| 72400 | 07 - EIFS/STUCCO |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 72700 | 07 - AIR BARRIER |  | 0 | 0 | 0 | IN WP ABOVE | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 78000 | 07 - FIREPROOFING |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 74000 | 07 - EXTERIOR PANELS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/roofing |  |  |  | RK International | Chu | Prestige
JC | 74000 | 07 - METAL PANELS |  | 194004 | 194004 | 9.7002 | 185476.8 | 194004 | 286108.25 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Chu | HRGM | Forsythe
JC | 75000 | 07 - ROOFING | 1961479.38 | 901053.0176 | -1060426.362 | 45.0527 | 883728 | 901053.0176 | 912211.5 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
MCN Build
MK | 79000 | 07 - JOINT SEALANTS | 65076 | 50184 | -14892 | 2.5092 | 50184 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Washington Door | Allegany Door | Aorbis
NT | 81000 | 08 - DOORS, FRAMES, HARDWARE | 239021.7 | 155478.192 | -83543.508 | 7.7739 | 155478.192 | 153000 | 204301.92 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/dfh |  |  |  | Miner Corp | McKeon Door DC, Inc. | OHD Co. | Door Systems Inc
NT | 83000 | 08 - SPECIAL DOORS |  | 17229.84 | 17229.84 | 0.86149 | 10606.2456 | 12894.9012 | 17229.84 | 17442 |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
| 84000 | 08 - GLASS & GLAZING |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | AGM Contracting | Ranger | Prestige | Innovo
JC | 84000 | 08 - ALUM & GLASS | 749516.4 | 639450.24 | -110066.16 | 31.9725 | 488784 | 585738.06 | 621435 | 639450.24 |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
| 84000 | 08 - INT GLASS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[8 empty] | Uniconstruction | Dynamic Contracting
NT | 92000 | 09 - DRYWALL & CEILINGS | 1141518.18 | 1207715.7 | 66197.52 | 60.3858 |  | 814269.06 | 1207715.7 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Floors Etc | Admiral
NT | 93000 | 09 - TILE | 107100 | 66059.28 | -41040.72 | 3.303 | 66059.28 | 102000 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 96000 | 09 - TERRAZZO |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Admiral | Floors Etc
NT | 96000 | 09 - CARPET, RESILIENT, RUBBER FLOORING | 680734.74 | 221540.94 | -459193.8 | 11.077 | 221540.94 | 283407 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Precision Wall Tech | Uniconstruction | District Construction
NT | 99000 | 09 - PAINT & WALL COVERING | 197052.78 | 113230.2 | -83822.58 | 5.6615 | 129540 | 109497 | 113230.2 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
W/Specialties
| 100000 | 10 - TOILET ACCESSORIES |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
W/Specialties
| 100000 | 10 - TOILET PARTITIONS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/specialties |  |  |  | Gelberg Signs | Modulex Mid Atlantic
NT | 100000 | 10 - SIGNAGE | 0 | 25798.86 | 25798.86 | 1.2899 | 25798.86 | 42067.0644 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Nelson Specialties | Newton Distributing | Washington Door | Aorbis
NT | 100000 | 10 - SPECIALTIES (Visual Display Units, TA's FEC's, Lockers, op partitions,matts) | 254229.9 | 344400.96 | 90171.06 | 17.22 | 344400.96 | 351463.338 | 386921.7 | 464375.5836 |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
W/Specialties
| 100000 | 10 - LOCKERS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 61000 | 12 - FF&E |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Singer | 11400, Inc.
VJ | 11 40 00 | 11 - Kitchen Equipment | 890209.08 | 132227.7 | -757981.38 | 6.6114 | 132227.7 | 170850 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/kitchen equipment |  |  |  | TJ Distributor | Degler Whiting
VJ | 116600 | 11 - ATHELTIC EQUIPMENT | 0 | 200940 | 200940 | 10.047 | 200940 | 205576.92 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  | carrying matts w/specialties |  | ADD FOR FITNESS EQUIPMENT |  |  | DES | SBE
MK | 120000 | 12 - FF&E | 292369.74 | 101292.12 | -191077.62 | 5.0646 | 101292.12 | 79125.75 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 123000 | 12 - RESIDENTIAL CABINETS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 123000 | 12 - COUNTERTOPS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/FFE |  |  |  | Total Shading
MK | 120000 | 12 - WINDOW TREATMENTS | 0 | 85912.152 | 85912.152 | 4.2956 | 85912.152 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
Millenium- TBD
MK | 130000 | 13 - POOLS | 393851.58 | 393851.58 | 0 | 19.6926 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
District
MK | 140000 | 14 - ELEVATORS | 183600 | 344148 | 160548 | 17.2074 | 344148 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Bayside | Continental
MK | 210000 | 21 - FIRE PROTECTION | 230112 | 0 | -230112 | 0 | 170834.7 | 154020 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | CornerStone | Tomko | VMG
MK | 220000 | 22 - PLUMBING | 1140105 | 983280 | -156825 | 49.164 | 983280 | 867000 | 770742.6 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | CornerStone | Tomko | VMG
MK | 230000 | 23 - HVAC | 3679675.5 | 1857313.92 | -1822361.58 | 92.8657 | 1857313.92 | 2509710 | 2057238 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Mona | Robinson | Freestate
WS | 260000 | 26 - ELECTRICAL | 3214618.74 | 2827110.132 | -387508.608 | 141.3555 | 2790118.2 | 2827110.132 | 2983500 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Genesys | Robinsons
WS | 270000 | 27 - LOW VOLTAGE | 420051.3 | 428816.16 | 8764.86 | 21.4408 | 428816.16 | 484923.3 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 310000 | 31 - SUPPORT OF EXCAVATION |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Hadcon | GS
MK | 310000 | 31 - EARTHWORK & SITE DEMO&E,S | 1005720 | 640382.52 | -365337.48 | 32.0191 | 640382.52 | 672180 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 310000 | 31 - DEEP FOUNDATIONS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 310000 | 31 - DEWATERING |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/landscaping |  |  |  | Metro Paving | Ruston
SK | 320000 | 32 - ASPHALT |  | 353866.05 | 353866.05 | 17.6933 | 345540.3 | 353866.05 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 320000 | 32 - SEGMENTAL WALLS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/landscaping |  |  |  | Alcoa | AMA Construciton
SK | 320000 | 32 - SITE CONCRETE |  | 305592 | 305592 | 15.2796 | 221911.965 | 305592 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 320000 | 32 - PAVERS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/landscaping |  |  |  | Long Fence
SK | 320000 | 32 - SITE FENCING |  | 103858.44 | 103858.44 | 5.1929 | 103858.44 | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
| 320000 | 32 - SITE FURNISHINGS |  | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | BeechField | Complete
SK | 320000 | 32 - LANDSCAPING & SITE FURN | 2168044.68 | 284381.5488 | -1883663.131 | 14.2191 | 261977.412 | 284381.5488 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
[7 empty] | Hadcon | Magnolia | Oakridge
MK | 330000 | 33 - WET UTILITIES | 1419136.2 | 1037865.565 | -381270.6348 | 51.8933 | 1037865.565 | 987972 | 1338751.612 |  |  |  |  | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/wet utillities | w/electrical |  |  | Dry utilties system
MK | 330000 | 33 - DRY UTILITIES |  | 0 | 0 | 0 | waiting for their number | [6 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
|  |  | w/HVAC |  |  |  | Allied | Brightcore
MK | 330000 | 33 - GEOTHERMAL |  | 795345 | 795345 | 39.7672 | 795345 | 892500 | [5 empty] | 0 | [7 empty] | Section 2 - Bid Breakdown
# NEED CSI #
|  | TEMPLATE |  | 0 | 0 | 0 | [7 empty] | 0
TRADE SUBTOTAL |  |  | 27337425.42 | 20936943.13 | -6400482.292 | 1046.8472 | [7 empty] | 0
|  | PERSONNEL GENERAL CONDITIONS | 1270000 | 1270000 | 0 | 63.5
|  | GENERAL CONDITIONS-NON PERSONNEL | 0 | 0 | 0 | 0
|  | PRECONSTRUCTION FEE (15% Base Design Build Fee) | 100000 | 100000 | 0 | 5
|  | DESIGN FEE (BY OWNER) | 0 | 0 | 0 | 0
|  | PERMITS (BY OWNER) | 0 | 0 | 0 | 0
|  | PUBLIC ART - Owner Allowance | 100000 | 100000 | 0 | 5
|  | UTILITIES CONSUMPTION (BY OWNER) | 0 | 0 | 0 | 0
|  | PUBLIC SPACE IMPROVEMENTS (BY OWNER) | 0 | 0 | 0 | 0
| 5% | OWNER DIRECTED CONSTRUCTION CONTINGENCY | 1440371.247 | 1120347.156 | -320024.0906 | 56.0174
|  | CONTAMINATED SOIL (BY OWNER) | 0 | 0 | 0 | 0
|  | TESTING AND INSPECTIONS (BY OWNER) | 0 | 0 | 0 | 0
| 2% | INSURANCE BURDEN | 604955.9237 | 470545.8057 | -134410.1181 | 23.5273
| 0% | BUILDERS RISK INSURANCE | 0 | 0 | 0 | 0
| 0% | DESIGN CONTINGENCY | 0 | 0 | 0 | 0
| 4% | CONSTRUCTION CONTINGENCY | 1234110.0844 | 959913.4436 | -274196.6408 | 47.9957
| 0% | ESCALATION | 0 | 0 | 0 | 0
| 1.3% | PERFORMANCE & PAYMENT BOND | 417129.2085 | 324450.7439 | -92678.4646 | 16.2225
| CONSTURCTION COST |  | 32503991.88 | 25282200.28 | -7221791.606 | 1264.11
0
| FIXED | GC/CM Fee | 825000 | 825000 | 0 | 41.25
0
| TOTAL |  | 33328991.88 | 26107200.28 | -7221791.606 | 1305.36
|  | GCs/month |  | GCs % of total
|  | 0 |  | 0%
0%
GRs/month
23120

## Demo
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Celtic Demo |  |  | Marc's Demo |  |  | ACECO |  |  | Berg Demo |  |  | D&H |  |  | Rath |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Alex Bruns |  |  | Marc Dardaghani |  |  | mstocker@acecoworld.com |  |  | Shawn Wells |  |  | Hessler Espinal |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0 |  | MBE/CBE
[7 empty] | Email: |  | Alex@celticdemo.com |  |  | marc@marcsdemolitions.com | [5 empty] | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Berg Demo | 154826 | 0 | 3096.52 | 157922.52 |  | 0
Trade: | 02 - DEMOLITION | [5 empty] | Phone: |  | 703-739-9103 |  |  | 703-678-6719 |  |  | 443-677-5122 |  |  | 681-285-4995 |  |  | 240-495-4725 |  |  | Number |  |  | Number |  | 2 | Marc's Demo | 240000 | 0 | 4800 | 244800 |  | 0
Rev/Date: | Date Issued 01-27-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO | 3 | D&H | 255000 | 0 | 5100 | 260100 |  | 0
[9 empty] | Base Bid: | 290000 |  | Base Bid: | 240000 |  | Base Bid: | 358597 |  | Base Bid: | 154826 |  | Base Bid: | 255000 |  | Base Bid: | 260000 |  | Base Bid: |  | 4 | Celtic Demo | 290000 | 0 | 5800 | 295800 |  | 0
Contact: | Safi Khan | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | ACECO | 358597 | 0 | 7171.94 | 365768.94 |  | 0
Email: | safi.khan@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 5800 | 2% | Bond: | 4800 | 2% | Bond: | 7171.94 | 2% | Bond: | 3096.52 | 2% | Bond: | 5100 | 2% | Bond: | 5200 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-674-5842 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 295800 |  | Total Bid: | 244800 |  | Total Bid: | 365768.94 |  | Total Bid: | 157922.52 |  | Total Bid: | 260100 |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 4 |  |  | 2 |  |  | 5 |  |  | 1 |  |  | 3 |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 290000 |  |  | 240000 |  |  | 358597 |  |  | 154826 |  |  | 255000 |  |  | 260000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Structural and Interior Demo | # | $ |  |  |  | 0
5 | [6 empty] | 0
6 | Key Quantity Breakdown | [5 empty] | 0
7 | Stuff | # | CY |  |  |  | 0
8 | Thing | # | SF |  |  |  | 0
9 | Stuff 2 | # | LF |  |  |  | 0
10 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y | [5 empty] | Y | [8 empty] | Y
A | Specifications
| Division 01 - General Requirements | Y | [5 empty] | Y | [8 empty] | Y
| Division 2 - Demolition | Y | [5 empty] | Y | [8 empty] | Y
| 31 00 00 - Earthwork | Y | [5 empty] | Y | [8 empty] | Y | by others
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y | [8 empty] | Y
2 | BUILDING & EX. STRUCTURE DEMOLITION | Y | [5 empty] | Y | [8 empty] | Y
3 | Demolition of existing building structure in its entirety. | Y | [5 empty] | Y | [8 empty] | Y
4 | Conduct structural demolition shown in drawing including exterior walls, roof and floor Structure, utilities, concrete slab, and footings. | Y | [5 empty] | Y | [8 empty] | Y
5 | Remove Exterior steps and guardrails / handrails. | Y | [5 empty] | Y | [8 empty] | Y
6 | Raze all interior walls, partitions, ceilings, mezzanine ﬂoors, doors, windows, and ﬁnishes, as well as mechanical, electrical, and plumbing services as indicated in the plans, except as noted here-in. | Y | [5 empty] | Y | [8 empty] | Y
7 | Remove interior stair and guardrails / handrails. | Y | [5 empty] | Y | [8 empty] | Y
8 | Remove existing roof drains, rooftop equipment and associated curbs and flashing | Y | [5 empty] | Y | [8 empty] | Y | Make safe/abatement by others
9 | Demo & haul off from the site. | Y | [5 empty] | Y | [8 empty] | Y
10 | Demo existing structure & footings/grade beams as per structure drawings | Y | [5 empty] | Y | [8 empty] | Y
11 | Gas fireplace insert, shut-off valve, and flue to be removed. Gas to Be cut & capped by others. | Y | [5 empty] | Y | [8 empty] | Y
12 | FP piping, equipment, valves, pump, to be removed. | Y | [5 empty] | Y | [8 empty] | Y
13 | Perform all demolition activities involving mechanical, electrical, and plumbing (MEP) systems in full compliance with established safety requirements, regulatory standards, and approved demolition protocols. | Y | [5 empty] | Y | [8 empty] | Y
14 | Assure to take extra precautions for demolition activities around the historic tree areas(exisitng Trees to Remain). | Y | [5 empty] | Y | [8 empty] | Y | Tree protection by others
15 | Be cognitive of all existing areas and portions designated to remain as indicated on the drawings, any damage incurred the sole responsibility of the subcontractor to repair. | Y | [5 empty] | Y | [8 empty] | Y
16 | Salvage and protect reusable components for future installation or recycling, as directed by the project specifications and/or GC. | Y | [5 empty] | Y | [8 empty] | N/A
17 | Salavage of bricks to neat piles for reuse. Cleaning of bricks is by others | Y | [5 empty] | Y | [8 empty] | N/A
18 | Coordinate with all trades to ensure safe removal, proper handling, and compliance with site requirements. | Y | [5 empty] | Y | [8 empty] | Y
19 | Safe excavation for the Work is the responsibility of this subcontractor. Assume open cut/layback as needed. | Y | [5 empty] | Y | [8 empty] | Y | Demolition contractor to remove foundation walls in coordination with excavation/ lay back / backfill by earthwork
20 |  | Y | [5 empty] | Y | [8 empty] | Y
21 | STANDARD / GENERAL SCOPE | Y | [5 empty] | Y | [8 empty] | Y
22 | Provide all equipment, material, labor, tools, supervision, etc. | Y | [5 empty] | Y | [8 empty] | Y
23 | Cooperate with Owner's Soil Testing Agency | Y | [5 empty] | Y | [8 empty] | Y
24 | Provide necessary shoring and support for demo Work | Y | [5 empty] | Y | [8 empty] | N/A
25 | Multiple mobilizations for the Work. | Y | [5 empty] | Y | [8 empty] | Y | 1
26 | Traffic control as required for the Work | Y | [5 empty] | Y | [8 empty] | Y | Flag man nly
27 | Any necessary saw-cutting for the Work | Y | [5 empty] | Y | [8 empty] | N/A
28 | Dust control for the Work. | Y | [5 empty] | Y | [8 empty] | Y | Wwater Source by others
0
C | Exclusions
1 | HAZ MAT remediation | N | by others
2 | Cut, Cap and Safe of MEP | N | by MEP Subcontractor
3 | Earthwork | N | by others
4 | Site Demo | N | by others
5 | Tree Protection | N | by others
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 |  | ---> | [6 empty] | 5 weeks | total duration
4 |  | --->
5 |  | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 |  | --->
9 |  | --->
10 |  | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Conc
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | LA Howard |  |  | Blackwood of DC |  |  | Alcoa |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Lazerrick Howard |  |  | Dan Amaro |  |  | Rahi |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | lahowardconstruction@msn.com |  |  | damaro@blackwood-dc.com |  |  | rahi@alcoacm.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Alcoa | 1301239.52 | 215315 | 30331.0904 | 1546885.61 |  | 0
Trade: | 03 - CONCRETE | [5 empty] | Phone: |  | 202-543-5399 |  |  | 771-215-9514 |  |  | (240) 505-6913 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | LA Howard | 1528643 | 229950 | 35171.86 | 1793764.86 |  | 0
Rev/Date: | Date Issued 01-26-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Blackwood of DC | 1037365 | 760259 | 35952.48 | 1833576.48 |  | 0
[9 empty] | Base Bid: | 1528643 |  | Base Bid: | 1037365 |  | Base Bid: | 1301239.52 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Vaibhav Jain | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 229950 |  | Adjustments: | 760259 |  | Adjustments: | 215315 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | vaibhav.jain@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 35171.86 | 2% | Bond: | 35952.48 | 2% | Bond: | 30331.0904 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-494-1156 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 1793764.86 |  | Total Bid: | 1833576.48 |  | Total Bid: | 1546885.61 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 3 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 1528643 |  |  | 1037365 |  |  | 1301239.52
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Pool Structure | # | $ |  |  |  | 0
6 | Geo Vault | # | $ |  |  |  | 0
6 | [6 empty] | 0
7 | Key Quantity Breakdown | [5 empty] | 0
8 | Foundation and Footing | # | CY |  |  |  | 0
9 | SOG | # | SF |  |  |  | 0
10 | SOMD | # | SF |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 031000 - CONCRETE FORMING AND ACCESSORIES | Y
| 032000 - CONCRETE REINFORCING | Y
| 033000 - CAST-IN-PLACE CONCRETE | Y
| 035300 - CONCRETE TOPPING | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | Use this scope as a reference only. This scope was made to highlight major parts of the scope of work. Please provide pricing for a full scope of work based off the Plans and Specifications provided. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
2 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
3 | All cast-in-place concrete within the building footprint to include mats, footings, grade beams, walls, pits, columns, piers, SOG, elevated slabs, topping slabs, beams, slab folds, drop heads, stairs, pads, curbs, etc. shown on the drawings to the lines and grades indicated | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
4 | Form to profiles indicated, strip & reshore - designed & engineered w/PE stamp | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
5 | Supply & place ready-mix; incl. admixtures | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
6 | Excavation from SOG subgrade for all footings, grade beams & pits. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
7 | Excavation for footings. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
8 | Bench excavations per OSHA requirements | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
9 | Backfill and compaction to SOG subgrade after pour | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
10 | Locate spoils in a central location for removal from site by others | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
11 | Advise of spoil quantity to be disposed of ________CY. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
12 | Fine grading for the Work from +/- 0.2’ of design subgrade (of slab-on-grade). | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
13 | Concrete Work as indicated on the Contract Documents, including but not limited to the following. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
14 | Wall and column footing, grade beam and piers. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
15 | Spread footing, refer schedule on S101 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
16 | Grade Beam & concrete pier, refer schedule on S-112 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
17 | Continuous wall & retaining wall footing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
18 | Stair footing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
19 | CIP Concrete wall | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
20 | Bioretention walls, refer sheet S602. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
21 | Slab-on-Grade & Slab Edge. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
22 | SOG including rebar/WWF, vapor barrier & stone base. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
23 | Turn down slab, thickened slab. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
24 | Interior slab on grade stairs | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
25 | Slab on Metal deck. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
26 | Light weight concrete with reinforcement. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
27 | Pool Building, as per S603, including. | Y |  |  |  |  | 0 | N |  | 14635 | Y |  | 14635 | Y
28 | Wall Footing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
29 | PV Canopy post footing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
30 | Underground Geo Vault , as per A2.3, including. | Y |  |  |  |  | 0 | Y |  |  | Y |  | 530309 | Y
31 | Concrete wall & footing. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
32 | SOG including rebar/WWF, vapor barrier & stone base. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
29 | Concrete Pad for Mockup work, demo by others, refer A1.0 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
30 | Elevator pit concrete slab, footing and walls. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
31 | Concrete fills for steel pan stairs & landings, bollards, etc. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
32 | Concrete equipment pads and equipment curbs | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
33 | Epoxy coated rebar/WWF at exposed area for the Work. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
34 | Polystyrene or Rigid insulation for the Work | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
35 | Provide perimeter safety cable, orange safety fence & toe boards at edges of elevated slabs & shaft openings until permanent is in place; removal by others | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
36 | Provide pumps for dewatering of rain water in footing excavations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
37 | Strip placing sequence for SOG; construction joints as shown | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
38 | Vapor barrier and aggregate subbase under SOG | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
39 | Saw cutting of control joints in SOG; isolation joints around columns | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
40 | Build box outs for MEP penetrations for placement by others; strip boxes | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
41 | Insulation under slab on grade at building perimeter | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
42 | Allowance of [10] cubic yards for additional MEP pads not indicated | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
43 | Accessories to include chamfer strips, waterstops, form ties, release agent, keyways, blockouts, PEJs, reglets, etc. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
44 | Setting of embedded items to include anchor bolts, weld plates/angles, curtainwall embeds, corner guards, railing sleeves, tennis fencing post, stair nosing's, wedge anchors, window washing tie-backs, etc. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
45 | Furnish and install dovetail slot where concrete abuts brick masonry. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
46 | Setting of column leveling plates and grouting of column base. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
47 | Grouting of elevator sills | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
48 | Furnish and install all reinforcing bars (cut to length, bent) and wire mesh | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
49 | Furnish only rebar for CMU walls | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
50 | Provide embedded dowels in slabs at CMU wall locations as req'd | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
51 | Epoxy-coated rebar where indicated | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
52 | Accessories to include chairs, tie wire, trim bars, tendon sheathing, anchorage devices/couplers, coating compound, grease | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
53 | Included costs to provide 3-day break cylinders to facilitate early formwork stripping operations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
54 |  | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
55 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
56 | Tentative concrete schedule/duration (concrete start: August 2026) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
57 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
58 | Shop drawings, submittals, product data, mix designs, test reports, certs, etc. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
59 | All cranes, pumps, tools, equipment, hoisting, supervision, etc. for this work | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
60 | Cooperate with Owner's testing service & provide samples | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
61 | Winter protection as needed | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
62 | Provide dumpster service for your work | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
63 |  | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
64 | PV Canopy At Site | Y |  |  |  |  | 0 | N |  | 215315 | Y |  | 215315 | N |  | 215315
65 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Mass Excavation for large mat foundations | N | by earthwork
2 | Backfill of perimeter foundation walls | N | by earthwork
3 | Site Concrete (all concrete outside of building footprint) | N | by site concrete
4 | Fill for bollards | N | by site concrete
5 | Caulking | N | by caulk
6 | Testing and Inspection | N | by Owner
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Footing & Foundation | --->
4 | SOG | --->
5 | SOMD | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Submittals & shop Drawings | --->
9 |  | --->
10 |  | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Masonry
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Forsythe DC |  |  | Hammer Masonry |  |  | JPN Masonry |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Zach Travers |  |  | Nancy Zelaya |  |  | Oswaldo Guevara |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | zach@forsytheinc.net |  |  | nancy@hammermasonry.com |  |  | oguevara@jpnmasonry.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Forsythe DC | 1356862 | 0 | 27137.24 | 1383999.24 |  | 0
Trade: | 04 - MASONRY | [5 empty] | Phone: |  | 301-848-7325 |  |  | 202-890-4600 ext 105 |  |  | 202-510-1132 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Hammer Masonry | 1399891 | 0 | 27997.82 | 1427888.82 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | JPN Masonry | 1400950 | 60900 | 29237 | 1491087 |  | 0
[9 empty] | Base Bid: | 1356862 |  | Base Bid: | 1399891 |  | Base Bid: | 1400950 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 60900 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 27137.24 | 2% | Bond: | 27997.82 | 2% | Bond: | 29237 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 1383999.24 |  | Total Bid: | 1427888.82 |  | Total Bid: | 1491087 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | 3 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y |  | 1356862 |  | taxes excl | 1399891 |  | taxes excl | 1400950
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Interior CMU | # | $ |  |  |  | 0 | Y |  |  | Y | 174435 |  | Y | 133670
5 | Brick Veneer | # | $ |  |  |  | 0 | Y |  |  | Y | 975564 |  | Y | 1082000
6 | Cast Stone | # | $ |  |  |  | 0 | Y |  |  | Y | 249892 |  | Y | 185280
7 | Rebar Installation | # | $ |  |  |  | 0 | Y |  |  | Y | 4000 |  | Y
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | CMU | # | SF |  |  |  | 0 | Y |  |  | Y | 4144 |  | Y | 4249
11 | Brick Veneer | # | SF |  |  |  | 0 | Y |  |  | Y | 18761 |  | Y | 21875
12 | Cast Stone | # | LF |  |  |  | 0 | Y |  |  | Y | 1295 |  | Y | 1452
13 | Masonry Rebar (Install Only. Furnish By Others) | # | TONS |  |  |  | 0 | Y |  |  | Y | 1 |  | Y | 1.5
14 | Precast Panels | # | SF |  |  |  | 0 | Y |  |  | Y | 373
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 04 20 00 - Unit Masonry | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 04 72 00 - Cast Stone Masonry | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 05 12 00 - Structural Steel Framing (as applicable to this Bid Package) | Y | [8 empty] | Y
| 07 21 00 - Thermal Insulation (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 07 27 26 - Fluid-Applied Membrane Air Barriers (as applicable to this Bid Package) | Y | [8 empty] | N
| 07 62 00 - Sheet Metal Flashing and Trim (as applicable to this Bid Package) | Y | [8 empty] | Y
| 07 92 00 - Joint Sealants (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | N |  |  | Y
| 08 11 13 - Hollow Metal Doors and Frames (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
2 | This section outlines the requirements for furnishing, fabrication, and installation of all CMU and brick veneer systems as indicated in the Contract Documents. All masonry Work must meet specified design, quality, and performance standards. | [9 empty] | Y
3 | CMU: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
4 | Furnish & install CMU walls to lines & grades, and all indicated masonry accessories, with sizes based on partition types and typical details: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
5 | Below grade CMU indicated on the Contract Documents | Y | [5 empty] | Y |  |  | Y |  |  | Y
6 | Interior wall partitions at stairs and elevator and all other areas indicated on Contract Documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
7 | Exterior CMU wall back-up partitions | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
8 | Grout CMU bond beams as shown | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
9 | CMU/precast lintels or bond beams at openings in CMU walls | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
10 | Install reinforcing (rebar furnished by others) grouted into cells/bond beams as noted | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
11 | Mason is responsible for providing rebar drawings | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
12 | Provide quantity (ton) of rebar drawings | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
13 | Firestop the top of CMU walls as required | Y |  |  |  |  | 0 |  |  |  | Y
14 | Control joint material and backer rod. Finish caulk by others. | Y |  |  |  |  | 0 |  |  |  | N
15 | Grouting of elevator door frames and hollow metal (HM) door frames. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
16 |  | Y |  |  |  |  | 0
17 | Brick Veneer (Main Building & Pool House): | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
18 | Furnish and install all CMU walls according to the specified lines, grades, and all indicated masonry accessories, with sized based on partition types and typical details: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
19 | 4" below grade CMU | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
20 | 8" CMU at pool house | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
21 | Modular brick | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
22 | Brick soldier course header | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
23 | Through wall flashing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
24 | Metal drip edge | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
25 | Weeps, cavity drainage material | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
26 | End dams | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
27 | Furnish brick tie anchor plates to drywall contrtactor for installation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
28 | Furnish & install brick tie anchor plates on sheathing. Provide Alternate | ALT |  |  |  |  | 0 | Y |  |  | Y |  |  | N | ADD | 60000
29 | Grout cavity insulation behind masonry façade, includimg under copings and at joints | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
30 | Compressible filler in masonry façade, including under copings and at joints | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
31 | Control joint material and backer rod. Finish caulk by others. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
32
33 | Cast Stone (Main Building &Pool House) : | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
34 | Furnish & install all cast stone to sizes, shapes, lines & grades indicated: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
35 | Cast stone cap at parapet, TYP | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
36 | Provide cast stone shapes as shown | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
37 | Install handset cast stone banding, sills, lintels and copings (under 300 lbs) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
38 | Cast stone coping | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
39 | Finishes and colors as indicated | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
40 | Include means of lifting and setting all pieces | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
41 | Provide anchors/dowels/attachment hardware necessary for installation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
42 | Mortar/grout | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
43
44 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y
45 | Provide all tools, equip, scaffolding, swing stages, lifts, hoisting, etc for your work | Y |  |  |  |  | 0 | Y
46 | Allow scaffolding to be used by waterproofing and drywall contractor for installation of sheathing, vapor barrier, brick ties and any damproofing necessary | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N | SEE ALT BELOW | 900
47 | Accessories to include mortar materials (mixed on-site) horizontal reinforcing, compressible filler/fire safing at all tops of CMU partitions, masonry anchors/ties, dovetails, wedge anchors, mortar net, weep hole fillers, etc | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
48 | Field cut masonry to fit site conditions and the work of other trades | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
49 | Install loose steel lintels (furnished by others) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
50 | Tooling of joints | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
51 | Vertical control joints as shown or at least 30'-0" o.c. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
52 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
53 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
54 | Samples, product data, mix designs, test reports, certs, etc | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
55 | Mock-up | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
56 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
C | Exclusions
1 | Rebar material | N | by concrete |  |  |  |  | N |  |  | N |  |  | N
2 | Misc metals supports, braces, clip angles, embeds, etc. | N | by metals |  |  |  |  | N |  |  | N |  |  | N
3 | Wood blocking | N | by carpentry |  |  |  |  | N |  |  | N |  |  | N
4 | Metal flashing material | N | by roofer; glazier |  |  |  |  | N |  |  | N |  |  | N
5 | Sealant and backer rod | N | by caulk |  |  |  |  | N |  |  | N |  |  | N
6 | Setting of hollow metal frames | N | by carpentry |  |  |  |  | N |  |  | N |  |  | N
7 | Winter Protection | N | by GC, if req'd |  |  |  |  | N |  |  | N |  |  | N
8 | Air Barriers | N | by waterproofing |  |  |  |  | N |  |  | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y | [8 empty] | Y | TBD |  | Y | Yes
2 | Advise of Durations
3 | Submittals | ---> | [8 empty] | Y | 2 weeks |  | Y | 2-3 weeks
4 | Drawings | ---> | [8 empty] | Y | 4-5 weeks |  | Y | 3-4 weeks
5 | Brick Install | ---> | [8 empty] | Y | TBD |  | Y | 20 weeks
6 | Advise of Lead Times:
7 | Brick Veneer | ---> | [8 empty] | Y | TBD |  | Y | 20 weeks
8 | Cast Stone | ---> | [8 empty] | Y | TBD |  | Y | 10-12 weeks
9 | CMU | ---> | [8 empty] | Y | 1 week |  | Y | 3-4 weeks
10
Allowances
1
2
3
4
Alternates
1 | Alternate #1 - Furnish & install brick tie anchor plates on sheathing | # | [8 empty] | Y | Incl in base bid |  | N | ADD | 60000
2 | Alternate #2 - Installation of brick tie anchor plates on sheathing | # | [11 empty] | N
3 | Sub Alternate - Allow scaffolding to be used by other trades - ADD $900/each sub/weekly | # | [11 empty] | Y | ADD Above
4 | Sub Alternate - Use Glen grey 56-DD in lieu Watsontown Rosemount molded - DEDUCT - $12,000 | # | [11 empty] | Y
5 | Sub Alternate - F &I 2" Z girt as shown in 1 &2/A6.2. Add - $102,810 | # | [11 empty] | Y
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SS & MM
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Boldmark Steel |  |  | East Coast |  |  | Iron Fab |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Samy Abisaleh |  |  | Steven |  |  | Luyao Ji |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | samy@boldmarksi.com |  |  | steven@eastcoastironmd.com |  |  | l.ji@ironfs.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | East Coast | 1145400 | 628100 | 35470 | 1808970 |  | 0
Trade: | 05 - SS & MM | [5 empty] | Phone: |  | 443-255-1330 |  |  | Number |  |  | 240-543-8017 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Iron Fab | 1225000 | 620400 | 36908 | 1882308 |  | 0
Rev/Date: | Date Issued 01-26-26 | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 1495040 |  | Base Bid: | 1145400 |  | Base Bid: | 1225000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Vaibhav Jain | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 6500 |  | Adjustments: | 628100 |  | Adjustments: | 620400 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | vaibhav.jain@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 30030.8 | 2% | Bond: | 35470 | 2% | Bond: | 36908 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-494-1156 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | 1808970 |  | Total Bid: | 1882308 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 1495040 |  |  | 1145400 |  |  | 1225000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Structural Steel | # | $ |  |  |  | 0
5 | Misc. Metals | # | $ |  |  |  | 0
6 | [6 empty] | 0
7 | Key Quantity Breakdown | [5 empty] | 0
8 | Column, Beams, Joist etc. | # | Tons |  |  |  | 0
9 | Steel Decking | # | SQ |  |  |  | 0
10 | Stairs & Landing | # | EA |  |  |  | 0
11 | Railing & Guardrail | # | LF |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 051200 - STRUCTURAL STEEL FRAMING | Y
| 051213 - ARCHITECTURALLY EXPOSED STRUCTURAL STEEL FRAMING | Y
| 052100 - STEEL JOIST FRAMING | Y
| 055000 - METAL FABRICATIONS | Y
| 055113 - METAL PAN STAIRS | Y
| 055213 - METAL HANDRAILS | Y | Not Provided, RFI'ed
| 055213.13 - PIPE AND TUBE RAILINGS - INTERIOR | Y | Not Provided, RFI'ed
| 057100 - DECORATIVE METAL STAIRS | Y
| 057300 METAL PICKET GUARDRAIL | Y | Not Provided, RFI'ed
| 057300.13 DECORATIVE METAL RAILINGS | Y | Not Provided, RFI'ed
| 057300 METAL PICKET GUARDRAIL | Y | Not Provided, RFI'ed
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | Use this scope as a reference only. This scope was made to highlight major parts of the scope of work. Please provide pricing for a full scope of work based off the Plans and Specifications provided. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
2 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
3 | Fabricate, furnish & erect all structural steel framing shown on the structural drawings to include Columns, beams, joist, brace framing, support framing, wind frames, outriggers & all supplemental angles, channels, braces, kickers, stiffeners, gussets, base plates, bent plates, bearing plates, other misc. connection steel req'd for a complete structural assembly. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
4 | Beams and joist framing, as shown on structural drawings. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
5 | Includes long span joists | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
6 | Includes pool structure | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
7 | Steel decking as shown on structural drawings, Refer 4 on S102 & 3 on S103. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
8 | Floor deck - 3”, 20 gage galvanized. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
9 | RD1, Roof Deck – 1-1/2"-18 gage galvanized. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
10 | RD2, Roof Deck – 1-1/2"-18 gage galvanized, Accoustical Deck. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
11 | Pool Roof Deck – 1-1/2"-18 gage galvanized | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
12 | Deck support angle (DSA) all sides of deck as per typical details. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
13 | Steel columns, post and base plates, including but not limited to following: | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
14 | Steel Column Schedule , as per sheet S201. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
15 | Provide anchor bolts and templates to Structural concrete for setting | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
16 | Brace framing, including diagonal supports, plates, stiffeners etc. for the Work. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
17 | Bracing at new structure as per sheet S230. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
18 | Splicing of vertical steel as required for logistical constraints | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
19 | Additional framing and support as noted, including but not limited to: | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
20 | Support for floor deck or roof deck openings. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
21 | Support for basketball hoops | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
22 | Roll-up curtain/Divider Beam | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
23 | Elev. Hoist Beam | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
24 | Operable Partitions | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
25 | Cont. galvanized brick relieving angle connnected to steel structure | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
26 | Thermal break angle as per note 3 on J/S009 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
27 | Pour stops, bent plates, and angles at slab edge | Y |  |  |  |  | 0 |  |  |  | N |  | 15000 | N |  | 15000
28 | Kickers, tabs, angles, plates, stiffeners, connections, supports as noted | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
29 | MISC METALS | Y |  |  |  |  | 0 |  |  |  | Y |  | 229600 | Y |  | 225000
30 | Ext. & Int. Metal pan stairs and landings, including but not limited to | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
31 | Stair A (S101) - Refer A1.1 & A7.1 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
32 | Stair B (S101) - Refer A1.1 & A7.1 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
33 | Int. &Ext. Railings system, Refer sheet A7.2, including but not limited to : | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
34 | Stair A - Guardrail w/handrail and wall handrail incl. woven wire mesh. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
35 | Stair B - Baluster guardrail w/handrail and wall handrail. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
36 | Stair Balcony - Guardrail w/wire mesh in channel frame,angle per 6 & 11/A7.2 | Y |  |  |  |  | 0 |  |  |  | N |  | 15000 | Y
37 | Pool Stairs - Handrail, refer detail 6/AQ1.1. | Y |  |  |  |  | 0 |  |  |  | N |  | 7500 | N |  | 7500
38 | Elevator Metals, including but not limited to following. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
39 | Sill Angles | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
40 | Pit Ladder | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
41 | Sump pump pit grate and angle | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
42 | Galvanized steel angle support angl, including but not limited to following: for | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
43 | Storefront sill, refer typ. detail 1/A9.1 etc. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
44 | Window sill, refer typ. detail 11 & 12/A9.1 etc. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
45 | Window head, refer typ. detail 7 & 8/A9.1 etc. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
46 | Provide continuous brick ledge/releiving angle not connected to strutural steel , refer typ detail on S501 & S505. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
47 | Jamb and head steel angle for coiling counter door. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
48 | Provide all steel ladders, including but not limited to following | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
49 | Over the deck steel ladders at pool, refer note 1 on AQ1.0 & 1/AQ1.1. | Y |  |  |  |  | 0 |  |  |  | N |  | 4500 | Y |  | 4500
50 | Access ladder and steel hatch access door at geo vault, refer A2.3 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
51 | Access ladder for roof at Laundry room 221, refer A1.2 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
52 | Provide all steel required for mockup section, removal by others, refer A1.0. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
53 | CMU wall bracing, including, but not limited to, both perpendicular and parallel bracing as typically indicated on sheet S-206. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
54 | Furnish only misc. metals, inclusive of: | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
55 | Loose lintels | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
56 | Steel bollards, refer landscape drawings | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y |  | 11900
57 |  | Y |  |  |  |  | 0 |  |  |  | Y
58 | ADD ALTERNATE | Y |  |  |  |  | 0 |  |  |  | Y |  | 350000 | N |  | 350000
59 | Solar Panel Aluminum Canopy Structure system, refer sheet L1.1. - Lumos | Y |  |  |  |  | 0 |  |  |  | Y
60 | Pool Deck - Type A & C, refer L1.4 | Y |  |  |  |  | 0 |  |  |  | Y
61 | Parking Space - Type A & B, refer L1.5 | Y |  |  |  |  | 0 |  |  |  | Y
62 | Aluminum Post and beams, PV Panels by others. | Y |  |  |  |  | 0 |  |  |  | Y
63 |  | Y |  |  |  |  | 0 |  |  |  | Y
64 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 |  |  |  | Y
65 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 |  |  |  | Y
66 | Include PE calcs & design, stamps for connections and metal stairs | Y |  |  |  |  | 0 |  |  |  | Y
67 | Shop dwgs, samples, product data, certs, test reports, etc. | Y |  |  |  |  | 0 |  |  |  | Y
68 | Provide all material, tools, equipment, hoisting, supervision req'd for your work | Y |  |  |  |  | 0 |  |  |  | Y
69 | Shop fab holes in steel for connections & for penetrations shown for other trades | Y |  |  |  |  | 0 |  |  |  | Y
70 | Bare steel if fireproofed and at connection points; galvanized if exposed to weather, in cavity wall or embedded, shop prime balance of steel | Y |  |  |  |  | 0 |  |  |  | Y
71 | Perform field measurements, or modify in field as needed | Y |  |  |  |  | 0 |  |  |  | Y
72 | Perform all welded and bolted connections; moment connections | Y |  |  |  |  | 0 |  |  |  | Y
73 | Grinding of welds & touch up finishes after connections are made | Y |  |  |  |  | 0 |  |  |  | Y
74 | Provide temporary bracing, guys during erection as needed | Y |  |  |  |  | 0 |  |  |  | Y
75 | Furnish & deliver all embeds to include anchor bolts, weld plates/angles, etc. | Y |  |  |  |  | 0 |  |  |  | Y
76 | Furnish bearing plates to be installed in masonry walls to Mason for installation | Y |  |  |  |  | 0 |  |  |  | Y
77 | Furnish anchor bolts and templates to Structural concrete for installation | Y |  |  |  |  | 0 |  |  |  | Y
78 | Touch up finishes where damaged by welding, handling | Y |  |  |  |  | 0 |  |  |  | Y
79 | Provide all fasteners and misc. steel for complete assemblies | Y |  |  |  |  | 0 |  |  |  | Y
80 | Furnish all embedded items relating to your work (weld plates/angles, anchor bolts, sleeves, etc.) | Y |  |  |  |  | 0 |  |  |  | Y
81 | Grout railing posts into sleeves, or core drill if sleeves are not furnished | Y |  |  |  |  | 0 |  |  |  | Y
82 | Galvanize if exposed to weather, in wall cavity or embedded; shop prime balance | Y |  |  |  |  | 0 |  |  |  | Y
83 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0 |  |  |  | Y
84 |  | Y |  |  |  |  | 0 |  |  |  | Y
85 | Add for Flagpole - F+I | Y |  |  |  |  | 0 | Y | P- FW HAX | 6500 | Y | P- FW HAX | 6500 | Y | P- FW HAX | 6500
86 |  | Y |  |  |  |  | 0 |  |  |  | Y
87 |  | Y |  |  |  |  | 0 |  |  |  | Y
88 |  | Y |  |  |  |  | 0 |  |  |  | Y
0
C | Exclusions
1 | Testing and Inspection | No | by Owner
2 | Bike Racks | N | w/ Site
3 | Install of loose lintels | N | by Mason
4 | Install of pipe bollards or concrete fill of pipe bollards | N | by Site Concrete
5
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Beams & Columns | --->
4 | Metal Deck | --->
5 | Stairs and Landing | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Fabrication | --->
9 | Structural Steel | --->
10 | Misc. Metals | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Rough Carpentry
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 06 - ROUGH CARPENTRY | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Roof blocking | Y |  |  |  |  | 0
3 | Roof cants | Y |  |  |  |  | 0
4 | **Other specific wood blocking items** | Y |  |  |  |  | 0
5 | Plywood backer boards at Electrical/Telephone Closets | Y |  |  |  |  | 0
6 | Plywood backer boards at mirrors | Y |  |  |  |  | 0
7 | Plywood substrate at stone vanities | Y |  |  |  |  | 0
8 | Plywood substrate at shingle/metal roof decks (under roofing) | Y |  |  |  |  | 0
9 | **Other specific plywood items** | Y |  |  |  |  | 0
10 | Wood or sheet metal In-wall blocking (coordinate with drywall): | Y |  |  |  |  | 0
11 | At wall mounted handrails | Y |  |  |  |  | 0
12 | At wall mounted cabinetry (base and wall cabinets; countertops) | Y |  |  |  |  | 0
13 | At toilet accessories | Y |  |  |  |  | 0
14 | At wall bumpers | Y |  |  |  |  | 0
15 |  | Y |  |  |  |  | 0
16 | Receive, Unload, Catalogue, Store and Install only items: | Y |  |  |  |  | 0
17 | Commercial Buildings: | Y |  |  |  |  | 0
18 | Hollow metal frames (coordinate with drywall) | Y |  |  |  |  | 0
19 | Hollow metal doors | Y |  |  |  |  | 0
20 | Wood doors | Y |  |  |  |  | 0
21 | Door hardware sets | Y |  |  |  |  | 0
22 | Louvers | Y |  |  |  |  | 0
23 | Fire extinguisher cabinets | Y |  |  |  |  | 0
24 | Toilet Accessories | Y |  |  |  |  | 0
25 | **Other specialty items** | Y |  |  |  |  | 0
26 | Additional Items for Residential Construction: | Y |  |  |  |  | 0
27 | Running wood trim (list: wood base, shoe moulding, window sills/aprons, entry door trim, casings, crown mouldings, chair rails, etc) | Y |  |  |  |  | 0
28 | Wood or wire shelving | Y |  |  |  |  | 0
29 | Pre-hung doors | Y |  |  |  |  | 0
30 | Hardware for pre-hung doors | Y |  |  |  |  | 0
31 | Set appliances in place | Y |  |  |  |  | 0
32 | Hard Installation of range hoods and mounted microwaves | Y |  |  |  |  | 0
41 |  | Y |  |  |  |  | 0
42 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
43 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
44 | Include all anchors and fasteners for this work | Y |  |  |  |  | 0
45 | Furnish anchor bolts for sill plates for installation into conc/masonry by others | Y |  |  |  |  | 0
46 | Perform all necessary field cutting of lumber/plywood | Y |  |  |  |  | 0
47 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
48 | Clean up to MCN dumpster | Y |  |  |  |  | 0
49 |  | Y |  |  |  |  | 0
50 | LEED Issues: | Y |  |  |  |  | 0
51 | FSC-certified lumber | Y |  |  |  |  | 0
52 | No CCA pressure treatment for lumber | Y |  |  |  |  | 0
53 | Plywood/substrates free of urea formaldehyde | Y |  |  |  |  | 0
54 | Low VOC adhesives | Y |  |  |  |  | 0
54 | Sorting of debris for recycling | Y |  |  |  |  | 0
54 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Covered walkways | N | by GC
2 | Temporary partitions | N | by GC
3 | Floor protection | N | by GC
4 | Elevator cab protection | N | by GC
5 | Construction signs | N | by GC
6 | Temporary stairs, ramps, rails and platforms | N | by GC
7 | Guardrails and toeboards | N | by GC
8 | Clean up Labor | N | by GC
9 | Blocking occurring outside of walls for millwork items | N | by Millwork
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Millwork
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Biltco LLC |  |  | Columbia Woodworking |  |  | Architectural Wood |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Andres Fernandez |  |  | Jay Blass |  |  | Wade Oosterbeek |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | afernandez@biltco.com |  |  | jay@cwwcorp.com |  |  | woosterbeek@arcwoodwv.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Biltco LLC | 100000 | 0 | 2000 | 102000 |  | 0
Trade: | 06 - MILLWORK | [5 empty] | Phone: |  | 567-350-2445 |  |  | 202-526-2387 |  |  | 703-901-3889 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Columbia Woodworking | 108235 | 0 | 2164.7 | 110399.7 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 100000 |  | Base Bid: | 108235 |  | Base Bid: | 80000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 2000 | 2% | Bond: | 2164.7 | 2% | Bond: | 1600 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 102000 |  | Total Bid: | 110399.7 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [12 empty] | Waiting on Wade's responses to my inquiries
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y |  | 100000 | Y |  | 108235 | Y |  | 80000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Casework | # | $ |  |  |  | 0
5 | Millwork | # | $ |  |  |  | 0
6 |  | # | $ |  |  |  | 0
Section 3 - Scope of Work
| Furnish and Install All Items UON (Uinless Otherwise Noted) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
| Division 05 - Metals (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
| 06 41 16 - Plastic-Laminate-Clad Architectural Cabinets | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
| 06 61 16 - Solid Surfacing Fabrications | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
| 07 92 00 - Joint Sealants (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
| 08 14 16 - Flush Wood Doors (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Casework: | Y |  |  |  |  | 0
3 | Provide all casework and cabinetry indicated on Contract Documents: | Y |  |  |  |  | 0 | Y
4 | Solid surface countertops | Y |  |  |  |  | 0 | Y
5 | Quartz solid surface countertops | Y |  |  |  |  | 0 | ALT | Incl in base bid
6 | Back/sidesplash where tile is not indicated | Y |  |  |  |  | 0 | Y
7 | Upper cabinets | Y |  |  |  |  | 0 | Y
8 | Lower cabinets | Y |  |  |  |  | 0 | Y
9 | Toe kicks | Y |  |  |  |  | 0 | Y
10 | [6 empty] | 0
11 | Millwork: | Y |  |  |  |  | 0
12 | Provide all millwork indicated on Contract Documents: | Y |  |  |  |  | 0
13 | Desks | Y |  |  |  |  | 0
14 | Trophy case | Y |  |  |  |  | 0
15 | Shelving (Glass shelving) | Y |  |  |  |  | 0
16
17 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
18 | Include all plastic laminate, melamine, wood veneer paneling, hardwood trim, wood support framing, plywood substrates & blocking related to your work | Y |  |  |  |  | 0
19 | Shop-applied natural finishes, colors and stains as specified | Y |  |  |  |  | 0
20 | Field paint at reveals in millwork as noted | Y |  |  |  |  | 0
21 | Include all stainless steel paneling and trim associated with your work | Y |  |  |  |  | 0
22 | Include miscellaneous metal support framing for desks/cabinetry | Y |  |  |  |  | 0
24 | Include all caulking and sealants associated with your work | Y |  |  |  |  | 0
25 | Provide cut-outs/grommets for plumbing/electrical req'ments as needed | Y |  |  |  |  | 0
26 | Include all cabinetry hardware including keyed locks, drawer pulls, sliders, grommet covers, adjustable shelving items, etc | Y |  |  |  |  | 0
27 | Include all anchors and fasteners for this work | Y |  |  |  |  | 0
28 | Obtain field measurements or modify millwork in the field to fit site conditions | Y |  |  |  |  | 0
29 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
30 | Clean up to MCN dumpster | Y |  |  |  |  | 0
31 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0
C | Exclusions
1 | In-wall blocking | N | By Drywall Subcontractor | [7 empty] | N
2 | Protection of finished work | N | By GC | [7 empty] | N
3 | Typical wood doors | N | By DFH Subcontractor | [7 empty] | N
4 | Field painting of paint-grade millwork items; filling of holes/caulking | N | By Painting Subcontractor | [7 empty] | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Submittals | --->
4 | Shop Drawings | --->
5 | Duration for Submittals and Shop Drawings | --->
6 | Advise of Lead Times:
7 | Material 1 | --->
8 | Material 2 | --->
9 | Material 3 | --->
Allowances
1 | Add Alternate #1 - Solid Surfaces (QZ-01)
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Waterproof
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Davenport TruTeam |  |  | HRGM |  |  | LP |  |  | Forsythe |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Will Rego |  |  | John Maviglia |  |  | Dan Morin |  |  | Zach Travers |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | william.rego@truteam.com |  |  | john@hrgm.com |  |  | dan@lproofingllc.com |  |  | zach@forsytheinc.net |  |  | Email |  |  | Email |  |  | Email |  | 1 | Davenport TruTeam |  | 260752.3 | 5215.046 | 265967.346 |  | 0
Trade: | 07 - WP & AB | [5 empty] | Phone: |  | 240-749-4668 |  |  | 202-889-8400 |  |  | 778-208-1125 |  |  | 301-848-7325 |  |  | Number |  |  | Number |  |  | Number |  | 2 | HRGM |  | 336739.3 | 6734.786 | 343474.086 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Forsythe |  | 346544 | 6930.88 | 353474.88 |  | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | LP |  | 405398.1 | 8107.962 | 413506.062 |  | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 260752.3 |  | Adjustments: | 336739.3 |  | Adjustments: | 405398.1 |  | Adjustments: | 346544 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 5215.046 | 2% | Bond: | 6734.786 | 2% | Bond: | 8107.962 | 2% | Bond: | 6930.88 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 265967.346 |  | Total Bid: | 343474.086 |  | Total Bid: | 413506.062 |  | Total Bid: | 353474.88 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | 4 |  |  | 3 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Waterproofing | # | $ |  |  |  | 0 |  |  | 33730 |  |  | 47449 |  |  | 95900 |  |  | 54986
5 | Elevator interior and exterior | # | $ |  |  |  | 0
6 | Air Barriers | # | $ |  |  |  | 0 |  |  | 139810 |  |  | 202078 | P |  | 222285.8 |  |  | 185306
7 | Joint Sealants | # | $ |  |  |  | 0 | P |  | 77212.3 | P |  | 77212.3 | P |  | 77212.3 |  |  | 70193
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 |  | # | CY |  |  |  | 0
11 |  | # | SF |  |  |  | 0
12 |  | # | LF |  |  |  | 0
13 |  | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y | [5 empty] | Y | [8 empty] | Y
| 071326 - Self-Adhering Sheet Waterproofing | Y | [5 empty] | Y | [8 empty] | Y
| 071413 - Hot Fluid-Applied Rubberized Asphalt Waterproofing | Y | [5 empty] | Y | [8 empty] | Y
| 071616 - Crystalline Waterproofing | Y | [5 empty] | Y | [8 empty] | Y
| 071800 - Traffic Coatings | Y | [5 empty] | Y | [8 empty] | Y
| 072100 - Thermal Insulation | Y | [5 empty] | Y | [8 empty] | Y
| 072600 - Vapor Retarders | Y | [5 empty] | Y | [8 empty] | Y
| 072726 - Fluid-Applied Membrane Air Barriers | Y | [5 empty] | Y | [8 empty] | Y
| 078413 - Penetration Firestopping | Y | [5 empty] | Y | [8 empty] | Y
| 078443 - Joint Firestopping | Y | [5 empty] | Y | [8 empty] | Y
| 079200 - Joint Sealants | Y | [5 empty] | Y | [8 empty] | Y
B | Inclusions
1 | Self-Adhering Sheet Waterproofing | Y |  |  |  |  | 0 | Y | [8 empty] | Y
2 | Modified bituminous sheet waterproofing B.O.D.: | Y |  |  |  |  | 0 | Y | [8 empty] | Y
3 | Carlisle Coatings & Waterproofing Inc; CCW MiraDRI 860/861 or comparable product per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
4 | Self-adhering rubberized-asphalt strips per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
5 | Include all materials and accessories to include, but not limited to; | Y |  |  |  |  | 0 | Y | [8 empty] | Y
6 | Primer | Y |  |  |  |  | 0 | Y | [8 empty] | Y
7 | Surface conditioner | Y |  |  |  |  | 0 | Y | [8 empty] | Y
8 | Liquid membranes | Y |  |  |  |  | 0 | Y | [8 empty] | Y
9 | Substrate patching membrane | Y |  |  |  |  | 0 | Y | [8 empty] | Y
10 | Metal termingation bars | Y |  |  |  |  | 0 | Y | [8 empty] | Y
11 | Nonwoven-geotextile faced molded-sheet drainage panels with polymeric film B.O.D.: | Y |  |  |  |  | 0 | Y | [8 empty] | Y
12 | Carlisle Coatings & Waterproofing Inc; CCW MiraDRAIN 6000 or camparable product per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
13 | Insulation drainage panels to comply with Section 072100 "Thermal Insulation" | Y |  |  |  |  | 0 | Y | [8 empty] | Y
14 | Waterproofing warranty per specifications for a period of five years from date of Substantial Completion | Y |  |  |  |  | 0 | Y | [8 empty] | Y
15 | Installer's special warranty per specification for a warranty period of two years | Y |  |  |  |  | 0 | Y | [8 empty] | Y
16 | Obtain waterproofing materials, protection course, and molded-sheet drainage panels from single source from single manufacturer | Y |  |  |  |  | 0 | Y | [8 empty] | Y
17
18 | Crystalline Waterproofing | Y |  |  |  |  | 0 | Y | [8 empty] | Y
19 | Crystalline waterproofing B.O.D.: | Y |  |  |  |  | 0 | Y | [8 empty] | Y
20 | KOSTER American Corporation; NB 1 Grey or comparable product per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
21 | Include all meterials and accessories to include, but not limited to; | Y |  |  |  |  | 0 | Y | [8 empty] | Y
22 | Patching compoung per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
23 | Potable water | Y |  |  |  |  | 0 | Y | [8 empty] | Y
24
25 | Fluid-Applied Membrane Air Barrer | Y |  |  |  |  | 0 | Y | [8 empty] | Y | GE Elemax 2600
26 | High-build vapor-retarding air barrier | Y |  |  |  |  | 0 | Y | [8 empty] | Y
27 | Installed dry film thickness per manufacturer's instruction of 35 mils or thicker | Y |  |  |  |  | 0 | Y | [8 empty] | Y
28 | Synthetic polymer tape manufacturer per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
29 | Physical and performance properties per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
30 | High-build vapor-permeable air barrier | Y |  |  |  |  | 0 | Y | [8 empty] | Y
31 | Installed dry film thickness per manufacturer's instruction of 35 mils or thicker | Y |  |  |  |  | 0 | Y | [8 empty] | Y
32 | Synthetic polymer tape manufacturer per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
33 | Physical and performance properties per specifications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
34 | Include all materials and accessories to include, but not limited to, as recommended in writing by air-barrier manufacturer to product a complete air-barrier assembly; | Y |  |  |  |  | 0 | Y | [8 empty] | Y
35 | Primers | Y |  |  |  |  | 0 | Y | [8 empty] | Y
36 | Transition strips, termination strips | Y |  |  |  |  | 0 | Y | [8 empty] | Y
37 | Joint reinfocring fabric and strips | Y |  |  |  |  | 0 | Y | [8 empty] | Y
38 | Joint sealants | Y |  |  |  |  | 0 | Y | [8 empty] | Y
39 | Counterflashing strips | Y |  |  |  |  | 0 | Y | [8 empty] | Y
40 | Flashing sheets | Y |  |  |  |  | 0 | Y | [8 empty] | Y
41 | Metal termination bars | Y |  |  |  |  | 0 | Y | [8 empty] | Y
42 | Termination mastic | Y |  |  |  |  | 0 | Y | [8 empty] | Y
43 | Substrate patching materials | Y |  |  |  |  | 0 | N/A | [8 empty] | Y
44 | Adhesives | Y |  |  |  |  | 0 | Y | [8 empty] | Y
45 | Tapes | Y |  |  |  |  | 0 | Y | [8 empty] | Y
46 | Foam sealants | Y |  |  |  |  | 0 | N/A | [8 empty] | Y
47 | Lap sealants | Y |  |  |  |  | 0 | Y | [8 empty] | Y
48 | ABAA certified installers and supervisors per specfications | Y |  |  |  |  | 0 | Y | [8 empty] | Y
49 | Obtain primary air-barrier materials and air-barrier accessories from single source from single manufacturer | Y |  |  |  |  | 0 | Y | [8 empty] | Y
50 | Include all ABAA rees, testing and reports | Y |  |  |  |  | 0 | Y | [8 empty] | Y |  | 18165
51 | Include all warranty requirements per specificaitons | Y |  |  |  |  | 0 | Y | [8 empty] | Y
52
53 | Provide an add/alt for the drain tile | Y |  |  |  |  | 0 | [9 empty] | Y
54
55 | Refer to general note 3 on AQ4.0 stating the inside surfaces of the backwash catch basin much be watperoofing | Y |  |  |  |  | 0 | [9 empty] | Y
56
57 | Refer to 1/A6.1 for wall section at basement and curtainwall and include the necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
58 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
59 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
60 | Watperoofing | Y |  |  |  |  | 0 | [9 empty] | Y
61 | Drainage composite layer | Y |  |  |  |  | 0 | [9 empty] | Y
62 | Ensure fabric facing SOE to extend from at minimum 2 ft. below finish grade to 1 ft. above bottom of footing | Y |  |  |  |  | 0 | [9 empty] | Y
63 | Refer to 2/A6.1 for wall section at gym and include necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
64 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
65 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
66 | Refer to 3/A6.1 for wall section at gym and include necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
67 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
68 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
69 | 2" (R-10 min.) extruded polystyrene insulation extended down to 24" below grade | Y |  |  |  |  | 0 | [9 empty] | Y
70 | Refer to 4/A6.1 for wall section at vestibule/circulation and include necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
71 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
72 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
73 | 2" (R-10 min.) extruded polystyrene insulation extended down to 24" below grade | Y |  |  |  |  | 0 | [9 empty] | Y
74 | Refer to 1/A6.2 for wall section at lobby/gym/mechanical room and include the necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
75 | Fabric flap | Y |  |  |  |  | 0 | [9 empty] | Y
76 | Watperoofing | Y |  |  |  |  | 0 | [9 empty] | Y
77 | Fabric layer | Y |  |  |  |  | 0 | [9 empty] | Y
78 | Drainage composite layer | Y |  |  |  |  | 0 | [9 empty] | Y
79 | Fabric flap | Y |  |  |  |  | 0 | [9 empty] | Y
80 | Refer to 3/A6.2 for exterior wall section at stair B and include the necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
81 | 2" extruded polystyrene insulaiton extended down to frost depth | Y |  |  |  |  | 0 | [9 empty] | Y
82 | Fabric flap | Y |  |  |  |  | 0 | [9 empty] | Y
83 | Waterproofing | Y |  |  |  |  | 0 | [9 empty] | Y
84 | Drainage composite layer | Y |  |  |  |  | 0 | [9 empty] | Y
85 | Ensure fabric facing SOE to extend from at minimum 2 ft. below finish grade to 1 ft. above bottom of footing | Y |  |  |  |  | 0 | [9 empty] | Y
86 | Fabric flap | Y |  |  |  |  | 0 | [9 empty] | Y
87 | Refer top 4/A6.2 for exterior wall section at auxillary gym and include the necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
88 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
89 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
90 | 2" (R-10 min.) extruded polystyrene insulation extended down to 24" below grade | Y |  |  |  |  | 0 | [9 empty] | Y
91 | Refer to 2/A6.2 for wall section at game room/TLT/shower and include the necessary items; | Y |  |  |  |  | 0 | [9 empty] | Y
92 | Drain board | Y |  |  |  |  | 0 | [9 empty] | Y
93 | Geotextile fabric | Y |  |  |  |  | 0 | [9 empty] | Y
94 | Include the vapor barrier at all exterior wall assemblies | Y |  |  |  |  | 0 | [9 empty] | Y
95 | Include the waterproofing at the inside surfaces of the backwash catch basin as noted on note 3 on AQ4.0 | N/A |  |  |  |  | 0 | [9 empty] | Y
96 | Include the waterproof membrane at metal panel wall assemblies. Refer to 4/A6.1 | Y |  |  |  |  | 0 | [9 empty] | Y | [$4,800] ADD
97 | Include all waterproofing at interior and exterior of elevator | Y |  |  |  |  | 0 | [9 empty] | Y |  | 9420
98 | Waterproofing and drawin tile at geo vault | Y |  |  |  |  | 0 | P |  | 10000 | P |  | 10000 | P |  | 10000 | Y |  | 8474
99
100 | Ref. A1.2-6.3, A9.1, A9.3, A9.10, S301, S001-005 | Y |  |  |  |  | 0 | [9 empty] | Y
101 | Furnish and install below-grade wall system with drainage board and insulation, ref. A6.3 | Y |  |  |  |  | 0 | [9 empty] | Y
102 | Furnish and install drainage board/mat with geotextile fabric, ref. A6.1, A6.4, A9.1, A9.3 | Y |  |  |  |  | 0 | [9 empty] | Y
103 | Furnish and install drainage board with weeps, ref. S001 | Y |  |  |  |  | 0 | [9 empty] | Y
104 | Furnish and install vapor barrier/retarder as shown, refi. A6.1-6.4, A9.10 | Y |  |  |  |  | 0 | [9 empty] | Y
105 | Furnish and install waterproofing membrane, ref. A6.1, A9.1-9.4, a9.10 | Y |  |  |  |  | 0 | [9 empty] | Y
106 | Furnish and install water resistive barrier (WRB), ref. A6.1-6.4, A9.1-9.3 | Y |  |  |  |  | 0 | [9 empty] | Y
107 | Furnish and install 2" (R-10 min.) extruded polystyrene insulation below grade, ref. 3/2A6.1, A6.4, 1/A9.4 | Y |  |  |  |  | 0 | [9 empty] | Y
108 | Furnish and install 3" polystyrene insulation, ref. 13/A9.1 | Y |  |  |  |  | 0 | [9 empty] | Y
109 | Furnish and install R-20 minimum 25 PSI extruded polystyrene insulation below grade, ref. 2/A6.1, 1/A6.2 | Y |  |  |  |  | 0 | [9 empty] | Y
110 | Refer to structural details for waterproofing, foundation CMU block and connection details | Y |  |  |  |  | 0 | [9 empty] | Y
111
112 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y | [8 empty] | Y
113 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0 | Y | [8 empty] | Y
114 | Advise if use of mason's scaffold will be required | Y |  |  |  |  | 0 | Y | [8 empty] | Y
115 | Accessories to include primers, mastics, adhesives, tapes, joint seals/gels, flashings, transitions strips, sealants, etc | Y |  |  |  |  | 0 | Y | [8 empty] | Y
116 | Minor surface prep, filler, dampening/rinsing as needed | Y |  |  |  |  | 0 | Y | [8 empty] | Y
117 | Term bars as req'd | Y |  |  |  |  | 0 | Y | [8 empty] | Y
118 | Flashing/sealing of penetrations | Y |  |  |  |  | 0 | Y | [8 empty] | Y
119 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | Y | [8 empty] | Y
120 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y | [8 empty] | Y
121 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0 | Y | [8 empty] | Y
122 |  | Y |  |  |  |  | 0
123 | Provide an add price for perimeter drain tile including gravel & filter fabric | Y |  |  |  |  | 0 | [9 empty] | Y | 43800
124 | Provide an add price for expansion joint assemblies | Y |  |  |  |  | 0
125 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Payment and Performance Bond | N
2 | Sales Tax | N
3 | Wood Blocking | N
4 | Roofing (provide separate price if bidding this package) | N
5 | Below slab vapor retarders | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | ALT 01: Provide Payment & Performance Bond | #
2 | ALT 02: Sales Tax | #
3 | ALT 03: Drain Tile ADD/ALT | # | [16 empty] | 43800
4 | ALT 04: Sheet applied WP and Drain Tile at Site Retaining Wall (S301/5 & L3.1/5) | # | [16 empty] | 53206
5 | ALT 05: Sheet applied WP and Drain Tile at Ext. Bio Retention Wall (L1.6 & S601/B) | # | [16 empty] | 24420
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## MetPanel
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | RK International |  |  | Chu |  |  | Prestige |  |  | Innovo |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Rawad El Khawand |  |  | Sean Kim |  |  | Dave Cotter |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | rawad@rkinternational.com |  |  | seankim@chucontracting.com |  |  | david@prestigefacades.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | RK International |  | 181840 | 3636.8 | 185476.8 |  | 0
Trade: | 07 - METAL PANELS | [5 empty] | Phone: |  | 703-810-9193 |  |  | Number |  |  | 919-616-0371 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Chu |  | 190200 | 3804 | 194004 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Prestige |  | 279130 | 6978.25 | 286108.25 |  | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: | 298209 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | Innovo | 298209 | 0 | 5964.18 | 304173.18 |  | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 181840 |  | Adjustments: | 190200 |  | Adjustments: | 279130 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 3636.8 | 2% | Bond: | 3804 | 2.5% | Bond: | 6978.25 | 2% | Bond: | 5964.18 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 185476.8 |  | Total Bid: | 194004 |  | Total Bid: | 286108.25 |  | Total Bid: | 304173.18 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | [11 empty] | 298209
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Flat Lock Metal Panel System | # | $ |  |  |  | 0 |  |  | 106840 |  |  | 152900 |  |  | 181820 |  |  | INCL
5 | Formed Metal Wall Panels | # | $ |  |  |  | 0
6 | Exterior Metal Soffits | # | $ |  |  |  | 0 |  |  | EXCL |  |  | 37300 |  |  | 69940 |  |  | INCL
7 | Rigid Insulation at Panel Systems | # | $ |  |  |  | 0 | [5 empty] | INCL |  |  | 27370 |  |  | INCL
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Flat Lock Metal Panel System | # | SF |  |  |  | 0 | [7 empty] | 780
11 | Formed Metal Wall Panels | # | SF |  |  |  | 0
12 | Exterior Metal Soffits | # | SF |  |  |  | 0 | [7 empty] | 416
13 | Rigid Insulation at Panel Systems | # | SF |  |  |  | 0 | [7 empty] | 460
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y | [8 empty] | Y |  |  | Y
| Division 01 - General Requirements | Y | [8 empty] | Y |  |  | Y
| 072100 - Thermal Insulation | Y | [8 empty] | Y |  |  | Y
| 074213.13 - Formed Metal Wall Panels | N/A | [8 empty] | N/A |  |  | N/A
| 074293 - Soffit Panels | Y | [8 empty] | Y |  |  | Y
| 076200 - Sheet Metal Flashing and Trim | Y | [8 empty] | Y |  |  | Y
| 076419 - Flat Lock Metal Panel System | Y | [8 empty] | Y |  |  | Y
| 078413 - Penetration Firestopping | Y | [8 empty] | N | NO/OK |  | N | NO/OK
| 078443 - Joint Firestopping | Y | [8 empty] | N | NO/OK |  | N | NO/OK
| 079200 - Joint Sealants | Y | [8 empty] | Y |  |  | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y | [8 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
2 | Flat Lock Metal Panel System | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
3 | Light gauge wall panel system. Ref. 1 & 4/A6.. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
4 | Copper cladding | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
5 | 2" thick (R-8 min.) semi-rigid mineral fiber continuous insulation | Y |  |  |  |  | 0 | N |  |  | Y |  |  | Y
6 | Waterproofing membrane [provide add/alt] | Y | PROVIDE ADD/ALT |  |  |  | 0 | N |  |  | Y |  |  | Y
7 | B.O.D. Americlad AC-5500 "No Clip" Flat-Lock Panel System or approve equal | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y | Alt man.
8 | Longitudinal flat seam with clip integrated directly in panel system | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
9 | Copper sheet - 16 oz./sq. ft. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
10 | Nonpatinated mill finish | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
11 | Include all materials and accessories to include, but not limited to, flashing, trim, and panel fasteners | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
12 | Include all insulation for a complete assembly | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
13
14 | Formed Metal Wall Panels | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
15 | Exposed-Fastener Lap-Seam Wall Panels at mechanical roof | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
16 | Ribbed-profile exposed-fastener perforated metal wall panels | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
17 | B.O.D. Metl Span; Ecoscreen BR5-36 or approved equal per specifications | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
18 | Coil-coated aluminum sheet | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
19 | 0.040 inches thick | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
20 | Smooth flat finish | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
21 | Two-coat fluropolymer finish, color to match Architect's sample | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
22 | 7.2 inch o.c. rib spacing | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
23 | 36 inch panel coverage | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
24 | 1.5 inch panel height | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
25 | Include all materials and accessories to include, but not limited to, trim, copings, fascia, mullions, sills, corner units, clips, flashings, sealants, gaskets, fillers, clousre strips, backing plates, etc. | N/A |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
26
27 | Exterior Metal Soffit Panels | Y |  |  |  |  | 0 | P | MCN Plug | 75000 | Y |  |  | Y
28 | Prefinished aluminum exterior soffit panels. Ref. 1/A6.1& 2/A6.2. | Y |  |  |  |  | 0 |  | In plug above |  | Y |  |  | Y
29 | Tongue-and-groove aluminum soffit B.O.D.: | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
30 | Longboard Tongue-and-Groove Planks or approved equal per specifications | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
31 | V-groove profile | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
32 | Powder coated wood grain color finish as selected by Architect | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
33 | Include rigid insulation | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
34 | Include all materials and accessories for a complete systems to include, but not limited to, to match materail and finish of metal panels u.n.o.; | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
35 | Trim | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
36 | Flashings | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
37 | Fillings | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
38 | Fillers | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
39 | Closure strips | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
40 | Flashing and trim | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
41 | Panel fasteners | Y |  |  |  |  | 0 |  | " " |  | Y |  |  | Y
42
43 | Furnish and install all metal copings to match the metal panel as shown on the drawings | Y |  |  |  |  | 0 | Y |  |  | Y | Copper coping to match wall panels |  | Y
44 | Ensure all performance and physical properties are met per specifications | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
45 | Include all warranty requirements per specificaitons | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y | 1 Yr workmanship
46
47 | Refer to A1.2 for Level 01 - First Floor Plan | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
48 | Refer to A1.3 for Level 02 - Second Floor Plan | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
49 | Refer to A1.4 for Roof Plan | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
50 | Refer to A3.2 for Level 01 - Reflected Ceiling Plan | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
51 | Refer to A3.3 for Level 02 - Reflected Ceiling Plan | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
52 | Refer to A4.1 for Exterior Elevations | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
53 | Refer to A5.1 - A5.2 for Building Sections | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
54 | Refer to A6.1 - A6.2 for Wall Sections | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
55 | Refer to A12.1 for Finish Schedules | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
56
57 | Provide ADD/ALT for exterior rigid insulation at all exterior wall types | Y | PROVIDE ADD/ALT |  |  |  | 0 |  |  |  | N
58
59 |  | Y |  |  |  |  | 0
60 | Furnish and install light-gauge natural copper flat lock panel system, ref. A4.1, A6.1, A6.3-6.4, A9.1-9.3 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
61 | Ensure note that front entrance canopy is to be reduced to 8" to match stone | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
62 | Furnish and install metal panel façade system, ref. S505, A4.1 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
63 | Coordinate with roofing and metal panel subs, ref. 2&3/A9.1 | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
64 | Provide all material, labor, tools, equipment, hoisting, supervision, etc. for this work | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
65 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
66 | Clean up to MCN dumpster | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
67 | Shop drawings, samples, product data, certs, etc. | Y |  |  |  |  | 0 |  |  |  | Y |  |  | Y
0
C | Exclusions
1 | Wood blocking | N | by carpentry | [7 empty] | N
2 | Caulking | N | by caulking | [7 empty] | N
3 | Composite metal panels (provide separate number, if bidding) | N | by glass/glazing | [7 empty] | N
4 | Studs, sheathing & vapor barrier | N | by drywall | [7 empty] | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Shop fabricated copper panel ILO Americlad panel [CHU] | # | [10 empty] | -86500
2 | 5/8" Plywood and air barrier behind Americlad panel required | # | [10 empty] | 8600 |  |  | 3840
3 | Aluminum anchor straps for wood panels (perpindicular to studs & panels) | # | [13 empty] | 12790
4 |  | #
#
Unit Prices
1 | Labor: Site Labor [Prestige] | # | [13 empty] | 120
2 |  | #
3 |  | #
4 |  | #

## Roof
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Chu |  |  | HRGM |  |  | LP Roofing |  |  | Forsythe |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Sean Kim |  |  | John Maviglia |  |  | Dan Morin |  |  | Zach Travers |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | 703-378-8190 |  |  | 202-889-8400 |  |  | 703-843-7374 |  |  | zach@forsytheinc.net |  |  | Email |  |  | Email |  |  | Email |  | 1 | Chu |  | 866400 | 17328 | 883728 |  | 0
Trade: | 07 - ROOFING | [5 empty] | Phone: |  | seankim@chucontracting.com |  |  | john@hrgm.com |  |  | dan@lproofingllc.com |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | HRGM | 876073 | 15000 | 9980.0176 | 901053.0176 |  | 0
Rev/Date: | Date Issued 01-30-2025 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Forsythe | 894325 | 0 | 17886.5 | 912211.5 |  | 0
[9 empty] | Base Bid: |  |  | Base Bid: | 876073 |  | Base Bid: | 622200 |  | Base Bid: | 894325 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | James Crowle | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 866400 |  | Adjustments: | 15000 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | James.Crowle@MCNBuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 17328 | 1.12% | Bond: | 9980.0176 | 2% | Bond: | 12444 | 2% | Bond: | 17886.5 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 771-209-1893 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 883728 |  | Total Bid: | 901053.0176 |  | Total Bid: | not level |  | Total Bid: | 912211.5 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | 3 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y |  |  | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | [5 empty] | 876073 |  |  | 622200 |  |  | 894325
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | PVC Roofing | # | $ |  |  |  | 0 |  |  | 402200
5 | Green Roof | # | $ |  |  |  | 0 |  |  | 464200
6 |  | # | $ |  |  |  | 0
7 |  | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | PVC Roofing | # | SF |  |  |  | 0
11 | Green Roof | # | SF |  |  |  | 0
12 |  | # |  |  |  |  | 0
13 |  | # |  |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y | [5 empty] | Y
| 072100 - Thermal Insulation | Y | [5 empty] | Y
| 074213.13 - Formed Metal Wall Panels | Y | [5 empty] | Y
| 074293 - Soffit Panels | Y | [5 empty] | Y
| 075423 - Thermoplastic-Polyolefin (TPO) Roofing | Y | [5 empty] | Y
| 076200 - Sheet Metal Flashing and Trim | Y | [5 empty] | Y
| 076419 - Flat Lock Metal Panel System | Y | [5 empty] | Y
| 077200 - Roof Accessories | Y | [5 empty] | Y
| 078413 - Penetration Firestopping | Y | [5 empty] | Y
| 078443 - Joint Firestopping | Y | [5 empty] | Y
| 079200 - Joint Sealants | Y | [5 empty] | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y | [5 empty] | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | Polyvinyl Chloride (PVC) Roofing | Y |  |  |  |  | 0 | Y |  |  | Y
3 | Fabric reinforced, heavy fleece-back PVC sheet type III - B.O.D.: Soprema Sentinel P200HFB | Y |  |  |  |  | 0 | Y |  |  | Y
4 | 80 mils nominal thickness | Y |  |  |  |  | 0 | Y |  |  | Y
5 | White exposed face color | Y |  |  |  |  | 0 | Y |  |  | Y
6 | Include all materials and accessories per manufacturer's recommendations per specifications to include, but not limited to; | Y |  |  |  |  | 0 | Y |  |  | Y
7 | Adhesive and sealants | Y |  |  |  |  | 0 | Y |  |  | Y
8 | Sheet flashing, standard manufacturer's standard unreinforced TPO sheet flashing, 55 mils thick min of same color as PVC sheet | Y |  |  |  |  | 0 | Y |  |  | Y
9 | Prefabricated pipe flashings | Y |  |  |  |  | 0 | Y |  |  | Y
10 | Bonding adhesive - Soprema Duotack SPF HFO Adhesive | Y |  |  |  |  | 0 | Y |  |  | Y
11 | PCV-Clad sheet metal | Y |  |  |  |  | 0 | Y |  |  | Y
12 | Metal termination bars, predrilled stainless steel or aluminum bars approximately 1 by 1/8 inch thick with anchors | Y |  |  |  |  | 0 | Y |  |  | Y
13 | Metal battans, aluminum-zinc-allow-coated or zinc-coated steel steeh approximately 1 inch by 0.05 inch thick, prepunched | Y |  |  |  |  | 0 | Y |  |  | Y
14 | Fasteners | Y |  |  |  |  | 0 | Y |  |  | Y
15 | Pourable sealers | Y |  |  |  |  | 0 | Y |  |  | Y
16 | Preformed cone and vent sheet flashings | Y |  |  |  |  | 0 | Y |  |  | Y
17 | Preformed inside and outside corner sheet flashings | Y |  |  |  |  | 0 | Y |  |  | Y
18 | T-joint covers | Y |  |  |  |  | 0 | Y |  |  | Y
19 | Lap sealants | Y |  |  |  |  | 0 | Y |  |  | Y
20 | Termination reglets | Y |  |  |  |  | 0 | Y |  |  | Y
21 | Additional accessories as required for a complete assembly per manufacturer's recommendations | Y |  |  |  |  | 0 | Y |  |  | Y
22 | Preformed roof insulation boards manufactured by of approved by roof membrane manufacturer and detailed in Project Documents | Y |  |  |  |  | 0 | Y | R-33 per 1/A6.1 |  | Y
23 | Thermal insulation systems as detailed in Project Documents | Y |  |  |  |  | 0 | Y |  |  | Y
24 | SBS-Modified bitumen vapor retarder/air barrier membranes as detailed in Project Documents - SOPRAVAP'R | Y |  |  |  |  | 0 | Y |  |  | Y
25 | Roof insulation as detailed in the Project Documents | Y |  |  |  |  | 0 | Y |  |  | Y
26 | Cover board | Y |  |  |  |  | 0 | Y |  |  | Y
27 | All additional materials for a complete assembly | Y |  |  |  |  | 0 | Y |  |  | Y
28 | Flexible walkways per specifications | Y |  |  |  |  | 0 | N | None shown |  | Y | 50LF INCL
29 | Approximately 36" x 60" with 3/16" thichness | Y |  |  |  |  | 0 | Y |  |  | Y
30 | Contrasting color with roof membrane | Y |  |  |  |  | 0 | Y |  |  | Y
31 | Roof-hatch units per specifications | Y |  |  |  |  | 0 | Y |  |  | Y
32 | Manufacturer's warranty per specifications for a term of 20 years from date of Substantial Completion | Y |  |  |  |  | 0 | Y |  |  | Y
33 | Roof Installer's warranty per specifications for a term of 2 years from date of Substantial Competion | Y |  |  |  |  | 0 | Y |  |  | Y
34 | Obtain components for roofing system from roof membrane manufacturer or manufacturers approved by roofing membrane manufacturer | Y |  |  |  |  | 0 | Y |  |  | Y
35
36 | Green Roof and Hot Fluid-Applied Rubberized Asphalt Waterproofing | Y |  |  |  |  | 0 |  | TBD
37 | Reinforced 100% solids rubberized asphalt membrane B.O.D.: | Y |  |  |  |  | 0 |  | Ecoline 4+1 per 1/A6.1
38 | American Hydrotech, Inc. Monolithic Membrane 6125 or caomparable product per specifications | Y |  |  |  |  | 0
39 | Include all accessories and materials per manufacturer's recommendation to include, but not limited to; | Y |  |  |  |  | 0
40 | Asphalt primer B.O.D. American Hydrotect, Inc. Surface Conditioner | Y |  |  |  |  | 0
41 | Elastomeric sheet flashing | Y |  |  |  |  | 0
42 | Adhesives | Y |  |  |  |  | 0
43 | Liquid applied flashing | Y |  |  |  |  | 0
44 | Metal termination bars | Y |  |  |  |  | 0
45 | Reinforcing fabric | Y |  |  |  |  | 0
46 | Drainage/Water retention component per specs B.O.D.: American Hydrotech, Inc. Gardendrain GR10 | Y |  |  |  |  | 0
47 | Non-woven polymeric geotextile fabric per specs B.O.D.: American Hydrotech, Inc. Systemfilter | Y |  |  |  |  | 0
48 | Metal edging per specs B.O.D.: American Hydrotech, Inc. GardenEdge | Y |  |  |  |  | 0
49 | Inspection chambers per specs B.O.D.: American Hydrotech, Inc. GardenEdge | Y |  |  |  |  | 0
50 | Seperation/root barrier protection course B.O.D.: | Y |  |  |  |  | 0
51 | American Hydrotech, Inc. Hydroflex 30 and Root Stop or approved equal per specs | Y |  |  |  |  | 0
52 | Pressure-sensitive polyethylene root barrier tape with rubber adhesive B.O.D.: | Y |  |  |  |  | 0
53 | American Hydrotech, Inc. Root Stop Tape or approved equal per specs | Y |  |  |  |  | 0
54 | Nonwoven-Geotextile-Faced molded-sheet drainage panels B.O.D.: | Y |  |  |  |  | 0
55 | American Hydrotech, Inc. Hydrodrain 300 or approved equal per specs | Y |  |  |  |  | 0
56 | Type VI unfaced plaza-deck insulation drainage panels typical, B.O.D.: | Y |  |  |  |  | 0
57 | DuPont de Nemours, Inc. Styrofoam Roofmate | Y |  |  |  |  | 0
58 | Type VII unfaced plaza deck insulation drainage panels at top two inches of insulation at paver locations, B.O.D.: | Y |  |  |  |  | 0
59 | DupPont de Nemours, Inc. Styrofoam Plazamate | Y |  |  |  |  | 0
60 | Provide factory-tapered insulation boards with minimum thickness of 1/4 inch with slope of 1/2 inch per foor unless otherwise shown | Y |  |  |  |  | 0
61 | Concrete plaza-deck pavers per sepcs B.O.D.: | Y |  |  |  |  | 0
62 | Hanover Architectural Products Roof and Plaze Pavers, 2 inch thickness, 24 inch square face | Y |  |  |  |  | 0
63 | Paver-support assembly standard per manufacturer including adjustable or stackable pedestals, shims, and spacer tabs for joint spacing of 1/8 inch | Y |  |  |  |  | 0
64 | Include complete green roof assembly as shown on drawings and detailed in specifications | Y |  |  |  |  | 0 |  | Ecoline 4+1 per 1/A6.1 |  | Y | 4+1 Green Roof System
65 | Include all roofing accessories as shown on drawings and detailed in specifications | Y |  |  |  |  | 0 |  |  |  | Y
66 | Extend roof membrane up parapet walls for a complete and enclodues system, refer to A6.1 & A6.2 for the wall sections | Y |  |  |  |  | 0 |  |  |  | Y
67 | Storm overflow scuppers and downspouts | N/A |  |  |  |  | 0 |  |  |  | N/OK | None shown
68 | Ensure coverboard at entire roof for PV panels and supports to attach to | Y |  |  |  |  | 0 |  |  |  | Y/N | No attachments
69
70 | Exterior Metal Soffit Panels [PROVIDE BREAKOUT] | [5 empty] | 0 | N | IN PANELS
71 | Tongue-and-groove aluminum soffit B.O.D.: | [5 empty] | 0 | N | 37300
72 | Longboard Tongue-and-Groove Planks or approved equal per specifications | [5 empty] | 0 | N
73 | V-groove profile | [5 empty] | 0 | N
74 | Powder coated wood grain color finish as selected by Architect | [5 empty] | 0 | N
75 | Include all materials and accessories for a complete systems to include, but not limited to, to match materail and finish of metal panels u.n.o.; | [5 empty] | 0 | N
76 | Trim | [5 empty] | 0 | N
77 | Flashings | [5 empty] | 0 | N
78 | Fillings | [5 empty] | 0 | N
79 | Fillers | [5 empty] | 0 | N
80 | Closure strips | [5 empty] | 0 | N
81 | Flashing and trim | [5 empty] | 0 | N
82 | Panel fasteners | [5 empty] | 0 | N
83
84 | Ensure roof at pool equipment building is included | N |  |  |  |  | 0 | N/NA |  |  | N/NA
85 | Furnish and install metal coping to match copper metal wall panels where shown on drawings [PROVIDE BREAKOUT] | Y |  |  |  |  | 0 | N/NA | IN Panels
86 | Provide warranty as specificed in the specifications | Y |  |  |  |  | 0 | Y |  |  | Y
87 | Include all insulation as specified | Y |  |  |  |  | 0 | Y |  |  | Y
88 | Include aggregate ballast per specifications and product requirements | Y |  |  |  |  | 0 | Y |  |  | Y
89 | Flash and seall all roof transitions and penetrations to include parapets, walls, curbs, columns, rail posts, roof drains, window washing anchors, pipe penetrations, etc. | Y |  |  |  |  | 0 | Y |  |  | Y | Crossed out columns, rail posts, window washing anchors - OK!
90 | Include expansion joint bellows/assembly systems through roof system is shown on drawings | N/A |  |  |  |  | 0 | Y |  |  | N/A
91 | Include vapor barrier running up parapet wall | Y |  |  |  |  | 0 | Y |  |  | Y
92 | Specification requirements for manufacturer's site visits and inspections | Y |  |  |  |  | 0 | Y |  |  | Y
93 | Include all testing as required | Y |  |  |  |  | 0 | Y |  |  | Y
94 | Provide any temporary curbs and flashing of curbs for testing operations as required if testing is required | Y |  |  |  |  | 0 | Y |  |  | N | Need more details
95 | Parapet copings, flashings and coutnerflashings | Y |  |  |  |  | 0 | Y |  |  | N | Copper and stone coping excl
96 | Gravel stops | Y |  |  |  |  | 0 | Y |  |  | N | None shown
97 | Curb flashings, counterflashings and termination bars | Y |  |  |  |  | 0 | Y |  |  | Y
98 | Collar flashings and roof penetrations | Y |  |  |  |  | 0 | Y |  |  | Y
99 | Gutters and downspouts | Y |  |  |  |  | 0 | Y
100 | Through-wall scuppers | Y |  |  |  |  | 0 | Y
101 | Ensure roofing membrane is extended up and over parapet | Y |  |  |  |  | 0 | Y |  |  | Y
102 | Include all roof blocking and blocking at parapet | Y |  |  |  |  | 0 | Y |  |  | P |  | 15000
103 | Include all metal coping to match wall panels | Y |  |  |  |  | 0 | Y |  |  | N
104 | Refer to L2.3 for Green Roof Plan and Details | Y |  |  |  |  | 0 | Y
105 | Refer to A1.4 for Roof Plan | Y |  |  |  |  | 0 | Y
106
107 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y
108 | Coordinate with roofing and metal panel subs, ref. 2&3/A9.1 | Y |  |  |  |  | 0 | Y |  |  | Y
109 | Furnish and install PVC membrane roofing system including tapered insulation and cover board as shown on drawings. Ref. A1.3, A6.3, A9.1, A9.2 | Y |  |  |  |  | 0 | Y |  |  | Y
110 | Furnish and install extensive green roof system. Ref. A1.3, A6.1-A6.4, L1.1 | Y |  |  |  |  | 0 | Y |  |  | Y
111 | Furnish and install roof access hatch with ladder and safety rail, ref. A1.3, A7.1 | Y |  |  |  |  | 0 | Y |  |  | Y
112 | Provide all materials, tools, equipment, hoisting, supervision, etc. for this work | Y |  |  |  |  | 0 | Y |  |  | Y
113 | Include all accessories and materials for a complete system | Y |  |  |  |  | 0 | Y |  |  | Y
114 | Minor surface preperation | Y |  |  |  |  | 0 | Y |  |  | Y
115 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | Y |  |  | Y
116 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y |  |  | Y
117 | Shop drawings, samples, product data, certs, etc. | Y |  |  |  |  | 0 | Y |  |  | Y
118 | Ensure roofing membrane is extended up and over parapet | Y |  |  |  |  | 0 | Y |  |  | Y
119 | Include all roof blocking and blocking at parapet | Y |  |  |  |  | 0 | Y |  |  | N
120 | Include all metal coping to match wall panels | Y |  |  |  |  | 0 | Y |  |  | N
121 | Included coverboard at roof to for PV panels and supports | Y |  |  |  |  | 0 | Y |  |  | Y | Coverboard no attachments
122
123 | LEED Issues: | N |  |  |  |  | 0
124 | EnergyStar roofing/Green roof system employed | N |  |  |  |  | 0
125 | Roof pavers to be 100% recycled tire rubber | N |  |  |  |  | 0
126 | Roof insulation to have a minimum 9% recycled/recovered content | N |  |  |  |  | 0
127 | Low VOC Materials | N |  |  |  |  | 0
128 | Sorting of debris for recycling | N |  |  |  |  | 0
129 | LEED documentation | N |  |  |  |  | 0
0
C | Exclusions
1 | Payment and Performance Bond | N | [5 empty] | N |  |  | N
2 | Through-wall membrane flashings at wall sections | N | [5 empty] | N |  |  | N
3 | Roof blocking, plywood and cant strips | N | [5 empty] | N |  |  | N
4 | Aluminum copings at curtainwall | N | [5 empty] | N |  |  | N
5 | Head, jamb and sill flashings integral with window systems | N | [5 empty] | N |  |  | N
5 | Temporary dry-in considerations | N | [5 empty] | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | ALT 01: Provide Payment & Performance Bond | #
2 | ALT 02: Sales Tax | #
3 | ALT 03: 2-Year Green Roof Maintenance | # | [10 empty] | 39381
4 | ALT04 : Solar Racks | # | [7 empty] | 174600
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Sealants
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - JOINT SEALANTS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Joint Sealants | Y |  |  |  |  | 0
3 | Landscape drawings: | Y |  |  |  |  | 0
4 | Expansion joints in paving | Y |  |  |  |  | 0
5 | Concrete paving/pavers to adjacent paving | Y |  |  |  |  | 0
6 | Paving to vertical site walls | Y |  |  |  |  | 0
7 | Paving to building | Y |  |  |  |  | 0
8 | Curb to paving | Y |  |  |  |  | 0
9 | Vertical joint at curb and gutter | Y |  |  |  |  | 0
10 | Precast inlets to paving | Y |  |  |  |  | 0
11 | Expansion joints at top tread and bottom riser of site stairs | Y |  |  |  |  | 0
12 | Control joints in masonry veneer at site walls | Y |  |  |  |  | 0
13 | ***Other locations*** | Y |  |  |  |  | 0
14 | Architectural drawings: | Y |  |  |  |  | 0
15 | Site paving to building | Y |  |  |  |  | 0
16 | Perimeters of hollow metal door frames in CMU/concrete, both sides | Y |  |  |  |  | 0
17 | Tops of CMU partitions, both sides (maintain fire rating with rated sealant) | Y |  |  |  |  | 0
18 | Control joints at CMU partitions, both sides | Y |  |  |  |  | 0
19 | Masonry control joints at façade | Y |  |  |  |  | 0
20 | Horizontal joints in masonry at relieving angles at façade | Y |  |  |  |  | 0
21 | Precast to precast joints at façade | Y |  |  |  |  | 0
22 | Stone to stone joints at façade | Y |  |  |  |  | 0
23 | Joints in non-composite metal panels [coordinate with metal panels] | Y |  |  |  |  | 0
24 | Joints in EIFS system [coordinate with EIFS] | Y |  |  |  |  | 0
25 | Interior side perimeter of exterior windows [if shown, otherwise it is a Tenant cost] | Y |  |  |  |  | 0
26 | Perimeter of louvers | Y |  |  |  |  | 0
27 | Assume at edge of egress stairs & landings to wall joints, typ | Y |  |  |  |  | 0
28 | Assume at edges of bathroom vanities to wall | Y |  |  |  |  | 0
29 | Assume perimeters of plumbing fixtures and toilet accessories in tile | Y |  |  |  |  | 0
30 | ***Other locations*** | Y |  |  |  |  | 0
31 | Structural drawings: | Y |  |  |  |  | 0
32 | Pourable urethane at slab-on-grade isolation, construction & control joints, typ | Y |  |  |  |  | 0
33 | Slab-on-grade to foundation walls | Y |  |  |  |  | 0
34 |  | Y |  |  |  |  | 0
35 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
36 | Provide all material, labor, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
37 | Accessories to include primer, backer rod, bond breaker tape, masking tape, etc | Y |  |  |  |  | 0
38 | Include minor surface prep | Y |  |  |  |  | 0
39 | Tooling of joints | Y |  |  |  |  | 0
40 | Clean-up to MCN dumpster | Y |  |  |  |  | 0
41 | Shop dwgs, samples, submittals, product data, certs, test reports, etc | Y |  |  |  |  | 0
42 | Field adhesion/compatibility testing of sealant to substrates | Y |  |  |  |  | 0
43 | Warranties per spec [Material and Workmanship] | Y |  |  |  |  | 0
44 |  | Y |  |  |  |  | 0
45 | LEED Issues: | Y |  |  |  |  | 0
46 | Formaldehyde and heavy metal free VOC compliant sealants | Y |  |  |  |  | 0
0
C | Exclusions
1 | Exterior side, perimeter of exterior windows and curtainwall | N | by glass
2 | Tops and bottoms of drywall partitons (acoustical sealant) | N | by drywall
3 | Painter's caulk" - interior door frames, other openings in drywall | N | by paint
4 | Compressible filler/fire safing at tops of CMU partitions | N | by masonry
5 | Firesafing assembly at slab edges | N | by drywall
6 | Firestopping for MEP penetrations | N | by MEP
7 | Roofer's caulk | N | by roofing
8 | Expansion joint covers; compressible seals | N | by EJ contractor
9 | Joints at millwork assemblies | N | by millworker
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## DFH
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Aorbis |  |  | Washington Door |  |  | Allegany Door |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Sahil Mathur |  |  | Ron Caldwell |  |  | Bobie Yost |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | bids@aorbis.com |  |  | ron.caldwell@integratedopenings.com |  |  | bobieyost@alleganydoor.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Allegany Door | 150000 | 0 | 3000 | 153000 |  | 0
Trade: | 08 - DOORS, FRAMES, HARDWARE | [5 empty] | Phone: |  | 860-317-7100 ext 506 |  |  | 202-297-5922 |  |  | 301-739-8900 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Washington Door | 147000 | 5429.6 | 3048.592 | 155478.192 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Aorbis | 195360 | 4936 | 4005.92 | 204301.92 |  | 0
[9 empty] | Base Bid: | 195360 |  | Base Bid: | 147000 |  | Base Bid: | 150000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 4936 |  | Adjustments: | 5429.6 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 4005.92 | 2% | Bond: | 3048.592 | 2% | Bond: | 3000 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 204301.92 |  | Total Bid: | 155478.192 |  | Total Bid: | 153000 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 3 |  |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y |  |  | Y |  |  | Y | Acknowledge except schedule
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y | includes tax | 195360.46 | Y | Excludes Tax | 147000 | Y | Excludes Tax | 150000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [12 empty] | Y | 26664.97
4 | Hollow Metal Doors | # | $ |  |  |  | 0 | Y | 18444.11 |  | Y |  |  | Y | 23314.34
5 | Flush Wood Doors | # | $ |  |  |  | 0 | Y | 37966.38 |  | Y |  |  | Y | 18634.31
6 | Hollow Metal Frames | # | $ |  |  |  | 0 | Y | 15131.29 |  | Y |  |  | Y | 81386.38
7 | Door Hardware | # | $ |  |  |  | 0 | Y | 108657.72 |  | Y
8
9 | Key Quantity Breakdown
10 | Hollow Metal Doors | # | leaf(s) |  |  |  | 0 | Y | 22 |  | Y | 23 |  | Y | 23
11 | Flush Wood Doors | # | leaf(s) |  |  |  | 0 | Y | 28 |  | Y | 29 |  | Y | 28
12 | Hollow Metal Frames | # | ea |  |  |  | 0 | Y | 34 |  | Y | 35 |  | Y | 40
13 | Door Hardware | # | set(s) |  |  |  | 0 | Y | 42 |  | Y | 52 |  | Y
Section 3 - Scope of Work
| Furnish All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 11 13 - Hollow Metal Doors and Frames | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 14 16 - Flush Wood Doors | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 71 00 - Door Hardware Sets | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 80 00 - Glazing (as applicable to this Bid Package) | Y | [5 empty] | N | By Others |  | N |  |  | N | By Others
| 09 91 13 - Exterior Painting (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | N |  |  | Y
| 09 91 23 - Interior Painting (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | N |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
2 | Hollow Metal Doors | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
3 | Furnish all hollow metal doors and frames, and accessories per plans, specs & schedule to include, but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y
4 | Hollow metal door leafs (single and double) as scheduled. Refer to drawing A8.2 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
5 | Hollow metal door frames (single and double) as scheduled. Refer to drawing A8.2 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
6 | Hollow metal interior sidelite/transom frames attached to door frames | Y |  |  |  |  | 0 | N | [5 empty] | N/A
7 | Hollow metal interior borrowed lite frames | Y |  |  |  |  | 0 | N | [5 empty] | N/A
8 | Hollow metal doors to come with glazing stops. Glass to be furnished and installed by others. | Y |  |  |  |  | 0 | Y |  |  | Y
9 | Factory primed finish at interior openings, galvanized at exterior locations | Y |  |  |  |  | 0 | Y | [5 empty] | Y
10 | Thermal rated (insulating) door and frame assemblies at exterior locations | Y |  |  |  |  | 0 | Y | [5 empty] | Y
11 | Comply with ANSI/SDI standards | Y |  |  |  |  | 0 | Y | [5 empty] | Y
12 | Comply with UL ratings | Y |  |  |  |  | 0 | Y | [5 empty] | Y
13 | Comply with NFPA standards | Y |  |  |  |  | 0 | Y | [5 empty] | Y
14 | Accessories to include integral louvers, jamb/floor anchors, glazing stops, attachement hardware, etc | Y |  |  |  |  | 0 | Y | [5 empty] | Y
15 | Provide Basis of Design (BOD) manufacturer(s): | Y |  |  |  |  | 0 | N | Meskar Inc. |  |  |  |  | Y
16 | 1. Ceco Door; ASSA ABLOY | ---> |  |  |  |  | 0 |  |  |  | Y | Ceco
17 | 2. Curries Company; ASSA ABLOY | ---> |  |  |  |  | 0 | [6 empty] | Y | Curries
18 | 3. Republic Doors and Frames | ---> |  |  |  |  | 0
19 | 4. Steelcraft; an Allegion brand | ---> |  |  |  |  | 0
20 | [6 empty] | 0
21 | Flush Wood Doors | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
22 | Furnish all solid core veneer wood doors and accessories per plans, specs & schedule to include but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
23 | Wood door leafs as scheduled. Refer to Drawing A8.2 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
24 | Shop priming flush wood doors | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N/A
25 | Factory-applied transparent finish | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
26 | Comply with NFPA standards | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
27 | Comply with AWI standards | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
28 | Accessories to include wood beads at light openings, etc. | Y |  |  |  |  | 0 |  |  |  | Y
29 | Provide Basis of Design (BOD) manufacturer(s): | Y |  |  |  |  | 0 | N | VT Industries |  | N | Forte Group |  | N | VT Industries
30 | 1. Activar Construction Products Group, Inc - JL Industries | ---> |  |  |  |  | 0
31 | 2. Babcock-Davis | ---> |  |  |  |  | 0
32 | 3. Nystrom | ---> |  |  |  |  | 0
33
34 | Finish Hardware | Y |  |  |  |  | 0 | Y
35 | Furnish hardware sets for all hollow metal and wood doors per schedule/spec: | Y |  |  |  |  | 0 | Y | [5 empty] | Y
36 | Furnish lock cylinders only for aluminum and glass doors/overhead doors | Y |  |  |  |  | 0 | Y | [5 empty] | Y | Construction cores & perm . Cores only
37 | Provide keying for all locks | Y |  |  |  |  | 0 | Y | [5 empty] | Y
38 | Provide electronic hardware | Y |  |  |  |  | 0 | N | Excluded |  |  |  |  | Y
39 | Coordinate with Electrical subcontractor for all requirements related to electrified door hardware and card readers | Y |  |  |  |  | 0 | Y | [5 empty] | Y
40 | Subcontractor is responsible for prepping doors and frames electronic hardware | Y |  |  |  |  | 0 | Y | [5 empty] | Y
41 | [13 empty] | Y
42 | Standard/General Scope | Y |  |  |  |  | 0 | Y
43 | All doors, frames, and hardware included are compliant with listed manufacturers | Y |  |  |  |  | 0 | Y | [5 empty] | Y
44 | Finishes and priming as required - paint and stain by Others | Y |  |  |  |  | 0 | N | Quoted as factory stain |  |  |  |  | Y
45 | Provide all keying for all locks | Y |  |  |  |  | 0 | Y | [5 empty] | Y
46 | Doors and frames in opening with electrified hardware to come predrilled for wiring | Y |  |  |  |  | 0 | Y | [5 empty] | Y
47 | Provide 6 temporary HM single leaf doors and frames with basic lever, hinges, and lock for temporary use for construction. | Y |  |  |  |  | 0 | N | Add $4,936 | 4936 | N | ADD - Aorbis | 5429.6 | Y
48 | Provide fire rated assemblies where indicated in schedule or in rated partitions | Y |  |  |  |  | 0 | Y | [5 empty] | Y
49 | All doors and frames factory-machined/prepped/reinforced for schedule hardware | Y |  |  |  |  | 0 | Y | [5 empty] | Y
50 | Include all construction cores with new doors | Y |  |  |  |  | 0 | Y | [5 empty] | Y
51 | Include relevant sales tax and shipping charges, FOB (Freight on Board) to the jobsite, for all materials | Y |  |  |  |  | 0 | Y | [5 empty] | Y
52 | Submittals, product data, shop drawings, and schedules | Y |  |  |  |  | 0 | Y | [5 empty] | Y
53 | Provide all warranties required | Y |  |  |  |  | 0 | Y | Per manufacturer standard |  |  |  |  | Y
C | Exclusions
1 | Installation of doors, frames and hardware | N | By Drywall Subcontractor | [10 empty] | N
2 | Wood door frames/trim | N | By Millwork Subcontractor | [10 empty] | N
3 | Glass lites in doors and borrowed lites/sidelites | N | By Glass/Glazing Subcontractor | [10 empty] | N
4 | Aluminum door and frames | N | By Glass/Glazing Subcontractor | [10 empty] | N
5 | Field painting | N | By Painting Subcontractor | [10 empty] | N
6 | Overhead doors | N | By Glass/Glazing Subcontractor | [10 empty] | N
D | Schedule
1 | Meet MCN Schedule | Y | [11 empty] | N | Not provided
2 | Advise of Durations
3 | Submittals | ---> | [11 empty] | Y | 3-4 Weeks
4 | Shop Drawings | ---> | [11 empty] | Y | 3-4 Weeks
5 | Advise of Lead Times
6 | Wood Doors | ---> | [11 empty] | Y | 6 Weeks
7 | Hollow Metal Doors | ---> | [11 empty] | Y | 9 Weeks
8 | Hollow Metal Frames | ---> | [11 empty] | Y | 7 Weeks
9 | Door Hardware | ---> | [11 empty] | Y | 18-20 Weeks
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 | Wood Doors | # | $/leaf
2 | Hollow Metal Doors | # | $/leaf
3 | Hollow Metal Frames | # | $/set
4 | Door Hardware | # | $/lockset

## SpecDoor
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Miner Corp |  |  | McKeon Door DC, Inc. |  |  | OHD Co. |  |  | Door Systems Inc |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Doug Luman |  |  | Mike Escribano |  |  | Josh Parsons |  |  | Caroline Sanchez |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | doug.luman@minercorp.com |  |  | mescribano@mckeondoor.com |  |  | coestimating@overheaddoors.com |  |  | carolinedsi@verizon.net |  |  | Email |  |  | Email |  |  | Email |  | 1 | Miner Corp | 11062 | -663.72 | 207.9656 | 10606.2456 |  | 0
Trade: | 08 - SPECIAL DOORS | [5 empty] | Phone: |  | 410-938-7876 |  |  | 631-449-1761 |  |  | 301.937.1800 |  |  | 703-490-1800 |  |  | Number |  |  | Number |  |  | Number |  | 2 | McKeon Door DC, Inc. | 13449 | -806.94 | 252.8412 | 12894.9012 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | OHD Co. | 16892 | 0 | 337.84 | 17229.84 |  | 0
[9 empty] | Base Bid: | 11062 |  | Base Bid: | 13449 |  | Base Bid: | 16892 |  | Base Bid: | 17100 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | Door Systems Inc | 17100 | 0 | 342 | 17442 |  | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | -663.72 |  | Adjustments: | -806.94 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 207.9656 | 2% | Bond: | 252.8412 | 2% | Bond: | 337.84 | 2% | Bond: | 342 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 10606.2456 |  | Total Bid: | 12894.9012 |  | Total Bid: | 17229.84 |  | Total Bid: | 17442 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y | Waiting on bid form |  | Y |  |  | Y |  |  | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  | taxes incl | 11061.53 |  | taxes incl | 13449 | Y | taxes excl | 16892 | Y | taxes excl | 17100
2 | Deduct Taxes | # | [6 empty] | DEDUCT TAXES | -663.72 |  | DEDUCT TAXES | -806.94
3 | Key Cost Breakdown
4 |  | # | $ |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
5 | Coiling Counter Door(s)
6
7 | Key Quantity Breakdown
8 | Coiling Counter Door(s) | # | ea |  |  |  | 0
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y | [5 empty] | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [14 empty] | Y
| 08 33 13 - Coiling Counter Doors | Y | [14 empty] | Y
| 08 71 00 - Door Hardware Sets (as applicable to this Bid Package) | Y | [14 empty] | Y
| 09 91 13 - Exterior Painting (as applicable to this Bid Package) | Y | [14 empty] | Y
| 09 91 23 - Interior Painting (as applicable to this Bid Package) | Y | [14 empty] | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Coiling Counter Doors | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
3 | Furnish and install electrically operated overhead doors at the following location(s): | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
4 | Room 209A, 4' - 0" H X 8' -0" W | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y |  |  | Y
5 | Material to be aluminum | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y |  |  | Y
6 | Finishes to be baked enamel or Powder-Coated finish | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
7 | Accessories to include door curtain slats, cycle counter, end locks, wind locks, bottom bar w/sensor edge, curtain jamb guides, mounting brackets, hoods, smoke seals, weatherseals, sills, locking devices, handles, counterbalancing mechanism, door operators, motor & control stations | Y |  |  |  |  | 0 | Y | [5 empty] | Y
8 | Provide Basis of Design Manufacturer (BOD): | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
10 | 1. Clopay Building Products | ---> |  |  |  |  | 0
11 | 2. Cookson; a CornellCookson company | ---> |  |  |  |  | 0
12 | 3. Cornell; a CornellCookson company | ---> |  |  |  |  | 0 | Y | Cornell Cookson | [7 empty] | Y | Cornell Cookson
13 | 4. McKeon Rolling Steel Door Company, Inc. | ---> |  |  |  |  | 0 |  |  |  | Y | McKeon
14 | 5. Overhead Door Corporation | ---> |  |  |  |  | 0 | [6 empty] | Y | Overhead Door Corp
15
16 | Standard/General Scope | Y |  |  |  |  | 0 | [6 empty] | Y
17 | Provide fire rated assemblies where indicated in schedule or in rated partitions | Y |  |  |  |  | 0 | [6 empty] | N
18 | All doors and frames factory-machined/prepped/reinforced for schedule hardware | Y |  |  |  |  | 0 | [6 empty] | Y
19 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | [6 empty] | Y
20 | Cleanup debris and dispose in MCN dumpster | Y |  |  |  |  | 0 | [6 empty] | Y
21 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0
22 | Provide all materials, tools, equipment, hoisting, supervision, etc. for this work | Y |  |  |  |  | 0 | [6 empty] | Y
23 | Include submittals, product data, shop drawings, schedules, certificates, test reports | Y |  |  |  |  | 0 | [6 empty] | Y
24 | Provide required warranties | Y |  |  |  |  | 0 | [6 empty] | Y
C | Exclusions
1 | Field Painting | N | By Painting Subcontractor | [10 empty] | N
D | Schedule
1 | Meet MCN Schedule | Y | [11 empty] | Y
2 | Advise of Durations
3 | Submittals | ---> | [11 empty] | Y | 1-2 Weeks
4 | Shop Drawings | ---> | [11 empty] | Y | 1-2 weeks
5 | Coiling Counter Door Install | ---> | [11 empty] | Y | 1-3 days
6 | Advise of Lead Times
7 | Coiling Counter Door | ---> | [11 empty] | Y | 8-10 weeks |  | Y | 6-16 weeks
8 | Fabrication | ---> | [11 empty] | Y
Allowances
1
2
3
4
Alternates
1 | Custom Paint Finish (Provided due to discrepancy in specifications) | # | [11 empty] | Y | ADD ALT - $3,960
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Alum
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | AGM Contracting |  |  | Prestige |  |  | Ranger |  |  | Innovo |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | John Won |  |  | Dave Cotter |  |  | Chip Sterritt |  |  | Isabella Hodjatzadeh |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | 301-324-7300 |  |  | david@prestigefacades.com |  |  | chip@rangerglass.com |  |  | isabellah@innovoconstruction.com |  |  | Email |  |  | Email |  |  | Email |  | 1 | AGM Contracting |  | 479200 | 9584 | 488784 |  | 0
Trade: | 08 - ALUM & GLASS | [5 empty] | Phone: |  | john@agmcontract.com |  |  | 919-616-0371 |  |  | 703-343-5630 |  |  | 240-455-4888 etx. 118 |  |  | Number |  |  | Number |  |  | Number |  | 2 | Ranger |  | 574253 | 11485.06 | 585738.06 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Prestige |  | 609250 | 12185 | 621435 |  | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: | 626912 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | Innovo | 626912 | 0 | 12538.24 | 639450.24 |  | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 479200 |  | Adjustments: | 609250 |  | Adjustments: | 574253 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 9584 | 2% | Bond: | 12185 | 2% | Bond: | 11485.06 | 2% | Bond: | 12538.24 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 488784 |  | Total Bid: | 621435 |  | Total Bid: | 585738.06 |  | Total Bid: | 639450.24 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 3 |  |  | 2 |  |  | 4 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | [11 empty] | 626912
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Storefront | # | $ |  |  |  | 0 |  |  | 157800 |  |  | 196770 |  |  | 482080
5 | Curtain Wall | # | $ |  |  |  | 0 |  |  | 236200 |  |  | 198340 |  |  | incl
6 | Interior Glazing | # | $ |  |  |  | 0 |  | Int SF | 60000 |  |  | 63260 |  |  | 92173
7 | Miscellaneous Glazing | # | $ |  |  |  | 0 |  | Mirrors | 8000 |  | mirrors | 10840 |  |  | incl
8 | Window Film | # | $ |  |  |  | 0 |  |  | 2500 |  |  | 14360 |  |  | incl
8 | [6 empty] | 0 |  |  |  |  | drs | 122360 |  | drs | incl
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Storefront | # | SF |  |  |  | 0 |  | 1570
11 | Curtain Wall | # | SF |  |  |  | 0 |  | 1313
12 | Interior Glazing | # | SF |  |  |  | 0 |  | 1120
13 | Miscellaneous Glazing | # | SF |  |  |  | 0 |  | 104
14 | Window Film | # | SF |  |  |  | 0 |  | 109
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y | [5 empty] | Y
A | Specifications
| Division 01 - General Requirements | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 074213.13 - Formed Metal Wall Panels | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 074293 - Soffit Panels | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 078413 - Penetration Firestopping | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 078443 - Joint Firestopping | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 079200 - Joint Sealants | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 084113 - Aluminum-Framed Entrances and Storefronts | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 084423 - Structural-Sealant-Glazed Curtain Walls | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 088000 - Glazing | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 088300 - Mirrors | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| 088700 - Glazing Surface Film | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y | [5 empty] | Y | [5 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
2 | Aluminum Framed Entrances, Storefront and Curtainwall | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
3 | Storefront systerms B.O.D.: | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
4 | Thermally broken: Kawneer 601UT | Y |  |  |  |  | 0 | Y | [5 empty] | N/OK | YKK, OBE, US Alum, Tubelite or aprvd sub |  | Y
5 | Non-thermal: Kawneer 301 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
6 | Entrance door systems B.O.D.: | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
7 | Thermally broken: Kawneer 500T Insulpour Entrance | Y |  |  |  |  | 0 | Y | [5 empty] | N/OK | YKK, OBE, US Alum, Tubelite or aprvd sub |  | Y
8 | Non-thermal: Kawneer 500 Heavy Wall | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
9 | Structual-Sealant Glazed Curtain Wall | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
10 | Delegated design per specifications | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
11 | Four-sided structural-sealant-glazed curtain wall assemblies | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
12 | Kawneer Clearwall Curtain Wall System | Y |  |  |  |  | 0 | Y | [5 empty] | N/OK | YKK, OBE, US Alum, Tubelite or aprvd sub |  | Y
13 | Glazing per specifications section 088000 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
14 | Laminated glass - Kuraray SentryGlass | Y |  |  |  |  | 0 | P |  | 5000 |  |  | 3320 | Y |  |  | Y
15 | Window film | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
16 | 3M Fassara per finish schedule A12.1 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
17
18 | Furnish and install all aluminum framed doors at interior and exterior locations, include all glazing in doors provided by others | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
19 | Exterior | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
20 | CW1 | Y |  |  |  |  | 0 | Y |  | Curtainwall |  |  |  | Y |  |  | Y
21 | Doors and hardware at CW1 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
22 | CW2 | Y |  |  |  |  | 0 | Y |  | Curtainwall |  |  |  | Y |  |  | Y
23 | CW3 | Y |  |  |  |  | 0 | Y |  | Curtainwall |  |  |  | Y |  |  | Y
24 | Doors and hardware at CW3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
25 | Metal fins and panels at SF-3 | N |  |  |  |  | 0 | N | [5 empty] | N |  |  | Y
26 | SF-4 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
27 | SF-5 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
28 | SF-6 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
29 | SF-7 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
30 | Door at SF-7 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | Y |  |  | N/OK! |  | WD doors by others
31 | SF-8 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
32 | Door at SF-8 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
33 | SF-9 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
34 | SF-10 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
35 | SF-11 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
36 | SF-12 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
37 | SF-13 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
38 | SF-14 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
39 | Interior | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
40 | SF-15 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
41 | Doors and hardware at SF-15 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
42 | SF-16 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
43 | SF-17 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
44 | Doors and hardware at SF-17 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
45 | SF-18 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
46 | Door and hardware at SF-18 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
47 | SF-19 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
48 | Door and hardware at SF-19 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
49 | SF-20 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
50 | Door and hardware at SF-20 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
51 | SF-21 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
52 | Door and hardware at SF-21 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
53 | SF-22 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
54 | Door and hardware at SF-22 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
55 | SF-23 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
56 | Door and hardware at SF-23 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
57 | SF-24 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
58 | Furnish and install all interior aluminum framed doors and frames | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
59 | Unlabeled SF assembly at Door 215 [Activity 1 - 215] Refer to 15/A10.2 | Y |  |  |  |  | 0 | Y | [5 empty] | Y | SF-24 |  | Y
60 | Unlabled SF assembly at Door 216 [Activity 2 - 216] Refer to 12/A10.2 | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
61 | Door 103A aluminum frame | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
62 | Door 103B aluminum frame | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
63 | All embedded glazing at doors and frames | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
64 | Door type FG | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
65 | Door type N | Y |  |  |  |  | 0 | N/OK! |  | WD doors by others |  |  |  | N/OK! |  | WD doors by others | N/OK! |  | WD doors by others
66 | Fire rated door type N | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
67 | Include window film as shown on drawings, specifications and and in finish schedule | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
68 | WF-01 at Fitness [106] Refer to 3 & 5/A10.1 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
69 | WF-02 at Guard [110] Refer to 10/A10.1 | N |  |  |  |  | 0 | N | [5 empty] | N |  |  | N
70
71 | Refer to A4.1 for the Exterior Elevations | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
72 | Refer to A8.2 for the Door and Frame Type and Schedules | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
73 | Refer to A8.3 for the Window Types and Schedules | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
74 | Refer to A10.1 - A10.6 for the Interior Elevations | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
75
76 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
77 | All Document References for Windows | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
78 | Furnish and install aluminum curtain wall system | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
79 | Furnish and install aluminum-framed storefront system, ref. A1.1-1.2, A4.1, A6.1-6.3, A9.10 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
80 | Furnish and install aluminum storefront entrance doors, ref. A4.1, A6.4, A9.10 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
81 | Furnish and install butt glazed systems, ref. A8.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
82 | Furnish and install curtain wall and storefront systems, ref. A4.1, A6.1, A8.3, A9.2 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
83 | Furnish and Install decorative and security window film, ref. A10.1-10.2, A12.1 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
84 | Furnish and install GL-1 heat-strengthened glazing, ref. A8.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
85 | Furnish and Install GL-2, GL-3, GL-4, GL-6, GL-7 Glazing, ref. A8.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
86 | Furnish and install laminated and laminated insulated glazing, ref. A8.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
87 | Furnish and install unframed mirrors as shown, ref. A10.1-10.6 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
88 | Furnish and install transom componenets for the curtain wall systems as shown, ref. 13/A9.1 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
89 | Furnish and install complete main entry vestibule 101 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
90 | Provide glazing for doors and frames | Y |  |  |  |  | 0 | Y |  | ALUM Only |  |  |  | Y |  |  | Y
91 | Provide head receivers and movement joints for deflection as needed, ref. A8.2-8.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y | If rqrd |  | Y
92 | Provide shims for aluminum frame installation, ref. A9.10 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
93 | Provide silicone sealant for butt joint glazing, ref. A9.3 | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
94 | Provide all materials, tools, equipment, hoisting, supervision, etc. for this work | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
95 | Finishes of aluminum framing as specified on drawings and specifications | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
96 | Systems meet performance criteria outlined on drawings and specifications | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
97 | Provide design, engineering, labor, material, equipment, manufacturing, fabrication, supervision, and installation necessary for the complete installation for the structural sealant glazed gurtain wall systems | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
98 | Edge of slab firesfaing system, including but not limited to, curtail wall insulaiton, firesafing insulation, and firestopping between curtain wall and edge of slab | N |  |  |  |  | 0 | N | [5 empty] | N |  |  | Y
99 | Provide protection at all sills, including stoll trim, as well as the bottom 4' of all vertical. Protection to be comprised of blue nitto tape and 1/8" corrugated plastic board or similar products. Maintenance and removal by MCN. | Y |  |  |  |  | 0 | Y |  | 9700 |  |  |  | Y |  |  | Y
100 | Include all break metal infills at glazing systems | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | N/A
101 | Include all aluminum sill extensions | N |  |  |  |  | 0 | N | [5 empty] | N |  |  | N
102 | Include all aluminum blind pockets as shown on drawings | Y |  |  |  |  | 0 | N | [5 empty] | N |  |  | N
103 | Include all mullion caps, fly-bys, and other aluminum accents at facades | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
104 | Include all head, jamb, and sill flashings adjacent to glazing systems | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
105 | Ensure compatibility of sealants with adjacent materials | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
106 | Provide cut-outs for work of other trades where necessary (drains, lighting, security, etc.) | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
107 | Provide overhead support/bracing for recessed vestibule/storefront systems as needed | Y |  |  |  |  | 0 | Y | [5 empty] | N | By misc metals |  | Y
108 | Furnish embedded items for installation by others | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
109 | Perform welded/bolted connections to attach window systems to skin/structure | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
110 | Accessories to include glazing sealants, gaskets, joint fillers, glazing channels, stops, spacers, setting blocks, inserts, shims, weatherstipping, mastics, bituminous paint, primers, anchors, clips, fasteners, etc. | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
111 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
112 | Shop drawings, samples, product data, certs, etc. | Y |  |  |  |  | 0 | Y | [5 empty] | Y |  |  | Y
113
114 | LEED Issues: | Y |  |  |  |  | 0
115 | Formaldehyde and heavy metal free VOC compliant sealants | Y |  |  |  |  | 0
116 | Fabrication from within 500 mile radius | Y |  |  |  |  | 0
117 | LEED documentation | Y |  |  |  |  | 0
C | Exclusions
1 | Structural steel support/back-up for curtainwall systems | N | by metals
2 | Glass railing systems | N | by ornamental
3 | Wood blocking and plywood | N | by carpentry
4 | Caulking at interior side of exterior window systems | N | by caulking
5 | Stud framing, sheathing and vapor barriers | N | by drywall
6 | Work in elevator cabs | N | by elevator
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Storefront performance mock-up | # | [16 empty] | 47320
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## GWB
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Uniconstruction |  |  | Dynamic Contracting |  |  | District Construction |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Roy Chaaban |  |  | Luis Cartagena |  |  | Melvin Vasquez |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | roy@uniconstruction |  |  | estimating@jpcontinc.com |  |  | melvin@districtconstruction.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Uniconstruction | 798303 | 0 | 15966.06 | 814269.06 |  | 0
Trade: | 09 - DRYWALL & CEILINGS | [5 empty] | Phone: |  | 804-666-1945 |  |  | 703-898-3836 |  |  | 301-674-6429 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Dynamic Contracting | 1105981 | 78054 | 23680.7 | 1207715.7 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 798303 |  | Base Bid: | 1105981 |  | Base Bid: | 1247628 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 78054 |  | Adjustments: | -45000 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 15966.06 | 2% | Bond: | 23680.7 | 2% | Bond: | 24052.56 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 814269.06 |  | Total Bid: | 1207715.7 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [6 empty] | Sent email to inquire about SOW items |  |  | Sent email to inquire about SOW items
Section 2 - Bid Breakdown
1 | Base Bid (Complete Package) | # | $ | xxx | xx | xxx | xxx | Y |  | 798303 | Y | Tax Incl | 1105981 | Y | Taxes excluded | 1247628
2 | Tax Deduct (if applicable) | [5 empty] | 0 |  |  |  | Y | DEDUCT | -20100
3 | Key Cost Breakdown
4 | Partitions, Framing, and Sheathing | # | $ |  |  |  | 0 | Y | 594853 |  | Y |  |  | Y
5 | Acoustical Ceilings | # | $ |  |  |  | 0 | Y | 105000 |  | Y |  |  | Y
6 | FRP Panels | # | $ |  |  |  | 0 | Y | 20000 |  | Y |  |  | Y
7 | Sound Absorbing Wall Units | # | $ |  |  |  | 0 | Y | 25000 |  | Y |  |  | Y
8 | Corner Guards (Installation Only) | # | $ |  |  |  | 0 | N | w/Div 10 |  | N | W/Div 10 |  | N | W/Div 10
9 | Rough Carpentry (In-Wall Blocking/Strapping/Etc) | # | $ |  |  |  | 0 | Y | 34000 |  | Y |  |  | Y
10 | Installation of Item. Furnished by Others (DFH, DIV 10 (TA, FEC)) | # | $ |  |  |  | 0 | Y | 19450 |  | Y |  |  | Y
11 | Installation of brick ties | # | $ |  |  |  |  | N | Excluded |  | Y | DEDUCT | -22767 | Y | DEDUCT | -45000
12 | Key Quantity Breakdown
13 | Partitions, Framing, and Sheathing | # | LF/SF |  |  |  | 0 | Y | 4300 |  | Y |  |  | Y
14 | Acoustical Ceilings | # | SF |  |  |  | 0 | Y | 6500 |  | Y |  |  | Y
15 | FRP Panels | # | SF |  |  |  | 0 | Y | 1200 |  | Y |  |  | Y
16 | Sound Absorbing Wall Units | # | SF |  |  |  | 0 | Y | 1250 |  | Y |  |  | Y
17 | Corner Guards | # | EA |  |  |  | 0 | N | W/Div 10 |  | N | w/Div 10 |  | N | W/Div 10
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [8 empty] | Y |  |  | Y
| 05 40 00 - Cold-Formed Metal Framing | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 06 10 53 - Miscellaneous Rough Carpentry | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 06 16 00 - Sheathing | Y
| 06 64 00 - Plastic Paneling | Y
| 07 21 00 - Thermal Insulation | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 07 42 10 - Composite Support Framing | Y
| 07 42 93 - Soffit Panels | Y
| 07 84 13 - Penetration Firestopping | Y
| 07 84 43 - Joint Firestopping | Y
| 07 92 00 - Joint Sealants | Y | [11 empty] | Y
| 08 11 13 - Hollow Metal Doors and Frames (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 14 16 - Flush Wood Doors (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 08 31 13 - Access Doors and Frames (as applicable to this Bid Package) | Y
| 09 84 33 - Sound Absorbing Wall Units | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 22 16 -Non-Structural Metal Framing | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 29 00 - Gypsum Board | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 51 13 - Acoustical Panel Ceilings | Y | [11 empty] | Y
| 09 72 00 - Wall Coverings (as applicable to this Bid Package) | Y
| 10 11 00 - Visual Display Boards (as applicable to this Bid Package) | Y | [5 empty] | N |  |  | N |  |  | Y
| 10 26 00 - Wall and Door Protection | Y | [5 empty] | N |  |  | N |  |  | Y
| 10 28 00 - Toilet, Bath, and Laundry Accessories (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Inclusions:
3 | Include types/colors per specifications and drawings for appropiate application: | Y |  |  |  |  | 0
4 | Refer to partion types on Drawing A8.1 | Y |  |  |  |  | 0
5 | Refer to the RCP on Drawings A3.1 & A3.2 | Y |  |  |  |  | 0
6 | Refer to wall sections on Drawings A6.1 - A6.4 | Y |  |  |  |  | 0
7 | Refer to enlarged plans on Drawings A2.1 or similar | Y |  |  |  |  | 0
8 | Refer to details/sections on Drawings A5.1 - A6.4 or similar | Y |  |  |  |  | 0
9 | Refer to Finish Schedule on Drawing A12.1 | Y |  |  |  |  | 0
10 | Refer to Finish Plan on Drawings A12.2 & A12.3 | Y |  |  |  |  | 0
11 | Refer to interior elevations on Drawings A10.1 - A10.6 | Y |  |  |  |  | 0
12
** | Furnish and Install All Items UNO (Unless Otherwise Noted) | Y |  |  |  |  | 0 | Y
13 | Sheathing:
14 | Furnish and install all gypsum sheathing at exterior stud wall locations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
15 | Furnish and install all vapor barrier at interior | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
16 | Sheathing at horizontal locations as shown | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
17
18 | Building Insulation:
19 | Include all batt, semi-rigid, and thermal insulation at the following locations: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
20 | Include exterior stud wall and soffit systems noted above | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
21 | Provide batt insulation for all the interior partitions as indicated at the partition type assemblies | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
22 | Provide and install mineral fiber blanket insulation to fill all perimeter window and door shim spaces, gaps, and crevices at exterior wall and roof assemblies associated with gypsim board construction, complete for a continous and code-compliant installation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
23 | Comply with specified r-values | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
24
25 | Metal Support Assemblies:
26 | Furnish and install metal stud, shaftwall framing and furring channels at all interior partitions per the Partition Types scheduled and inferrable from the plans | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
27 | Furnish and install metal stud, furring channels and suspension system for all drywall ceilings; including framing required for soffits, bulkheads and light coves | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
28 | Provide extend furring channels and gypsum board up 4" above finished ceiling on CMU walls. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
29 | Provide CFMF (cold-formed metal framing) including kickers and boxers | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
30 | Include slip-type head joints, per specifications | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
31
32 | Gypsum Board:
33 | Furnish & install gypsum board at all interior partitions, perimeter walls/column covers, ceilings, soffits, bulkheads, light coves, etc to include fire rated, impact-resistant, moisture-resistant & shaft liner as applicable per the scheduled Partition Types and as inferrable from the plans | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
34 | Provide isolation at gypsum board surfaces with control joints, where shown on Contract Documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
35 | Partitions at perimeter & exterior side | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
36 | Include rated duct enclosure assemblies indicated on Architectural and Mechanical drawings | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
37 | Include sound attenuation blanket as scheduled/inferrable | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
38 | Include acoustical sealant at tops and bottoms of partitions | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
39 | Include sealant for partition assembly as noted. Sealing of penetrations in your Work created by others in by that trade. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
40 | Include can't boards at elevator shafts | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
41 | Tape, spackle & sand all joints for assemblies scheduled to receive a finish | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
42 | Smooth skim coats finishes | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
43 | Provide a level 4 finish at all walls scheduled to receive graphics | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
44
45 | Acoustical Ceilings and Acoustical Treatments: | Y | [8 empty] | Y
46 | Furnish & install acoustical tile ceilings per the specifications, Finish Schedule and RCP's | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
47 | Furnish & install standard ceiling tile [ACP-01] BOD [Armstrong - Ultima 1912LEC, 9/16 Beveled Tegular - Bright White] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
48 | Furnish & install scrubable NSF [ACP-02] BOD [Armstrong - Kitchen Zone Square Lay In 15/16 - Bright White] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
49 | Provide seismec bracing for suspended ceilings or as shown on the drawings | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
50 | Include hanger wire and suspended metal grid system | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
51 | Deliver 2% unopened carton of above product (or fraction thereof) installed for each type, pattern and color as mentiioned in the specifications | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
52 | [7 empty] | Y |  |  | Y
53 | Sound Absorbing Wall Units - Wall Panels
54 | Furnish & install sound absorbing panels, SAW-01 (Tectum)at locations indicated on the Contract Documents | Y |  |  |  |  | 0 | Y |  |  | Y | ADD Per Proposal | 48594 | Y
55 | SAW-01: Armstrong - Direct Attach | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
56 | Panels shall be installed in compliance with manufacturer's installation requirements and specification requiremenrs for field-painted panels | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
57 | Coordinate with Painting Trade for field application of finish, including required surface preparation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
58 | Include all substrate preparation, layout, field measuring,cutting, trimming, and coordination with adjacent finishes | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
59 | Furnish and install all required mounting systems, fasteners, clips, ahesives, and accessories necessary for a complete and secure installation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
60
61 | Plastic Paneling - Wall Panels
62 | Furnish & install FRP and acoustic treatments per the Contract Documents: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
63 | Furnish & install Food Service Walls [FRP-01] BOD [Crane Composites - Glassboard Class A- White] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
64 | Include all necessary accessories and tracks required for proper installation | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
65
66 | Wall and Door Protection
67 | Furnish & install corner guards according to the Contract Documents: | Y | [5 empty] | N | W/Div 10 |  | N | W/Div 10 |  | N | W/Div 10
68 | CGD-01: Corner Guards, Inpro, 3/4", surface mounted | Y | [5 empty] | N | W/Div 10 |  | N | w/Div 10 |  | N | W/Div 10
69
70 | Rough Carpentry
71 | Provide all in wall blocking as required as stated in the Contract Documents | Y |  |  |  |  | 0 | Y
72 | Wood or sheet metal In-wall blocking, including but not limited to the following: | Y |  |  |  |  | 0 | Y
73 | - Fire-treated wood blocking | Y |  |  |  |  | 0 | Y
74 | - At wall mounted handrails | Y |  |  |  |  | 0 | Y
75 | - At wall mounted cabinetry (base and wall cabinets; countertops) | Y |  |  |  |  | 0 | Y
76 | - At toilet accessories | Y |  |  |  |  | 0 | Y
77 | - At wall corner guards | Y |  |  |  |  | 0 | N | Not needed
78 | - At Parapet | Y |  |  |  |  | 0 | Y |  |  | Y | ADD Per Proposal | 27782
79 | Receive, Unload, Catalogue, Store, and Install Only the following items: | Y |  |  |  |  | 0
80 | - Hollow metal frames | Y |  |  |  |  | 0 | Y |  |  | Y | ADD | 36985 | Y
81 | - Hollow metal doors | Y |  |  |  |  | 0 | Y |  |  | Y | Incl |  | Y
82 | - Wood doors | Y |  |  |  |  | 0 | Y |  |  | Y | Incl |  | Y
83 | - Door hardware sets | Y |  |  |  |  | 0 | Y |  |  | Y | Incl |  | Y
84 | - Louvers | Y |  |  |  |  | 0 | N/A |  |  | N/A |  |  | N/A
85 | - Fire extinguisher cabinets | Y |  |  |  |  | 0 | Y |  |  | Y | ADD Per Proposal | 2700 | Y
86 | - Toilet Accessories & Partitions | Y |  |  |  |  | 0 | Y |  |  | Y | ADD Per Proposal | 4860 | Y
87 | - Markerboards, tackboards | Y |  |  |  |  | 0 | N | W/Div 10 |  | Y | W/Div 10 | 0 | N | W/Div 10
88 | Standard/General Scope of Work
89 | Include all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
90 | Assume free use of General Contractor's material hoist [confirm with GC's] | Y |  |  |  |  | 0
91 | Field cutting & frame out to accommodate work of other trades to include windows, doors, lites, FEC's, toilet accessories, MEP/sprinkler penetrations, etc. | Y |  |  |  |  | 0
92 | Coordinate stud/ceiling layout with MEP trades - penetrations & potential spatial conflicts; verify inspections prior to wall/ceiling close-ins | Y |  |  |  |  | 0
93 | Include all supplemental framing, bridging, bracing & kickers necessary | Y |  |  |  |  | 0
94 | Include installation of access doors in drywall (furnished by others) | Y |  |  |  |  | 0
95 | Accessories to include corner/casing beads, trim, primers, tapes, adhesives, sealants, shims, gaskets, screws/anchors/fasteners, etc | Y |  |  |  |  | 0
96 | Include extra stock per Specifications | Y |  |  |  |  | 0
97 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 |  |  |  | Y
98 | Clean up to MCN dumpster | Y |  |  |  |  | 0 |  |  |  | Y
99 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0
100 | Provide all mockups required by the Contract Documents | Y |  |  |  |  | 0
101 | Provide all manufacturer's standards warranties for materials incorporated into the Work | Y |  |  |  |  | 0
102 | Provide all mobilizations necessary to perform the Work included in the Drywall Scope, across all applicable specification sections, in accordance with the Contract Documents and project schedule | Y |  |  |  |  | 0
103 | Provide all labor, materials, equipment, test samples, and documentation necessary to support required testing and inspections | Y |  |  |  |  | 0
C | Exclusions
1 | Fire safing at curtainwall slab edges | N | By Others |  |  |  |  | N
2 | Fire stopping of penetrations through drywall | N | By MEP Subcontractor |  |  |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Framing/Partitions | --->
4 | Drywall Board | --->
5 | Ceiling | --->
6 | Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Installation | --->
9 | ACT Ceiling | --->
Allowances
1
2
3
4
Alternates
1 | Deduct/ADD #1 - BO pricing for installation of brick ties | # | [8 empty] | Y | ADD - $22,767 |  | Y | Deduct - $63,000
2 | Add Alternate #1 - BO pricing for installation only of corner guards | # | [11 empty] | Y | ADD - $623.18
3 | Add Alternate #2 - BO pricing for furnishing and installing corner guards | # | [11 empty] | Y | ADD - $1,871
4 | Add Alternate #3 - BO pricing for installation of visual display boards | # | [8 empty] | Y | ADD - $6,708 |  | Y | ADD - $9,748
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Tile
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Floors Etc |  |  | Admiral |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Ata Rad |  |  | Fred Nustray |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | arad@floors-etc.com |  |  | fred@admiraldc.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Floors Etc | 60049 | 4715 | 1295.28 | 66059.28 |  | 0
Trade: | 09 - TILE | [5 empty] | Phone: |  | 410-329-9680 |  |  | 301-789-6393 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Admiral | 100000 | 0 | 2000 | 102000 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 60049 |  | Base Bid: | 100000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 4715 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 1295.28 | 2% | Bond: | 2000 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 66059.28 |  | Total Bid: | 102000 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y | Sales Tax Exclu | 58359 | Y | Sales Tax Excl | 100000
2 | [6 empty] | 0
3 | Key Cost Breakdown
4 | Ceramic Tiling | # | $ |  |  |  | 0 |  |  |  | Y
5 | Quarry Tiling | # | $ |  |  |  | 0 |  |  |  | Y
6 | Key Quantity Breakdown
7 | Ceramic Tiling | # | SF |  |  |  | 0 |  |  |  | Y
8 | Quarry Tiling | # | SF |  |  |  | 0 |  |  |  | Y
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y
| 07 92 00 - Joint Sealants (as applicable to this Bid Package) | Y | [8 empty] | Y
| 09 30 13 - Ceramic Tiling | Y | [5 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | Porcelain Tile
3 | Floor tile as scheduled: | Y |  |  |  |  | 0 | Y |  |  | Y
4 | Provide tile type/color as per schedule at the locations specified on the drawings: | Y |  |  |  |  | 0 | Y |  |  | Y
5 | Furnish and Install (FT-01) BOD [TileBar - Nashville - Taupe, Matte Finish] | Y |  |  |  |  | 0 | Y |  |  | Y
6 | Furnish and Install (FT-02) BOD [TileBar - Nashville - Taupe, Matte Finish] | Y |  |  |  |  | 0 | Y |  |  | Y
7
8 | Wall Tile
9 | Provide tile type/color as per schedule at the locations specified on the drawings: | Y |  |  |  |  | 0 | Y |  |  | Y
10 | Furnish and Install (WT-01) BOD [TileBar - Nashville - Beige, Matte Finish] | Y |  |  |  |  | 0 | Y |  |  | Y
11 | Furnish and Install (WT-02) [TileBar - Nashville - Beige, Matte Finish] | Y |  |  |  |  | 0 | Y |  |  | Y
12
13 | Quarry Tile
14 | Provide tile type/color as per schedule at the locations specified on the drawings: | Y |  |  |  |  | 0 | Y |  |  | Y
15 | Furnish and Install (QT-01) BOD [Daltile - Quarry Tile - Ahen Grey, Abrasive] | Y |  |  |  |  | 0 | Y |  |  | Y
16
17 | Base
18 | Provide tile type/color as per schedule at the locations specified on the drawings: | Y |  |  |  |  | 0 | Y |  |  | Y
19 | Furnish and Install (TB-01) BOD [TileBar - Nashville - Beige, Matte Finish] | Y |  |  |  |  | 0 | Y
20 | Furnish and Install (TB-02) BOD [Daltile - Quarry Tile Round Top Cove Base Q3565 - Beige, Matte Finish] | Y |  |  |  |  | 0 | Y |  |  | Y
21
22 | Standard/General Scope
23 | Include all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0 | Y
24 | Leveling compound for slope is by this Subcontractor | Y |  |  |  |  | 0 | Y
25 | Include all grouting required for a complete and finished installation | Y |  |  |  |  | 0 | Y
26 | Include all required metal edge strips | Y |  |  |  |  | 0 | Y
27 | Include application of floor sealer, including all required surface preparation, number of coats, curing time, and compatibility with specified flooring materials, in accordance with manufacturer requirements and project specifications. | Y |  |  |  |  | 0 | N/A
28 | Include trowelable underlayments and patching compounds | [6 empty] | Y | Minor prep only
29 | Accessories to include primers, adhesives, trim pieces, etc. | Y |  |  |  |  | 0 | Y
30 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y
31 | Skim coat and minor surface prep as required | Y |  |  |  |  | 0 | Y | Minor prep only
32 | Include divider and transition strips | Y |  |  |  |  | 0 | Y |  |  | Y
33 | Schluter strips at all tile edges and corners | Y |  |  |  |  | 0 | Y
34 | Application of specified sealer prior to installation of finish materials | Y |  |  |  |  | 0 | Y
35 | Mulitple mobilizations required for the schedule | Y |  |  |  |  | 0 | Y
36 | Waterproofing membranes as required | Y |  |  |  |  | 0 | Y | See ADD ALT
37 | Crack isolation membranes as required | Y |  |  |  |  | 0 | Y | See ADD ALT
38 | All related sealants at tile joints | Y |  |  |  |  | 0 | Y
39 | Stone and/or solid surface thresholds as indicated | Y |  |  |  |  | 0 | Y
40 | Layout fron GC control lines and benchmarks | Y |  |  |  |  | 0 | Y
41 | Attic stock | Y |  |  |  |  | 0 | Y
42 | Include all necessary field cutting to fit and at penetrations through tile | Y |  |  |  |  | 0 | Y
43 | Clean tile after installation | Y |  |  |  |  | 0 | Y
44 | Accessories to include adhesives, mortar, grout, sealers, metal edge strips, etc. as detailed in specifications | Y |  |  |  |  | 0 | Y
C | Exclusions
1 | Plywood substrate at vanity tops | N | By Carpentry |  |  |  |  | N
2 | Cementitious backer boards | N | By Drywall |  |  |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Shop Drawings | --->
4 | Submittals | --->
5 | Advise of Lead Times
6 | Porcelain Tile | --->
7 | Quarry Tile | --->
Allowances
1 | Add Alternate #1 - Additional skim at carpet tile | [6 empty] | Y | 432 | 0
2 | Add Alternate #2 - Additional skim at resilient flooring | [6 empty] | Y | 1199 | 0
3 | Add Alternate #3 - Protect grille with plywood | [6 empty] | Y | 1021 | 0
4 | Add Alternate #4 - Protect resilient with kraft paper | [6 empty] | Y | 417 | 0
5 | Add Alternate #5 - Waterproofing at restroom floors | [6 empty] | Y | 2429 | 2429
6 | Add Alternate #6 - Waterproofing at shower walls | [6 empty] | Y | 768 | 768
7 | Add Alternate #7 - Waterproofing at restroom walls | [6 empty] | Y | 1309 | 1309
8 | Add Alternate #8 - Protect tile with kraft paper | [6 empty] | Y | 209 | 209
Alternates
1 | Add Alternate #1 - Additional skim at carpet tile | # |  |  |  |  | 0 | Y | 432 | 0 | N
2 | Add Alternate #2 - Additional skim at resilient flooring | # |  |  |  |  | 0 | Y | 1199 | 0 | N
3 | Add Alternate #3 - Protect grille with plywood | # |  |  |  |  | 0 | Y | 1021 | 0 | N
4 | Add Alternate #4 - Protect resilient with kraft paper | # |  |  |  |  | 0 | Y | 417 | 0 | N
5 | Add Alternate #5 - Waterproofing at restroom floors | # |  |  |  |  | 0 | Y | 2429 | 2429 | N | Incl in Base Bid
6 | Add Alternate #6 - Waterproofing at shower walls | # |  |  |  |  | 0 | Y | 768 | 768 | N | Incl in Base Bid
7 | Add Alternate #7 - Waterproofing at restroom walls | # |  |  |  |  | 0 | Y | 1309 | 1309 | N | Incl in Base Bid
8 | Add Alternate #8 - Protect tile with kraft paper | # |  |  |  |  | 0 | Y | 209 | 209 | N | Incl in Base Bid
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Floor
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Floors Etc |  |  | Admiral |  |  | Master Care Flooring |  |  | Miller Floors |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Ata Rad |  |  | Fred Nustray |  |  | Ken Ackerson |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | arad@floors-etc.com |  |  | fred@admiraldc.com |  |  | ken@mastercarefloors.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Admiral | 75000 | 142197 | 4343.94 | 221540.94 |  | 0
Trade: | 09 - CARPET, RESILIENT, RUBBER FLOORING | [5 empty] | Phone: |  | 410-329-9680 |  |  | 301-789-6393 |  |  | 727-424-1243 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Floors Etc | 132584 | 145266 | 5557 | 283407 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 132584 |  | Base Bid: | 75000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 145266 |  | Adjustments: | 142197 |  | Adjustments: | 142197 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 5557 | 2% | Bond: | 4343.94 | 2% | Bond: | 2843.94 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 283407 |  | Total Bid: | 221540.94 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y | Sales Tax Excl | 132584 | Y | Sales Tax Excl | 75000 | Y
2 | [6 empty] | 0
3 | Key Cost Breakdown
4 | Solid Vinyl Floor Tile (LVT-01, LVT-02, LVT-03) | # | $ |  |  |  | 0 | Y |  |  | Y |  |  | N
5 | Rubber Sheet Flooring (RF-02) | # | $ |  |  |  | 0 | Y |  |  | Y |  |  | N
6 | Athletic Sports Flooring (RF-01) | # | $ |  |  |  |  | Y | ADD - Master Flooring | 142197 | Y | ADD - Master Flooring | 142197
7 | Tile Carpeting (CPT-01) | # | $ |  |  |  | 0 | Y |  |  | Y |  |  | N
8 | Rubber Base (WB-01, WB-02, WB-03) | # | $ |  |  |  | 0 | Y |  |  | Y |  |  | N
9 | Vented Wall Base (VWB-01) | # | $ |  |  |  | 0 | Y |  |  | Y |  |  | N
10 | Flooring Protection (Total) | # | $ |  |  |  | 0 | Y | See Alt |  | Y | Incl in base bid |  | N
11
12 | Key Quantity Breakdown
13 | Solid Vinyl Floor Tile (LVT-01, LVT-02, LVT-03) | # | SF |  |  |  | 0 | Y |  |  | Y
14 | Rubber Sheet Flooring (RF-02) | # | SF |  |  |  | 0 | Y |  |  | Y
15 | Athletic Sports Flooring (RF-01) | # | SF |  |  |  |  | Y | ADD - Master Flooring |  | Y | ADD - Master Flooring
16 | Tile Carpeting (CPT-01) | # | SF |  |  |  | 0 | Y |  |  | Y
17 | Rubber Base (WB-01, WB-02, WB-03) | # | LF |  |  |  | 0 | Y |  |  | Y
18 | Vented Wall Base (VWB-01) | # | LF |  |  |  | 0 | Y |  |  | Y
19 | Flooring Protection (Total) | # | SF |  |  |  | 0 | Y |  |  | Y
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y |  |  | N
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
| 07 92 00 - Joint Sealants (as applicable to this Bid Package) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
| 09 65 13 - Resilient Base and Accessories | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
| 09 65 19 - Resilient Tile Flooring | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
| 09 65 66 - Resilient Athletic Flooring | Y |  |  |  |  | 0 | Y | Master Care # |  | Y | Master Care # |  | Y
| 09 68 13 - Tile Carpeting | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y
2 | Rubber Flooring | Y |  |  |  |  | 0 | Y
3 | Furnish and Install RF-01 flooring BOD [Mondo - Sports Impact - 136 Brown] | Y |  |  |  |  | 0 | Y | See Above |  | Y | See Above |  | N
4 | Furnish and Install RF-02 stairs [Nora - Normanet Grano - 5302 Angelica Root] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
5 | Includes riser and thread to platform | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
6 | Include all nosing, thresholds, and reducer strips, transition strips for a complete assembly | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
7
8 | Resilient Tile Flooring | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
9 | Flooring: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
10 | Furnish and Install (LVT-01) Solid Vinyl Floor Tile [Interface - Northern Grain A025 - A02611 Oak Satin] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
11 | Furnish and Install (LVT-02) Solid Vinyl Floor Tile [Interface - Studioset A007 - A00712 Marigold] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
12 | Furnish and Install (LVT-03) Solid Vinyl Floor Tile [Interface - Studioset A007 - A00715 Chartreuse] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
13 | Include all nosing, thresholds, and reducer strips, transition strips for a complete assembly | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
14 | [13 empty] | N
15 | Base: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
16 | Furnish and Install (WB-01) [Roppe - 694 Parchment] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
17 | Furnish and Install (WB-02) [Johnsonite - Beige WB] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
18 | Furnish and Install (WB-03) [Allstate - D24] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
19 | Furnish and Install (VWB-01) [Johnsonite - 47 Brown] | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y |  | 142197
21
22 | Carpet Flooring | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | N
23 | Furnish and Install (CPT-01) [Shaw Contract - Observe Colo 5T309 - Radient Nature 05326] | Y |  |  |  |  | 0 | Y
24 | [6 empty] | 0
25 | Standard/ General Scope | Y |  |  |  |  | 0 | Y
26 | Include all materials, tools, equipment,and hoisting, supervision, etc for this work | Y |  |  |  |  | 0 | Y
27 | All flooring included is compliant with the listed manufacturers | Y |  |  |  |  | 0 | Y
28 | Include minor leveling | Y |  |  |  |  | 0 | Y
29 | Include minor surface prep | Y |  |  |  |  | 0 | Y
30 | Include floor protection after installation | Y |  |  |  |  | 0 | Y
31 | Provide extra stock of flooring materials per specifications | Y |  |  |  |  | 0 | Y
32 | Accessories to include primers, adhesives, trim pieces, etc. | Y |  |  |  |  | 0 | Y
33 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y
34 | Skim coat for manufacturer tolerances | Y |  |  |  |  | 0 | Y
35 | Includes sloping to meet edge of dissimilar finished (i.e. terrazo tile, tile, etc.) | Y |  |  |  |  | 0 | Y
36 | Schluter edging, divider, and transition strips | Y |  |  |  |  | 0 | Y
37 | Finish floor in elevator cabs | Y |  |  |  |  | 0 | Y
38 | Application of specified sealer prior to installation of finish materials | Y |  |  |  |  | 0 | Y
39 | Multiple mobilizations required for the schedule | Y |  |  |  |  | 0 | Y
40 | All related sealants at tile joints | Y |  |  |  |  | 0 | Y
41 | Stone thresholds at doorways | Y |  |  |  |  | 0 | Y
42 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0 | Y
43 | Shop drawings, samples, product data, certifications, etc. | Y |  |  |  |  | 0 | Y
44 | Provide mock-ups per specifications | [5 empty] | 0 | Y
C | Exclusions
1 | Tile base | N | By Tile Subcontractor |  |  |  |  | N |  |  | N |  |  | N
2 | Wood base | N | By Millwork Subcontractor |  |  |  |  | N |  |  | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations:
3 | Shop Drawings | --->
4 | Submittals | --->
5 | Advise of Lead Times:
6 | Solid Vinyl Floor Tile | --->
7 | Rubber Flooring Tile | --->
8 | Tile Carpeting | --->
Allowances
1 | Alternate#1 - Additional skim at carpet tile | Y | [5 empty] | Y | 432 | 432 | N | Incl in Base Bid
2 | Alternate #2 - Additional skim at resilient flooring | Y | [5 empty] | Y | 1199 | 1199 | N | Incl in Base Bid
3 | Alternate #3 - Protect grille with plywood | Y | [5 empty] | Y | 1021 | 1021 | N | Incl in Base Bid
4 | Alternate #4 - Protect resilient with kraft paper | Y | [5 empty] | Y | 417 | 417 | N | Incl in Base Bid
5 | Deduct #1 - Deduct Walkoff Mats | Y | [5 empty] | N | Not Incl |  | Y | 121000
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Paint
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | District Construction |  |  | Precision Wall Tech |  |  | Uniconstruction |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Nazim Bensari |  |  | Keith Stevens |  |  | Roy Chaaban |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | nazim@districtcontruction.com |  |  | kstevens@precisionwall.com |  |  | roy@uniconstruyiongroup.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Uniconstruction | 107350 | 0 | 2147 | 109497 |  | 0
Trade: | 09 - PAINT & WALL COVERING | [5 empty] | Phone: |  | 571-277-6506 |  |  | 202-702-6376 |  |  | 804-666-1945 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | District Construction | 111010 | 0 | 2220.2 | 113230.2 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Precision Wall Tech | 127000 | 0 | 2540 | 129540 |  | 0
[9 empty] | Base Bid: | 111010 |  | Base Bid: | 127000 |  | Base Bid: | 107350 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 2220.2 | 2% | Bond: | 2540 | 2% | Bond: | 2147 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-210-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 113230.2 |  | Total Bid: | 129540 |  | Total Bid: | 109497 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 3 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 111010 |  |  | 127000 |  |  | 107350
2
3 | Key Cost Breakdown
4 | Polished Concrete | # | $ |  |  |  | 0 | N | Not Needed |  | N | Not Needed |  | N | Not Needed
5 | Sealed Concrete | # | $ |  |  |  | 0 | Y | 2030 |  | Y | Included |  | Y
6 | Wall Coverings | # | $ |  |  |  | 0 | N | Excluded |  | N | Excluded |  | Y
7 | Paint | # | $ |  |  |  | 0 | Y | 108980 |  | Y | Included |  | Y
8 | High Performance Coatings | # | $ |  |  |  | 0 | Y | Included |  | Y | Included |  | ? | revising proposal
9
10 | Key Quantity Breakdown
11 | Polished Concrete | # | SF |  |  |  | 0 | N |  |  | N |  |  | N
12 | Sealed Concrete | # | SF |  |  |  | 0 | Y |  |  | Y |  |  | Y
13 | Wall Coverings | # | LF |  |  |  | 0 | N |  |  | N |  |  | Y
14 | Paint | # | SF |  |  |  | 0 | Y |  |  | Y |  |  | Y
15 | High Performance Coatings | # | SF |  |  |  | 0 | Y |  |  | Y |  |  | ? | revising proposal
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 03 35 43 - Polished Concrete Finishing | Y | [5 empty] | N |  |  | N |  |  | N
| 07 92 00 - Joint Sealants (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 72 00 - Wall Coverings (as applicable to this Bid Package) | Y | [5 empty] | N |  |  | N |  |  | Y
| 09 91 13 - Exterior Painting | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 91 23 - Interior Painting | Y | [5 empty] | Y |  |  | Y |  |  | Y
| 09 96 00 - High-Performance Coatings | Y | [5 empty] | Y |  |  | Y |  |  | ?
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | Inclusions | Y |  |  |  |  | 0 | Y |  |  | Y
3 | Includes types/colors per Contract Documents for appropriate application | Y |  |  |  |  | 0 | Y |  |  | Y
4 | Refer to partition types on A8.1 | Y |  |  |  |  | 0 | Y |  |  | Y
5 | Refer to RCP on A3.1 through A3.2 | Y |  |  |  |  | 0 | Y |  |  | Y
6 | Refer to wall sections A6.1 through A6.4 or similar | Y |  |  |  |  | 0 | Y |  |  | Y
7 | Refer to details/sections A5.1 | Y |  |  |  |  | 0 | Y |  |  | Y
8 | Refer to Finish Schedule and Details A12.1 | Y |  |  |  |  | 0 | Y |  |  | Y
9 | Refer to Interior Finish Plan(s) on A12.2 & A12.3 | Y |  |  |  |  | 0 | Y |  |  | Y
10 | Sealed and polished counters | Y |  |  |  |  | 0 | Y |  |  | Y
11
12 | Concrete Finishes | Y |  |  |  |  | 0
13 | PLC -01: Polished Concrete - Ardex - Ultraflor Diamatic - Low Gloss | Y |  |  |  |  | 0 | N |  |  | N
14 | SCE-01: Sealed Concrete (BOH) - Ardex | Y |  |  |  |  | 0 | Y |  |  | Y
15
16 | Wall Coverings | Y |  |  |  |  | 0 | N |  |  | N
17 | WC-01: Wall Covering - Refer to Contract Documents for specified locations | Y |  |  |  |  | 0 | N |  |  | N
18 | Extra stock shall be supplied from the same production run as the installed materials. Store at the project site where directed. Ensure all rolls are clearly identified by manufacturer, product, pattern, and color. | Y |  |  |  |  | 0 | N |  |  | N
19
20 | Paint | Y |  |  |  |  | 0 | Y |  |  | Y
21 | Gyp/CMU walls, columns, gyp ceilings/soffits & underside of structure per Finish Schedule | Y |  |  |  |  | 0 | Y |  |  | Y
22 | Provide all paint types as specified in schedule, BOD Sherwin Williams | Y |  |  |  |  | 0 | Y |  |  | Y
23 | Hollow metal doors and frames | Y |  |  |  |  | 0 | Y |  |  | Y
24 | Paint grade wood doors | Y |  |  |  |  | 0 | Y |  |  | Y
25 | Access doors | Y |  |  |  |  | 0 | Y |  |  | Y
26 | Bulkhead at typical corridors | Y |  |  |  |  | 0 | Y |  |  | Y
27 | Paint grade wood trim (base, chair rail, crown moulding, door/window trim, etc) | Y |  |  |  |  | 0 | Y |  |  | N
28 | Concrete egress stairs | Y |  |  |  |  | 0 | Y |  |  | Y
29 | Metal pan stairs | Y |  |  |  |  | 0 | Y |  |  | Y
30 | Painted steel guardrails and handrails at stairs | Y |  |  |  |  | 0 | Y |  |  | Y
31 | Steel bollards | Y |  |  |  |  | 0 | Y |  |  | Y
32 | Colors, locations, coat(s), etc as described in specifications | Y |  |  |  |  | 0 | Y |  |  | Y
33 | Include paint types/colors per specification for appropriate application | Y |  |  |  |  | 0 | Y |  |  | Y
34 | Include "painter caulk" at miscellaneous joints to drywall (door frames, wood base, vinyl windows/doors, etc) | Y |  |  |  |  | 0 | Y |  |  | Y
35 | Include primers and block fillers | Y |  |  |  |  | 0 | Y |  |  | Y
36 | Paint at masonry walls at Pool House | Y |  |  |  |  | 0
37
38 | High Performance Coatings | Y |  |  |  |  | 0 | Y |  |  | Y
39 | Provide high performance coatings at areas indicated on the Contract Documents | Y |  |  |  |  | 0 | Y |  |  | Y
40
41 | Standard/General Scope of Work
42 | Include all material, tools, equipment, hoisting, scaffolding | Y |  |  |  |  | 0 | Y |  |  | Y
43 | Assume free use of General Contractor's material hoist [confirm with GC's] | Y |  |  |  |  | 0 | Y |  |  | Y
44 | Include minor surface prep | Y |  |  |  |  | 0 | Y |  |  | Y
45 | Protection of adjacent work not to receive paint; "caution" signs for fresh paint | Y |  |  |  |  | 0 | Y |  |  | Y
46 | Touch-up of damaged finishes | Y |  |  |  |  | 0 | Y |  |  | Y | See Alt
47 | Extra stock of materials per spec | Y |  |  |  |  | 0 | Y |  |  | Y
48 | Accessories to include primers, fillers, tapes, adhesives, sealants, etc | Y |  |  |  |  | 0 | Y |  |  | Y
49 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y |  |  | Y
50 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0 | Y |  |  | Y
51 | Mock-ups per spec | Y |  |  |  |  | 0 | Y |  |  | Y
C | Exclusions
1 | Painting or prefinished items | N | By Others |  |  |  |  | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Submittals | --->
4 | Shop Drawings | --->
5 | Advise of Lead Times
Allowances
1
2
3
4
Alternates
1 | Alternate #1 - Touch-up allowance 80 straight manhours to repaint | # | [5 empty] | ALT | ADD | 6820 | ALT | 6200 | 6200
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Sign
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Gelberg Signs |  |  | Modulex Mid Atlantic |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Dominic Young |  |  | Tom Stacey |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | dyoung@gelbergsigns.com |  |  | tom.stacey@modulex.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Gelberg Signs | 25293 | 0 | 505.86 | 25798.86 |  | 0
Trade: | 10 - SIGNAGE | [5 empty] | Phone: |  | 240-603-8187 |  |  | 301-525-1723 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Modulex Mid Atlantic | 41242.22 | 0 | 824.8444 | 42067.0644 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 25293 |  | Base Bid: | 41242.22 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 505.86 | 2% | Bond: | 824.8444 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 25798.86 |  | Total Bid: | 42067.0644 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y | [5 empty] | Y | Used in-house manufacturer |  | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  | Taxes Exclu | 25293.26 |  | Tax Incl | 41242.22
2 | [11 empty] | Deduct Tax
3 | Key Cost Breakdown
4 | Interior/ Room-Identification Panel Signage | # | $ |  |  |  | 0 | Y | 7338.94 |  | Y | 4973
5 | Exterior/Dimensional Letter Signage | # | $ |  |  |  | 0 | Y | 8688.78 |  | Y | 17169.5
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y
| 10 14 19 - Dimensional Letter Signage | Y
| 10 14 23 - Room-Identificatiion Panel Signage | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | Interior Signage | [5 empty] | 0
3 | Provide all room identification signage as shown on Contract Documents, including but not limited to: | [6 empty] | Y |  |  | Y
4 | All interior signage types as shown on drawing A11.2 including but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y
5 | ADA Signs: Helvetica medium all capital letters | Y | [5 empty] | Y |  |  | Y
6 | Panel Signs/Other Signs: Helvetica medium, mixed upper and lower case | Y | [5 empty] | Y |  |  | Y
7 | Interior panel signs, including code-required signage | Y | [5 empty] | Y |  |  | Y
8 | In areas where discrepancies are available, please note that the specifications will govern over the drawings, specifically for material type and size. | Y | [5 empty] | Y |  |  | Y
9
10 | Exterior Signage
11 | Provide all exterior signage types as shown on Contract Documents, including but not limited to: | Y | [5 empty] | Y |  |  | Y
12 | S.S. Pin mounted letter reading - " FRANK R. JELLEF RECREATION CENTER 3265 S" | Y | [5 empty] | Y |  |  | Y
13 | Finishes shall include an integral stainless steel finish, No. 4 | Y | [5 empty] | Y |  |  | Y
14 | Include all required egress signage | Y | [5 empty] | Y |  |  | N
15 | Provide plates with square corners only. No beveled edges shall be provided. | Y | [5 empty] | Y |  |  | Y
16 | Provide Basis of Design (BOD) manufacturer(s): | Y | [5 empty] | N | Gelberg Signs |  | Y
17 | 1. A.R.K. Ramos | --->
18 | 2. ASI Sign Systems, Inc. | --->
19 | 3. Gemin Signage; Gemini. Inc. | ---> | [8 empty] | Y
20 | 4. Metallic Arts | --->
21
22 | Standard / General Scope
23 | Include all material, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0 | Y |  |  | Y
24 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y |  |  | Y
25 | Provide shop dwgs, samples, product data, etc | Y |  |  |  |  | 0 | Y |  |  | Y
26 | Include all mounting accessories | Y |  |  |  |  | 0 | Y |  |  | Y
27 | Include all required warranties | Y |  |  |  |  | 0 | Y |  |  | Y
28 | All signage included should be compliant with listed manufacturers | Y |  |  |  |  | 0 | Y |  |  | Y
29 | All signage to be code compliant | Y |  |  |  |  | 0 | Y |  |  | Y
C | Exclusions
1 | Hazardous material signage in the pool mechanical room | N | By Others |  |  |  |  | N |  |  | N
2 | Water depth marking and no diving signs | N | By Others |  |  |  |  | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Submittals | --->
4 | Shop Drawings | --->
5 | Install | --->
6 | Advise of Lead Times
7 | Production | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Specialties
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Aorbis |  |  | Washington Door |  |  | Nelson Specialties |  |  | Newton Distributing |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Jalpa Thaker |  |  | Samuel Richards |  |  | John Dysard |  |  | John Edinburg |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | itb@aorbis.com |  |  | sam.richards@integratedopenings.com |  |  | john@nelson-spec.com |  |  | john@newtondistributing.com |  |  | Email |  |  | Email |  |  | Email |  | 1 | Nelson Specialties |  | 337648 | 6752.96 | 344400.96 |  | 0
Trade: | 10 - SPECIALTIES (Visual Display Units, TA's FEC's, Lockers, op partitions,matts) | [5 empty] | Phone: |  | 860-317-7100 |  |  | 202-297-5922 |  |  | 410-882-5777 |  |  | 617-431-5123 |  |  | Number |  |  | Number |  |  | Number |  | 2 | Newton Distributing |  | 344571.9 | 6891.438 | 351463.338 |  | 0
Rev/Date: | Date Issued 01-26-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Washington Door |  | 379335 | 7586.7 | 386921.7 |  | 0
[9 empty] | Base Bid: | 89734.07 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | Aorbis | 89734.07 | 365536.11 | 9105.4036 | 464375.5836 |  | 0
Contact: | Nija Thomas | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 365536.11 |  | Adjustments: | 379335 |  | Adjustments: | 337648 |  | Adjustments: | 344571.9 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | nija.thomas@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 9105.4036 | 2% | Bond: | 7586.7 | 2% | Bond: | 6752.96 | 2% | Bond: | 6891.438 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-710-7534 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 464375.5836 |  | Total Bid: | 386921.7 |  | Total Bid: | 344400.96 |  | Total Bid: | 351463.338 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 4 |  |  | 3 |  |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx | Y | Taxes excl | 89734.07 | Y | Taxes excl |  | Y | Taxes excl |  |  | Taxes exclu
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Toilet Accessories (Furnish) | # | $ |  |  |  | 0 | Y |  | 13486.07 | Y |  | 36350 | Y |  | 24315 | Y |  | 18198.9
5 | Toilet Partitions (Furnish & Install) | # | $ |  |  |  | 0 | Y |  | 13440 | Y |  | 21250 | Y |  | 10963 | Y |  | 12269
6 | Fire Extinguishers Cabinets (Furnish) | # | $ |  |  |  | 0 | Y | $714.72 (incl in bb) |  | Y |  | 1800 | Y |  | 2520 | N | ADD - Nelson | 2772
7 | Fire Extinguishers (Furnish) | # | $ |  |  |  | 0 | Y | $538 (incl in bb) |  | Y | Incl in bb | 0 | Y |  | 0 | N | Incl | 0
8 | Corner Guards (Furnish & Install) | # | $ |  |  |  | 0 | Y |  | 4744.62 | N | ADD - Nelson | 1375 | Y |  | 1250 | N | ADD - Nelson | 1375
9 | Visual Display Units (markerboards & tackerboards) (Furnish & Install) | # | $ |  |  |  | 0 | N | See Allowance Below | 0 | N | See Allowance Below | 0 | Y | See Allowance Below |  | N | See Allowance Below | 0
10 | Operable Panel Partitions (Furnish & Install) | # | $ |  |  |  | 0 | N | ADD - Nelson | 92180 | N | ADD - Nelson | 92180 | Y |  | 83800 | N | ADD - Nelson | 92180
11 | Lockers and Benches (Furnish & Install) | # | $ |  |  |  | 0 | N |  | 46655.42 | Y |  | 31350 | Y |  | 37500 | Y |  | 22747
12 | Walkoff Mats (Furnish and Install) | # | $ |  |  |  | 0 | N | ADD - Nelson | 195030 | N | ADD - Nelson | 195030 | Y |  | 177300 | N | ADD - Nelson | 195030
13 | Key Quantity Breakdown
14 | Toilet Accessories | # | ls |  |  |  | 0 | Y | 1 LS |  | Y | 1 LS |  | Y | 1 LS |  | Y | 1 LS
15 | Toilet Partitions | # | ea |  |  |  | 0 | Y | 6 |  | Y | 6 EA |  | Y | 6 EA |  | Y
16 | Fire Extinguishers Cabinets | # | ea |  |  |  | 0 | Y | 4 |  | Y | 4 EA |  | Y | 4 EA |  | N | 0
17 | Fire Extinguishers | # | ea |  |  |  | 0 | Y | 4 |  | Y | 4 EA |  | Y | 4 EA |  | N | 0
18 | Corner Guards | # | ea |  |  |  | 0 | Y | 10 |  | N | 0 |  | Y | 7 EA |  | N | 0
19 | Visual Display Units (markerboards & tackerboards) | # | ea |  |  |  | 0 | N | 0 |  | N | 0 |  | Y | 2 EA |  | N | 0
20 | Operable Partitions | # | ea |  |  |  | 0 | N | 0 |  | N | 0 |  | Y | 2 EA |  | N | 0
21 | Lockers | # | ea |  |  |  | 0 | N | 0 |  | N | Unit Price (allowance) |  | N | Unit Price (allowance) |  | Y | Unit Price (allowance)
22 | Walkoff Mats | # | ea |  |  |  | 0 | N | 0 |  | N | 2 EA |  | Y | 2 EA |  | N | 0
Section 3 - Scope of Work
| Furnish and Install All Items UON (Unless Otherwise Noted) | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements (as applicable to this Bid Package) | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | Y
| 10 11 00 - Visual Display Units (as applicable to this Bid Package) | Y | [5 empty] | N |  |  | N |  |  | Y |  |  | N
| 10 21 13 - Phenolic-Core Toilet Compartments | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | Y
| 10 22 39 - Folding Panel Partitions | Y | [5 empty] | N |  |  | N |  |  | Y |  |  | N
| 10 26 00 - Wall and Door Protection | Y | [5 empty] | Y |  |  | N |  |  | Y |  |  | N
| 10 28 00 - Toilet, Bath, and Laundry Accessories | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | Y
| 10 43 13 - Defibrillator Cabinets | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | N
| 10 44 13 - Fire Protection Cabinets | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | N
| 10 44 16 - Fire Extinguishers | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | N
| 10 51 29 - Phenolic-Core Lockers | Y | [5 empty] | Y |  |  | Y |  |  | Y |  |  | Y
| 12 48 16 - Entrance Floor Grilles | Y | [5 empty] | N |  |  | N |  |  | Y |  |  | N
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2
3 | Visual Display Units | [9 empty] | N | ADD - Allowance |  | N | ADD - Allowance |  | Y | Allowance
4 | Furnish all visual markerboard and tackerboard panels and accessories according to the Contract Documents: | Y |  |  |  |  | 0 |  |  |  | N |  |  | N |  |  | Y
5 | MB-01: Markerboard panels | Y |  |  |  |  | 0 |  |  |  | N |  |  | N |  |  | Y
6 | TB-01: Tackboard panels | Y |  |  |  |  | 0 |  |  |  | N |  |  | N |  |  | Y
7 | Provide Add Alternate for installation of markerboard and tackboard panels | ALT |  |  |  |  | 0 |  |  |  | N |  |  | N |  |  | Y
8
9 | Phenolic Core Toilet Compartments
10 | Furnish floor to ceiling toilet compartments/partitions, including all accessories required for complete installation of the work: | Y |  |  |  |  | 0
11 | TPC-01: Toilet Partition, Bradley Corp, Fashion Grey | Y |  |  |  |  | 0
12 | Hardware for the work, including screws, plugs, inserts, anchor bolts, adhesives, latch and keeper, etc. as required | Y |  |  |  |  | 0
13
14 | Toilet, Bath, and Laundry Accessories
15 | Furnish all bath and laundry accessories according to the Contract Documents: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
16 | TTD: Toilet Tissue Dispenser (single roll) , Bobrick Washroom Equipment, Inc B-2890 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
17 | TTD: Toilet Tissue Dispenser (double roll), Bobrick Washroom Equipment, Inc B-2892 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
18 | PTD: Paper Towel Dispenser (Tall), Bobrick Washrook Equipment, Inc B-35903 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
19 | PTD-1: Paper Towel Dispenser (Short), Bobrick Washroom Equipment, Inc B-35903 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
20 | TD/WR: Toilet Dispenser/Waste Receptacle, Semi-Recessed, Bobrick Washroom Equipment, Inc B3803 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
21 | WR: Waste Receptacle, Semi-Recessed | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
22 | HD: Hand Dryer, Bradley 2902-2874 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
23 | HD-1: Hair Dryer, Bradley 2902-2874 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
24 | HS-1: Hook Strip, Rockwood Model RM828 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
25 | HS-2: Hook Strip - Vandal Resistant, Rockwood Model RM828 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
26 | MH: Mop and Broom Holder (No Shelf), Bradley Corporation 9953 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
27 | MR: Mirror, Bobrick Washroom Equipment, Inc B-290 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
28 | SC/SCR : Shower Rod & Hooks, Bobrick Washroom Equipment, Inc B-6047 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
29 | SC/SCR : Shower Curtain, Construction Specialties Snap Lock Curtain System | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
30 | SCD: Seat Cover Dispenser, Bobrick Washroom Equipment, Inc. B-5181 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
31 | SD: Soap Dispenser - Wall, Bobrick Washroom Equipment, Inc B-26617 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
32 | SD-1: Soap Dispenser- Counter, Bobrick Washroom Equipment, Inc B-26617 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
33 | SD-2: Soap Dish - Shower, Bobrick Washroom Equipment, Inc B-26617 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
34 | SND: Sanitary Napkin Disposal, Bobrick Washroom Equipment, Inc B-35139 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
35 | SNV: Sanitary Napkin Vendor, Bobrick Washroom Equipment, Inc B-35139 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
36 | TB: Towel Bar | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
37 | TH: Towel Hook, Accessible | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
38 | TH-1: Towel Hook | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
39 | US: Utility Shelf | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
40 | BCS: Baby Changing Station, Koala Kare Products; Bobrick Washroom Equipment, Inc. KB300-SS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
41 | CU: Combination Unit | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
42 | FLM: Full Length Mirror, Bobrick Washroom Equipment, Inc B-290 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
43 | FSS: Folding Show Seat, Bobrick Washroom Equipment, Inc B-5181 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
44 | GB-1: Grab Bar (Back Wall), Bobrick Washroom Equipment, Inc B-5806 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
45 | GB-2: Grab Bar (Side Wall), Bobrick Washroom Equipment, Inc B-5806 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
46 | GB-3: Grab Bar (Vertical), Bobrick Washroom Equipment, Inc B-5806 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
47 | GB-4: Grab Bar (Shower), Bobrick Washroom Equipment, Inc B-5806 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
48 | GB-5: Grab Bar (Back wall-shifted to open side of toilet), Bobrick Washroom Equipment, Inc B-5806 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
49
50 | Fire Protection Services
51 | Furnish fire extinguishers and cabinets including all accessories for a complete installation: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
52 | Recessed Fire Cabinet, Larsen's Manufacturing Company 2409-R, Flat Trim | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
53 | Semirecessed Cabinet, Larsen's Manufacturing Company 2409-6R | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
54 | Surface-Mounted Cabinet, Larsen's Manufacturing Company 2409-SM | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
55 | Portable, Hand Carried Fire Extinguishers | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
56 | Wet Chemical Fire Extinguishers | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
57 | Multipurpose Dry Chemical Fire Extinguishers | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
58 | Include all required accessories | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
59
60 | Lockers
61 | Furnish and install lockers according to the Contract Documents: | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
62 | LOC-01: Lockers, ASI Accurate Traditional Phenolic Lockers, or approved equal | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
63
64 | Corner Gaurds
65 | Furnish corner guards according to the Contract Documents: | Y |  |  |  |  | 0 | Y |  |  | N | ADD - Nelson
66 | CGD-01: Corner Guards, Inpro, 3/4", surface mounted | Y |  |  |  |  | 0 | Y |  |  | N | Excluded
67
68 | Entrance Floor Mats 9 (Walk-off Grilles) | Y | [5 empty] | N |  |  | N
69 | Furnish entrance floor mats according to the Contract Documents: | Y |  |  |  |  | 0 | N |  |  | N
70 | WOG-01: Construction Specialties , Gridline G6, Stainless Steel | Y |  |  |  |  | 0 | N | ADD - Nelson |  | N | ADD - Nelson |  | Y | Included |  | N | ADD - Nelson
71 | Include accessories to include mounting brackets, repair stand, hardware, etc. | Y |  |  |  |  | 0 | N |  |  | N
72
73 | Folding Panel Partitions
74 | Provide manual operable acoustical panel partitions according to the Contract Documents | Y | [5 empty] | Y |  |  | Y
75
76 | Standard/General Scope
77 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0 | Y |  |  | Y
78 | Include all necessary accessories, fasteners, and applicable hardware required for complete installation. | Y |  |  |  |  | 0 | Y |  |  | Y
79 | Clean up to MCN dumpster | Y |  |  |  |  | 0 | Y |  |  | Y
80 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0 | Y |  |  | Y
C | Exclusions
1 | In-wall blocking | N | By Rough Carpentry Subcontractor |  |  |  |  | N |  |  | N |  |  | N |  |  | N
2 | Installation of toilet and laundry accessories | N | By Drywall Subcontractor |  |  |  |  | N |  |  | N |  |  | N |  |  | N
3 | Installation of corner guards | N | By Drywall Subcontractor |  |  |  |  | Y |  |  | N |  |  | N |  |  | N
4 | Installation of visual display | N | By Others |  |  |  |  | N | See Allowance |  | N | See Allowance |  | N | See Allowance |  | N | See Allowance
5 | Installation of fire extinguisher cabinets | N | By Drywall Subcontractor |  |  |  |  | N |  |  | N |  |  | N |  |  | N
6 | Installation of toilet partitions | N | By Drywall Subcontractor |  |  |  |  | N |  |  | N |  |  | N |  |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Submittals | --->
4 | Shop Drawings | --->
5 |  | --->
6 | Advise of Lead Times
7 | Lockers | --->
8 | Toilet Partitions | --->
9 | Folding Panel Partitions | --->
Allowances
1 | Allowance #1 - Specification 10 11 00 - Visual Display Units call out for visual display units; however, it is not shown on the Contract Drawings (MB-01 & TB-01 - Markerboard & Tackboard Panels) | # | [5 empty] | N | ADD |  | N | ADD |  | Y | ADD |  | N | ADD
2
3
4
Alternates
1 | Installation of visual displays | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Kitch Eq
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Singer |  |  | 11400, Inc. |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Jason Locke |  |  | John |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | jlocke@singerequipment.com |  |  | jerisman@11400llc.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Singer | 122135 | 7500 | 2592.7 | 132227.7 |  | 0
Trade: | 11 - Kitchen Equipment | [5 empty] | Phone: |  | 410-683-5925 |  |  | 717-847-1090 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | 11400, Inc. | 160000 | 7500 | 3350 | 170850 |  | 0
Rev/Date: | Date Issued 02-01-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 122135 |  | Base Bid: | 160000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 7500 |  | Adjustments: | 7500 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 2592.7 | 2% | Bond: | 3350 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 132227.7 |  | Total Bid: | 170850 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | 2 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 122135 |  |  | 160000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Residential Appliances | # | $ |  |  |  | 0
5 | Foodservice Equipment | # | $ |  |  |  | 0
6 | [6 empty] | 0
7 | Key Quantity Breakdown | [5 empty] | 0
8 | Residential Appliances | # | EA |  |  |  | 0
9 | Foodservice Equipment | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 113013 - RESIDENTIAL APPLIANCES | Y
| 114000 - FOODSERVICE EQUIPMENT | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Appliances | Y |  |  |  |  | 0 | N/ |  | 7500 | N/ |  | 7500
3 | Furnish and deliver (FOB jobsite) the following | Y |  |  |  |  | 0
4 | Cloth Washer | Y |  |  |  |  | 0
5 | Clothes Dryer | Y |  |  |  |  | 0
6 | Include the following accessories: | Y |  |  |  |  | 0
7 | Washer supply & discharge hoses | Y |  |  |  |  | 0
8 | 5' of flexible dryer vent duct | Y |  |  |  |  | 0
9 | Use of manufacturers/products specified | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
11 | Foodservices Equipment | Y |  |  |  |  | 0 | Y
12 | Refer FS drawings | Y |  |  |  |  | 0
13 |  | Y |  |  |  |  | 0
14 |  | Y |  |  |  |  | 0
15 |  | Y |  |  |  |  | 0
16 |  | Y |  |  |  |  | 0
17 |  | Y |  |  |  |  | 0
18 |  | Y |  |  |  |  | 0
19 |  | Y |  |  |  |  | 0
20 |  | Y |  |  |  |  | 0
21 |  | Y |  |  |  |  | 0
22 |  | Y |  |  |  |  | 0
23 |  | Y |  |  |  |  | 0
24 |  | Y |  |  |  |  | 0
25 |  | Y |  |  |  |  | 0
26 |  | Y |  |  |  |  | 0
27 |  | Y |  |  |  |  | 0
28 |  | Y |  |  |  |  | 0
29 |  | Y |  |  |  |  | 0
30 |  | Y |  |  |  |  | 0
31 |  | Y |  |  |  |  | 0
32 |  | Y |  |  |  |  | 0
33 |  | Y |  |  |  |  | 0
34 |  | Y |  |  |  |  | 0
35 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
36 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
37 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
38 | Clean up to MCN dumpster | Y |  |  |  |  | 0
39 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Plumbing and HVAC hook-ups | N | by M/P
2 | Pans at diswashers/washing machines | N | by plumbing
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Provide an add price to unload, uncrate & install/set in place appliances | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Athl Eq
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Degler Whiting |  |  | TJ Distributor |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Andrew |  |  | Jason |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | andrew@deglerwhiting.com |  |  | jason@tjdistributors.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | TJ Distributor | 173300 | 23700 | 3940 | 200940 |  | 0
Trade: | 11 - ATHELTIC EQUIPMENT | [5 empty] | Phone: |  | 484-323-2316 |  |  | 410-638-6358 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Degler Whiting | 147940 | 53606 | 4030.92 | 205576.92 |  | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 147940 |  | Base Bid: | 173300 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 53606 |  | Adjustments: | 23700 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 4030.92 | 2% | Bond: | 3940 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 205576.92 |  | Total Bid: | 200940 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 147940 |  |  | 173300
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | GYMNASIUM EQUIPMENT | # | $ |  |  |  | 0
5 | DIVIDERS | # | $ |  |  |  | 0
6 | FIXED BLEACHER | # | $ |  |  |  | 0
7 | [6 empty] | 0
8 | Key Quantity Breakdown | [5 empty] | 0
9 | Stuff | # | CY |  |  |  | 0
10 | Thing | # | SF |  |  |  | 0
11 | Stuff 2 | # | LF |  |  |  | 0
12 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 11 66 23 - GYMNASIUM EQUIPMENT | Y
| 11 66 53 - GYMNASIUM DIVIDERS | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | GYMNASIUM EQUIPMENT | Y |  |  |  |  | 0 | Y |  | 6533 | Y
3 | Furnish and Install gym equipments in the drawings including but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y
4 | Basketball Equipment | Y |  |  |  |  | 0 | Y |  |  | Y
5 | Volleyball Equipment | Y |  |  |  |  | 0 | N |  | 21500 | Y
6 | Safety Pads | Y |  |  |  |  | 0 | Y |  |  | Y
7 | Gymnasium control center | Y |  |  |  |  | 0 | Y |  |  | Y
8 | Scoreboards | Y |  |  |  |  | 0 | Y |  |  | Y
9 | Provide mounting plates, brackets, anchors, hardware, electrical wiring and components, structural steel fabrications | Y |  |  |  |  | 0 | Y |  |  | Y
10 | Basketbal equipment to include but not limited to backstop assembly, backboard, goal, overhead structure | Y |  |  |  |  | 0 | Y |  |  | Y
11 | Include wall mounted touch screen control system | Y |  |  |  |  | 0 | Y |  |  | Y
12 | Floor-mounted equipment to include but not limited to: volley ball nets and posts, floor sleeves for posts | Y |  |  |  |  | 0 | Y |  |  | Y
13 | Include Wall padding | Y |  |  |  |  | 0 | Y |  |  | Y
14 | Provide Score Boards and Scoring Console as per specs | Y |  |  |  |  | 0 | Y |  |  | Y
15 |  | Y |  |  |  |  | 0 | Y |  |  | Y
16 | GYMNASIUM DIVIDERS | Y |  |  |  |  | 0 | Y |  |  | Y
17 | Furnish and Install gym dividers in the drawings including but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y
18 | Roll-up divider systems (GYC-01 & GYC-02) | Y |  |  |  |  | 0 | Y |  |  | Y
19 | Divider curtains | Y |  |  |  |  | 0 | Y |  |  | Y
20 | Electric operator for the Work | Y |  |  |  |  | 0 | Y |  |  | Y
21 | Divider system accessories | Y |  |  |  |  | 0 | Y |  |  | Y
22 |  | Y |  |  |  |  | 0 | Y |  |  | Y
23 | FIXED BLEACHER | Y |  |  |  |  | 0 | Y |  | 25573 | Y |  | 23700
24 | Furnish and Install Portable bleacher in the drawings including but not limited to: | Y |  |  |  |  | 0 | Y |  |  | Y
25 | Provide and install bleachers | Y |  |  |  |  | 0 | Y |  |  | Y
26 |  | Y |  |  |  |  | 0 | Y |  |  | Y
27 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y
28 | Use of specified manufacturers and materials | Y |  |  |  |  | 0 | Y |  |  | Y
29 | Include all anchors and fasteners for this work | Y |  |  |  |  | 0 | Y |  |  | Y
30 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0 | Y |  |  | Y
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## FFE
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 12 - FF&E | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Int Bike Racks | Y |  |  |  |  | 0
3 | Furnish & install [qty, wall-mounted or floor-mounted, capacity, powder-coated steel] bike racks as indicated in Bike Storage Rooms | Y |  |  |  |  | 0
4 | Include Accessories to include mounting brackets, repair stand, hardware, etc. | Y |  |  |  |  | 0
5 |  | Y |  |  |  |  | 0
6 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
7 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
8 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
9 | Clean up to MCN dumpster | Y |  |  |  |  | 0
10 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## POOL
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 13 - POOLS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Trash Chutes | Y |  |  |  |  | 0
3 | [xx] dia, [xx] gauge, [galvanized, SST] trash chute(s) | Y |  |  |  |  | 0
4 | [xx] dia, [xx] gauge, [galvanized, SST] recycling chute(s) | Y |  |  |  |  | 0
5 | Factory applied sound dampening material | Y |  |  |  |  | 0
6 | Provide all necessary floor supports | Y |  |  |  |  | 0
7 | Isolator pads at chute support frames to prevent sound transmission to the floor slab | Y |  |  |  |  | 0
8 | [Provide offsets as required] | Y |  |  |  |  | 0
9 | UL B Label intake doors | Y |  |  |  |  | 0
10 | Door gasket seals as required by NFPA.82 | Y |  |  |  |  | 0
11 | Intake door baffles to prevent backdrafting | Y |  |  |  |  | 0
12 | Vent at top of chute(s) that meets NFPA requirements and extends min 4'-0" above roof and includes bird/insect screens and roof flashing | Y |  |  |  |  | 0
13 | 3/4" IPS flushing spray head above top intake | Y |  |  |  |  | 0
14 | Disinfecting and sanitizing unit (connected to flushing water supply line by Plumbing) | Y |  |  |  |  | 0
15 | 1/2" IPS sprinkler head above the top intake and alternate intakes (connection to building spinkler by Sprinkler) | Y |  |  |  |  | 0
16 | Electric interlocks for intake doors | Y |  |  |  |  | 0
17 | Manual switch at discharge and top intake to lock all intakes | Y |  |  |  |  | 0
18 | Heat detector and smoke detectors | Y |  |  |  |  | 0
19 | Odor control neutralizer | Y |  |  |  |  | 0
20 | [Trisorter / Bisorter] | Y |  |  |  |  | 0
21 | Compactors | Y |  |  |  |  | 0
22 | Trash compactor(s) | Y |  |  |  |  | 0
23 | [xx] qty, [xx] capacity, [prod./manufac.] | Y |  |  |  |  | 0
24 |  | Y |  |  |  |  | 0
25 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
26 | Include all mat'l, tools, equipment, hoisting/rigging, supervision, etc for this work | Y |  |  |  |  | 0
27 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
28 | Clean up to MCN dumpster | Y |  |  |  |  | 0
29 | Shop dwgs, samples, product data, certs, test reports, manuals, etc | Y |  |  |  |  | 0
30 | Warranties per spec | Y |  |  |  |  | 0
0
C | Exclusions
1 | Solenoid, backflow preventer and connection of flushing spray head to building plumbing | N | by plumb
2 | Connecting sanitizing unit to flushing water supply line | N | by plumb
3 | Connecting sprinkler head in chute(s) to building spinkler | N | by sprinkler
4 | Conduit, wiring and final connection for interlocks, switches and detectors | N | by elec
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Elev
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 14 - ELEVATORS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Traction Elevators | Y |  |  |  |  | 0
3 | [Qty, Capacity, Speed, Type] Traction Passenger Elevators | Y |  |  |  |  | 0
4 | [Qty, Capacity, Speed, Type] Traction Service Elevators | Y |  |  |  |  | 0
5 | Hoistway equipment to include hoisting & governor ropes, counterweights | Y |  |  |  |  | 0
6 | Machine room equipment to include machines with hoisting motors w/VVVF drives, speed governors, brakes, deflector sheaves | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | Hydraulic Elevators | Y |  |  |  |  | 0
9 | [Qty, Capacity, Speed, Type] Hydraulic Passenger Elevators | Y |  |  |  |  | 0
10 | [Qty, Capacity, Speed, Type] Hydraulic Service Elevators | Y |  |  |  |  | 0
11 | Hoistway equipment to include casing, jack unit assembly & scavenger pump | Y |  |  |  |  | 0
12 | Machine room equipment to include hydraulic pump, power unit, oil tank & piping | Y |  |  |  |  | 0
13 | Augering of jack-hole | Y |  |  |  |  | 0
14 |  | Y |  |  |  |  | 0
15 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
16 | Advise elevator operator rate for elevator shaft point up | Y |  |  |  |  | 0
17 | Temporary inspection for temporary construction use | Y |  |  |  |  | 0
18 | Use of [##] elevator cab(s) for temporary contruction use for [##] months | Y |  |  |  |  | 0
19 | Advise if size of hoistway opening is acceptable for your standard cab req'ments | Y |  |  |  |  | 0
20 | Include all mat'l, tools, equipment, hoisting/rigging, supervision, etc for this work | Y |  |  |  |  | 0
21 | 12-month maintenance service | Y |  |  |  |  | 0
22 | ADA compliant | Y |  |  |  |  | 0
23 | Microprocessor-based Controller with Supervisory Control of all elevators | Y |  |  |  |  | 0
24 | Features to include Independent Service, Firefighters' Service, Emergency Service, Anti-Nuisance, Standby Power Operation, Battery back-up; Infrared door re-opening; buzzers, self-leveling, etc | Y |  |  |  |  | 0
25 | Hoistway equipment to include guide rails and brackets, buffers | Y |  |  |  |  | 0
26 | Steel-framed cabs to include wood platform; wall & ceiling finishes, padded blankets & hooks, swing panels, railings, cab doors & door operators, ventilation | Y |  |  |  |  | 0
27 | Include hoistway entrances and doors; furnish sills for grouting by others | Y |  |  |  |  | 0
28 | Include custom elements/material upgrades at Lobby [list custom elements] | Y |  |  |  |  | 0
29 | Signal equipment to include hall stations, car stations, car position indicators, hall annunciators, etc including all fixtrues, text, graphics, faceplates, etc. | Y |  |  |  |  | 0
30 | All electrical wiring & conduit/travel cables back to elevator disconnect; cab/car lighting; wiring/rough-in for security and communications | Y |  |  |  |  | 0
31 | Sound/vibration isolation | Y |  |  |  |  | 0
32 | Permits, Testing, Inspections and related fees for this work | Y |  |  |  |  | 0
33 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
34 | Clean up to MCN dumpster | Y |  |  |  |  | 0
35 | Shop dwgs, samples, product data, certs, test reports, manuals, etc | Y |  |  |  |  | 0
36 | Warranties per spec | Y |  |  |  |  | 0
37 |  | Y |  |  |  |  | 0
38 | LEED Issues: | Y |  |  |  |  | 0
39 | Energy efficiency achieved with gearless system | Y |  |  |  |  | 0
40 | Bio-based hydraulic oils | Y |  |  |  |  | 0
41 | Fabrication within 500-mile radius | Y |  |  |  |  | 0
42 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Elevator cab protection | N
2 | Hoistway final cleaning | N
3 | Removal of jack-hole spoils | N
4 | Temporary safety rails at hoistway openings | N
5 | Grouting of elevator sills | N
6 | Miscellaneous metals such as machine beams, hoist beams, divider beams, intermediate guiderail support, sill angles, pit ladders, pit grating, etc | N
7 | Flooring at elevator cab | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## FireP
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 21 - FIRE PROTECTION | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | 2026-01-27 | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | Marcel El Khoury | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | marcel.el-khoury@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | 202-394-6792 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 210500 COMMON WORK RESULTS FOR FIRE SUPPRESSION | Y
| 210523 GENERAL-DUTY VALVES FOR WATER-BASED FIRE-SUPPRESSION PIPING | Y
| 210529 HANGERS AND SUPPORTS FOR FIRE-SUPPRESSION PIPING AND EQUIPMENT | Y
| 210553 IDENTIFICATION FOR FIRE-SUPPRESSION PIPING AND EQUIPMENT | Y
| 211000 WATER-BASED FIRE-SUPPRESSION SYSTEMS | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish and install tamper switches, flow switches, pressure switches | Y |  |  |  |  | 0
3 | Furnish and install a UL listed fire stopping and sealing of all floor and wall penetrations associated with this scope of work | Y |  |  |  |  | 0
4 | Design, furnish and install a complete fire protection system hydraulically calculated in compliance with the latest adopted edition N.F.P.A. 13,14,20,70, 101 and the requirements of all authorities having jurisdiction. | Y |  |  |  |  | 0
5 | Furnish and layout all access doors for concealed equipment, valves, and devices | Y |  |  |  |  | 0
6 | Furnish all close-out requirements and documents (As-builts, O&M Manuals, testing certifications, attic stock, etc.) | Y |  |  |  |  | 0
7 | Furnish and install identification, color coding, stenciling, tagging and underground marking for this scope of work. | Y |  |  |  |  | 0
8 | Furnish and install all hangers, and supports any other items required for support of your work. | Y |  |  |  |  | 0
9 | Furnish and install all miscellaneous supports, hanging supports required for equipment included in this scope of work including physical layout | Y |  |  |  |  | 0
10 | Provide coordination with architect/engineer for all cutting & core drilling & patching of walls, floors and/or structural members required for this scope of work | Y |  |  |  |  | 0
11 | Provide x-ray or GPR for all core drills | Y |  |  |  |  | 0
12 | Provide all rigging & hoisting required for sprinkler work | Y |  |  |  |  | 0
13 | Provide all trade specific permits, inspections and associated fees | Y |  |  |  |  | 0
14 | Schedule, coordinate and assist with all testing and inspections, 3rd party inspections, and commissioning for this work | Y |  |  |  |  | 0
15 | All work requiring downtime of an enabled Fire Protection system of any area shall be scheduled 2 weeks in advance, and shall comply with interim life safety measures | Y |  |  |  |  | 0
16 | Provide BIM Coordination design assistance - Mechanical sub to lead | Y |  |  |  |  | 0
17 | comply with specifications for coordinated drawings | Y |  |  |  |  | 0
18 | Coordinate all work with project phasing requirements | Y |  |  |  |  | 0
19 | Standpipes and fire dept valves at egress stairwells per contract documents and specifications if required, if not, provide fire sprinkler riser | Y |  |  |  |  | 0
20 | Furnish and install FDC that is attached to the building, if any required | Y |  |  |  |  | 0
21 | Furnish FDC Post (typ) - refer to 11/FP3.1 - Post is on site - all water connections to post in the building to be furnished and installed by you and stubbed out to 5' outside of build - site utlities subcontractor to connect to stubbed out pipe and install FDC post furnished by you. | Y
22 | Provide all equipment neccesssary to comply with vibration and seismic controls requirements | Y |  |  |  |  | 0
23 | Provide Alarm Valve at fire service entrance at buildings | Y |  |  |  |  | 0
24 | Control panels | Y |  |  |  |  | 0
25 | Fire Hose valves with hose rack assembly & cabinet | Y |  |  |  |  | 0
26 |  | Y |  |  |  |  | 0
27 | note: Sprinkler pipe tpo be schedule 40 black steel | Y |  |  |  |  | 0
28 | note: Drain pipe to be schedule 40 GI | Y |  |  |  |  | 0
29 | [6 empty] | 0
30 | General | Y |  |  |  |  | 0
31 | All shop drawings, submittals and final permit drawings for final inspection | Y |  |  |  |  | 0
32 | Hydraulic Calculations | Y
33 | Identification & Tagging | Y
34 | System final test and as required per plans and specs | Y
35 | Hydrostatic, Function and backflow tests, etc… | Y
36
C | Exclusions
1 | Concrete Pads | N | by concrete
2 | Installation of Access Doors | N | by drywall
3 | Power Wiring of fire protection equipment | N | by elec
4 | Sales Tax | N | Public Job
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Duration to install sprinkler pipe network | --->
4 | Duration to install sprinkler heads | --->
5 |  | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Engineered Drawings/Submittals | --->
9 | Sprinkler Pipe | --->
10 | Sprinkler heads | --->
Allowances
1
2 | N/A
3
4
Alternates
1 |  | #
2 | ALT 01: Provide Payment & Performance Bond | #
3 | ALT 02: Jockey pump and or fire pump (advise if needed - non shown) | #
4 | ALT 03: Furnish fire protection backflow preventer (installed by plumber) | #
5
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Plumb
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 22 - PLUMBING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | 2026-01-27 | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | Marcel El Khoury | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | marcel.el-khoury@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | 202-394-6792 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Plumbing Fixtures | # | $ |  |  |  | 0
5 | Water Source Heat pump Water Heater | # | $ |  |  |  | 0
6 | electric Domestic water Heaters | # | $ |  |  |  | 0
7 | Domestic water distribution pipes | # | $ |  |  |  | 0
8 | Sanitary and Waste water pipes | # | $
9 | Storm water and roof drainage pipes | # | $
10 |  | # | $
11 | [6 empty] | 0
12 | Key Quantity Breakdown | [5 empty] | 0
13 | Domestic water distribution pipes | # | LF |  |  |  | 0
14 | Sanitary and Waste water pipes | # | LF |  |  |  | 0
15 | Storm water and roof drainage pipes | # | LF |  |  |  | 0
16 |  | # | EA |  |  |  | 0
17 |  | # | EA
18 | [6 empty] | 0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
1 | Division 01 - General Requirements | Y
2 | 220500 COMMON WORK RESULTS FOR PLUMBING | Y
3 | 220523 GENERAL-DUTY VALVES FOR PLUMBING PIPING | Y
4 | 220529 HANGERS AND SUPPORTS FOR PLUMBING PIPING AND EQUIPMENT | Y
5 | 220533 HEAT TRACING FOR PLUMBING PIPING | Y
6 | 220548.13 VIBRATION CONTROLS FOR PLUMBING PIPING AND EQUIPMENT | Y
7 | 220553 IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | Y
8 | 221116 DOMESTIC WATER PIPING | Y
9 | 221119 DOMESTIC WATER PIPING SPECIALTIES | Y
10 | 221123.13 DOMESTIC-WATER PACKAGED BOOSTER PUMPS | Y
11 | 221123.21 INLINE, DOMESTIC-WATER PUMPS | Y
12 | 221316 SANITARY WASTE AND VENT PIPING | Y
13 | 221319 SANITARY WASTE PIPING SPECIALTIES | Y
14 | 221319.13 SANITARY DRAINS | Y
15 | 221323 SANITARY WASTE INTERCEPTORS | Y
16 | 221414 STORM DRAINAGE PIPING | Y
17 | 221423 STORM DRAINAGE PIPING SPECIALTIES | Y
18 | 221429 SUMP PUMPS | Y
19 | 223300 ELECTRIC, DOMESTIC-WATER HEATERS | Y
20 | 224200 COMMERCIAL PLUMBING FIXTURES | Y
21 | 224500 EMERGENCY PLUMBING FIXTURES | Y
22 | 224700 DRINKING FOUNTAINS AND WATER COOLERS | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2
3 | Furnish and install a complete Domestic Water, Storm, Sanitary with all components, accessories, tests and adjustments as necessary to render a fully operational and complete working system. | Y
4 | Cut, Cape and Make safe - demolition is by others | Y
5 | Installation of plumbing equipment per code and service access | Y
6 | coordinate slab penetrations w/strut, mech, electrical and utilities subcontractor | Y
7 | Flush, pressure test, sanitize and sterilize piping systems in compliance with state and local codes | Y
8 | Provide all trade specific permits, inspections and associated fee. | Y
9 | Furnish and install floor drains, roof drains & trench drains as shown and specified in contract documents. | Y
10 | Furnish and install and provide factory certified start-up of Filtration Skids if applicable | Y
11 | Furnish and install a complete elevator sump pump with necessary controls and accessories. Electrical connections by Electrical Contractor. Coordinate work with other trades. | Y
12 | Furnish and install Goethermal mainfold Sump Pump see MS101 | Y
13 | Furnish and install all necessary piping and accessories for grease interceptor per contract documents | Y
14 | Furnish and install trap primers per contract documents. | Y
15 | Furnish and install all hot water heating equipment per contract documents. | Y
16 | Furnish and install plumbing fixtures per contract documents | Y
17 | Furnish and install all domestic water accessories per contract documents | Y
18 | Furnish and install domestic water to 5' out & connection to site water service | Y
19 | Furnish and install fire service to 5' out and connection to site fire service - Furnish and install of fire protection backflow preventer is by this subcontractor | Y
20 | Furnish and install sanitary sewer to 5' out with cleanout & connection to site sewer | Y
21 | Furnish and install storm sewer to 5' out with cleanout & connection to site sewer | Y
22 | Provide excavation & backfill and compaction for your scope of work as it extends to 5' outside of building | Y
23 | Furnish and install hangers, supports & sway bracing for piping and equipment provided under this scope | Y
24 | Provide all rigging & hoisting required for this scope of work | Y
25 | Provide all cutting & core drilling & patching of walls, floors and/or structural members required for Plumbing work | Y
26 | Provide x-ray or GPR for all core drill | Y
27 | Provide and Install fire stopping & moisture sealing of penetrations for plumbing work as specified | Y
28 | Furnish and Install sleeves for piping though slabs, walls & partitions where specified. Subcontractor to coordinate piping locations prior to drywall installation | Y
29 | Furnish access doors for concealed valves and devices as needed - Install by DIV09 see exclusions | Y
30 | Furnish as built drawings & O&M manuals | Y
31 | Warranties as specified including extended warranties specified in individual specification sections | Y
32 | Daily clean up to MCN supplied dumpster | Y
33 | Temporary water for the course of construction | Y
34 | BIM and coordinated drawings | Y
35 | Schedule, coordinate and assist with all testing and inspections, 3rd party inspections, and commissioning for this work | Y
36
37 | Furnish and Install Under slab on grade drain tile if needed - Please advise | Y
38 | Plumber to provide sleeves for any incoming utilities going through foundations/walls | Y
39 | Furnish and install grease interceptor | Y
40 | It is the responsibility of this subcontractor to furnish and install 6" waste from pool house connected to site sewer as shown on P2.1 - Please advise if full connection is by you | Y
41 | It is the responsibility of this subcontractor to furnish and install 2" CW from main building to pool house - piping to be heat traced for freeze protection - please advise if heat tracing required, and please advise if all connection from house to pool is included in your number | Y
42
43 | Furnish and install backflow preventers as shown | Y
44 | Connections to site storm for roof drains and overflow drains- SU subcontractor to stub out connection to 5' out of building | Y
45 | Bronze Downspout Nozzle connected to building façade | Y
46
47 | All plumbing fixtures as scheduled | Y
48 | - See P6.1 - all fixtures listed to be furnished and installed by this subcontractor | Y
49
50 | Water Surce heat pump Domestic Water Heater - and connections to HPWR/HPWS | Y
51
52 | Electric Domestic Water Heater | Y
53
54 | Backflow Preventer | Y
55
56 | Pumps as scheduled | Y
57
58 | Mixing valves | Y
59
60 | Expansion Tanks | Y
61
62 | Heat Tracing per schedule | Y
63
64 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
65 | Hangers & supports for piping and equipment provided under this scope | Y |  |  |  |  | 0
66 | All rigging & hoisting required for PHVAC work. | Y |  |  |  |  | 0
67 | Perform all cutting & core drilling required for PHVAC work | Y |  |  |  |  | 0
68 | Fire stopping & moisture sealing of penetrations for PHVAC work | Y |  |  |  |  | 0
69 | Excavation & Backfill | Y |  |  |  |  | 0
70 | Furnish access doors for concealed valves and devices | Y |  |  |  |  | 0
71 | As built drawings & O&M manuals | Y |  |  |  |  | 0
72 | Warranties as specified including extended warranties specified in individual specification sections | Y |  |  |  |  | 0
73 | Sleeves for piping though slabs, walls & partitions where specified | Y |  |  |  |  | 0
74 | Daily clean up to MCN supplied dumpster. | Y |  |  |  |  | 0
75 | Heat tracing for plumbing & HVAC piping | Y |  |  |  |  | 0
76 | Comply with specifications for coordinated drawings | Y |  |  |  |  | 0
77 | Installation of PHVAC equipment per required code and service access. | Y |  |  |  |  | 0
78 | Core drilling for all PHVAC work including x-ray or GPR | Y |  |  |  |  | 0
79 | [6 empty] | 0
C | Exclusions
1 | Concrete Pads | N
2 | Installation of Access Doors | N
3 | Fire Protection | N
4 | Power Wiring of PHVAC equipment | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Plumbing Pipes (Sanitary, domestic, stormwater) | --->
4 | Installation of Plumbing fixtures | --->
5 | Installation of equipment | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Water source water heater | --->
9 | Piping material | --->
10 | Plumbing fixtures | --->
Allowances
1
2 | N/A
3
4
Alternates
1 | ALT 01: P&P Bond | #
2 | ALT 02: Furnish Backflow Preventer | #
3 | ALT 03: Furnish and install Washing Machine | #
4 | ALT 04: Furnish and install 4" perimeter drain tile around foundation including grade clean outs (GCO) | #
5 |  | #
#
Advise
1 | Please advise what piping material assumed for Stormwater | Comment
2 | Please advise what piping material assumed for Sanitary | Comment
3 | Please advise what piping material assumed for domestic water | Comment
4 |  | #

## HVAC
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 23 - HVAC | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | 2026-01-27 | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | Marcel El Khoury | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | marcel.el-khoury@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | 202-394-6792 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 |  | # | $
5 | Water Source Heat Pumps | # | $
6 | DOAS | # | $
7 | Sheet Metal | # | $
8 | Geothermal Manifold | # | $
9 | Kitchen Exhaust Fan | # | $ |  |  |  | 0
10 | Toilet Exhaust Fans | # | $ |  |  |  | 0
11 | [6 empty] | 0
12 | Key Quantity Breakdown | [5 empty] | 0
13 | WSHPs | # | EA |  |  |  | 0
14 | DOAS | # | EA |  |  |  | 0
15 | Sheet Metal | # | LF |  |  |  | 0
16 | Kitchen Exhaust Fan | # | EA |  |  |  | 0
17 | Toilet Exhaust Fan | # | EA |  |  |  | 0
18 | [6 empty] | 0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
1 | Division 01 - General Requirements | Y
2 | 230513 COMMON MOTOR REQUIREMENTS FOR HVAC EQUIPMENT | Y
3 | 230516 EXPANSION FITTINGS AND LOOPS FOR HVAC PIPING | Y
4 | 230517 SLEEVES AND SLEEVE SEALS FOR HVAC PIPING | Y
5 | 230518 ESCUTCHEONS FOR HVAC PIPING | Y
6 | 230519 METERS AND GAGES FOR HVAC PIPING | Y
7 | 230523 GENERAL-DUTY VALVES FOR HVAC PIPING | Y
8 | 230529 HANGERS AND SUPPORTS FOR HVAC PIPING AND EQUIPMENT | Y
9 | 230548.13 VIBRATION CONTROLS FOR HVAC | Y
10 | 230553 IDENTIFICATION FOR HVAC PIPING AND EQUIPMENT | Y
11 | 230593 TESTING ADJUSTING AND BALANCING FOR HVAC | Y
12 | 230713 DUCT INSULATION | Y
13 | 230716 HVAC EQUIPMENT INSULATION | Y
14 | 230719 HVAC PIPING INSULATION | Y
15 | 230900 INSTRUMENTATION AND CONTROLS FOR HVAC | Y
16 | 232113 HYDRONIC PIPING | Y
17 | 232113.33 GROUND-LOOP HEAT-PUMP PIPING | Y
18 | 232116 HYDRONIC PIPING SPECIALTIES | Y
19 | 232123 HYDRONIC PUMPS | Y
20 | 232513 WATER TREATMENT FOR CLOSED-LOOP HYDRONIC SYSTEMS | Y
21 | 233113 METAL DUCTS | Y
22 | 233300 AIR DUCT ACCESSORIES | Y
23 | 233400 HVAC FANS | Y
24 | 233533 LISTED KITCHEN VENTILATION SYSTEM EXHAUST DUCTS | Y
25 | 233600 AIR TERMINAL UNITS | Y
26 | 233713.13 AIR DIFFUSERS | Y
27 | 233713.23 REGISTERS AND GRILLES | Y
28 | 233813 COMMERCIAL-KITCHEN HOODS | Y
29 | 237416.13 PACKAGED, LARGE-CAPACITY, ROOFTOP AIR-CONDITIONING UNITS | Y
30 | 238126 SPLIT-SYSTEM AIR-CONDITIONERS | Y
31 | 238146 WATER-SOURCE UNITARY HEAT PUMPS | Y
32 | 250923 DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Y
33 | 250924 TEMPERATURE CONTROL EQUIPMENT NAMING CONVENTIONS | Y
34 | 250950 INTEGRATION OF BUILDING AUTOMATION SYSTEMS | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish all labor, materials, appliances, equipment, tools, transportation, supervision, and services required for the Work | Y
3 | Cut, cap and make safe and refrigerant Flush out | Y
4 | Furnish and install all materials, labor and tools to provide a fully functioning mechanical controls system to include wiring, sensing devices, accessories, programming and functional testing | Y
5 | Furnish and install all mechanically operated louvers | Y
6 | Furnish and install hangers & supports for ductwork provided under this scope | Y
7 | Furnish and install hangers & supports for piping and equipment provided under this scope | Y
8 | Furnish and install insulation per piping and ductwork specification | Y
9 | Installation and support of HVAC equipment and system components per required code and service access | Y
10 | Furnish and install condensate traps and piping on all required equipment and route to nearest drain. Coordinate location of condensate piping with architect, engineer and other trades | Y
11 | Furnish and install all pipe accessories, control devices and isolation valves for Mechanical Equipment per contract documents | Y
12 | Provide all trade specific permits, inspections and associated fees | Y
13 | Comply with specifications for coordinated drawings | Y
14 | Provide all rigging & hoisting required for HVAC work | Y
15 | Provide all cutting & core drilling required for HVAC work | Y
16 | Perform x-ray or GPR for all core drills & cutting for this scope of work | Y
17 | Furnish and install fire stopping & moisture sealing of penetrations for HVAC work. Firestopping for penetrations of fire and smoke rated assembles must be an approved UL Listed Standard | Y
18 | Furnish and install sleeves for piping though slabs, walls & partitions where specified | Y
19 | Furnish and install all necessary rough ins for equipment per manufacturers IOM whether shown on drawings | Y
20 | Provide all cutting and patching required for the Work. This is for conditions where ductwork was not coordinated prior to drywall installation | Y
21 | Temporary patching required for work not completed within one working day | Y
22 | Furnish and layout all access doors for concealed equipment, valves, and devices | Y
23 | Coordinate and layout in field for all penetration through horizontal or vertical structure | Y
24 | Provide all start-up, testing, cleaning, balancing and training as required for this scope of work | Y
25 | Training, Adjusting, Testing & Balancing. Certified test reports to be provided to MCN Build within 48 hours of testing | Y
26 | Provide and install identification, color coding, stenciling, tagging and underground marking for this scope of work | Y
27 | Provide as built drawings & O&M manuals | Y
28 | Provide warranties as specified | Y
29 | Schedule, coordinate and assist with all testing and inspections, 3rd party inspections, and commissioning for this work | Y
30 | coordination with the MCN Build, electrical, and plumbing subcontractors on pipe locations | Y
31 | Coordinate the location of drains, thermostats, gas outlets, etc. with all caseworks equipment, mechanical room equipment, etc prior to commencing installation. Work not so coordinated shall be removed and properly install at the expense of the contractor | Y
32 | Lead BIM Coordination | Y
33 | Provide daily clean up to MCN supplied dumpster | Y
34 | Install smoke detectors (supplied by others) in duct, including control wiring to unit controller, contacts, accessories and programming to integration into unit controls | Y |  |  |  |  | 0
35 |  | Y |  |  |  |  | 0
36 | Geothermal heat pump coordination: | Y |  |  |  |  | 0
37 | - Geothrmal subcontractor to stub in HPWS/R HDPE pipe into geothermal vault as shown on MS100 and M200 | Y |  |  |  |  | 0
38 | - HVAC Subcontractor to provide 6" HPWS/R headers along wall with isolation valves and balance valves for each branch - branching into building from Vault - Whole manifold configuration to be by HVAC subcontractor | Y |  |  |  |  | 0
39 | - GSP-1& GSP-2 to be furnished and installed by HVAC subcontractor | Y |  |  |  |  | 0
| - Furnish and Install Ventilation blower and flexible duct at geothermal vault | Y
40 | [6 empty] | 0
41 | Equipment Schedule: | Y |  |  |  |  | 0
42 | - DOAS -1 | Y |  |  |  |  | 0
43 | -Energy recovery wheels | Y |  |  |  |  | 0
44 | -Rooftop Unit schedule - WSHP GYM | Y |  |  |  |  | 0
45 | -Distributed Water source heat pumps | Y |  |  |  |  | 0
46 | - Kitchen Make-up air unit | Y |  |  |  |  | 0
47 | -Exhaust fan - EF-1 F&I + Kitchen Exhaust Fan - KEF-1 and connections to kitchen hood including grease duct | Y |  |  |  |  | 0
48 | - Expansion tank for geothermal Loop | Y |  |  |  |  | 0
49 | -Pumps - GSP-1/GSP-2 | Y |  |  |  |  | 0
50 | - Pot feeder - PF-1 | Y
51 | - Air Seperator - AS-1 | Y
52 | - Single duct air terminal units - VAV boxes | Y
53 | - Single Duct Exhaust Air terminal units - EAVs | Y
54 | - Constant volume regulators - CVRs | Y
55 | - Grilles, registers & Diffusers | Y
56 | - Split system indoor and outdoor units | Y
57 | - Unit heaters - UH-1 | Y
58 |  | Y |  |  |  |  | 0
59 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
60 | Hangers & supports for piping and equipment provided under this scope | Y |  |  |  |  | 0
71 | All rigging & hoisting required for PHVAC work. | Y |  |  |  |  | 0
72 | Perform all cutting & core drilling required for PHVAC work | Y |  |  |  |  | 0
73 | Fire stopping & moisture sealing of penetrations for PHVAC work | Y |  |  |  |  | 0
74 | Excavation & Backfill | Y |  |  |  |  | 0
75 | Furnish access doors for concealed valves and devices | Y |  |  |  |  | 0
76 | As built drawings & O&M manuals | Y |  |  |  |  | 0
77 | Warranties as specified including extended warranties specified in individual specification sections | Y |  |  |  |  | 0
78 | Sleeves for piping though slabs, walls & partitions where specified | Y |  |  |  |  | 0
79 | Daily clean up to MCN supplied dumpster. | Y |  |  |  |  | 0
80 | Heat tracing for plumbing & HVAC piping | Y |  |  |  |  | 0
81 | Comply with specifications for coordinated drawings | Y |  |  |  |  | 0
82 | Installation of PHVAC equipment per required code and service access. | Y
83 | Core drilling for all PHVAC work including x-ray or GPR | Y
32 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Concrete Pads | N
2 | Installation of Access Doors | N
3 | Fire Protection | N
4 | Power Wiring of PHVAC equipment | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Total time for HVAC scope of work | --->
4 | Installation of Sheet Metal | --->
5 | Installation of Mech equipment | --->
6 | Installation of Mech piping
7 | Duration for Submittals and Shop Drawings | --->
8 | Advise of Lead Times:
9 | WSHPs | --->
10 | Sheet metal | --->
11 | Condensate and HDPE pipe | --->
12 | DOAS Unit | --->
Allowances
1
2 | N/A
3
4
Alternates
1 |  | #
2 | N/A | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 | N/A | #
3 |  | #
4 |  | #

## Elect
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Robinson |  |  | Mona |  |  | Freestate |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: | [10 empty] | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: | [10 empty] | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Mona | 2558140 | 177270 | 54708.2 | 2790118.2 |  | 0
Trade: | 26 - ELECTRICAL | [5 empty] | Phone: | [10 empty] | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Robinson | 2347221 | 424455.6 | 55433.532 | 2827110.132 |  | 0
Rev/Date: | 2026-01-26 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | Freestate | 2925000 | 0 | 58500 | 2983500 |  | 0
[9 empty] | Base Bid: | 2347221 |  | Base Bid: | 2558140 |  | Base Bid: | 2925000 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Walid Salhab | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 424455.6 |  | Adjustments: | 177270 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | walid.salhab@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 55433.532 | 2% | Bond: | 54708.2 | 2% | Bond: | 58500 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | (202) 655 - 6633 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 2827110.132 |  | Total Bid: | 2790118.2 |  | Total Bid: | 2983500 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | 3 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 2347221 |  |  | 2558140 |  |  | 2925000
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building Electrical | # | $ |  |  |  | 0
5 | Site Electrical | # | $ |  |  |  | 0
6 | Site transformer, ductbanks and vault | # | $ |  |  |  |  | P | Primary ductbank | 95445 |  | Primary ductbank | 38691
7 | Fire Alarm system | # | $
[7 empty] | 0 |  |  |  |  | Transformer? Pulls by pepco always (Primary, see secondary?)
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
1 | Division 01 - General Requirements | Y | [5 empty] | Y |  |  | Y |  |  | Y
2 | Division 23 - HVAC (As applies to this bid package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
3 | Division 26 - Electrical | Y | [5 empty] | Y |  |  | Y |  |  | Y
4 | Division 27 - Communications (As applied to this bid package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
5 | Division 28 - Electronic Safety and Security (As applies to this bid package) | Y | [5 empty] | Y |  |  | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
2 | SITEWORK | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
3 | Existing sports lighting control panels to be removed, stored, refinished and reinstalled per Electrical site plan and by this Subcontractor | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
4 | Existing sports lighting pole to be relocated. Subcontractor includes removal of existing poles, relocation and reinstallation including all footing, conduits, backfill etc. required. Refer to Landscape drawing for relocation area. | Y |  |  |  |  | 0 | P |  | 194010.6 | Y |  | 138579 | Y
5 | Demolition of existing pole lights and abandonment of conduit in place unless if conflicts with other site items. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
6 | Intercept and extend conduits and wires as required for this scope | Y | [5 empty] | Y |  |  | Y |  |  | Y
7 | Furnish and install new PEPCO vault, transformer and electrical feeders (concrete encased in ductbank) and associated accessories | Y | [5 empty] | Y |  |  | Y |  |  | Y
8 | Furnish and install energy metering system | Y | [5 empty] | Y |  |  | Y |  |  | Y
9 | Provide electrical utility service connection and equipment | Y | [5 empty] | Y |  |  | Y |  |  | Y
10 | Furnish and install underground conduits and feeders for electrical and low voltage systems | Y | [5 empty] | Y |  |  | Y |  |  | Y
11 | Furnish and install underground lighting and power conductors | Y | [5 empty] | Y |  |  | Y |  |  | Y
12 | [6 empty] | 0
13 | DISTRIBUTION + EMERGENCY POWER | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
14 | Provide temporary power per OSHA regulations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
15 | Furnish and install all required systems to VAV's, EAV's, motorized window shades, kitchen equipment, operable partition, gym equipment, pool equipment (refer to E2.1 and similar plans), elevator, as called out on power plans | Y | [5 empty] | Y |  |  | Y |  |  | Y
16 | Reinstall salvaged refinished lighting control panel on unistrut (refer to line item 3 above). Include extension of existing circuits to new panel location including new conduit routing as required | Y | [5 empty] | Y |  |  | Y |  |  | Y
17 | Provide power for new pool lift | Y | [5 empty] | P |  | 55000 | Y |  |  | Y
18 | Furnish and install all conduits for future PV installation per note 3 on ES.1 and electrical one line diagram. PV panels and racking is by others. | Y | [5 empty] | P |  | 80000 | Y |  |  | Y
19 | Furnish and install electrical pathways including cable trays and conduits for telecommunication items including electrical power in telecommunications rooms | Y | [5 empty] | Y |  |  | Y |  |  | Y
20 | Furnish and install general purpose electrical conduit and raceway systems including all panelboards, switchboards, distribution panels, disconnects switches, circuit breakers etc. | Y | [5 empty] | Y |  |  | Y |  |  | Y
21 | Provide 120V power connection to power supply and ADA door operation | Y | [5 empty] | Y |  |  | Y |  |  | Y
22 | Provide power for mechanical piping heat trace | Y | [5 empty] | Y |  |  | Y |  |  | Y
23 | Where homerun is longer than 75ft, use #10AWG minimum conductor sieze ILO #12 AWG for 20A, 120V circuits | Y | [5 empty] | Y |  |  | Y |  |  | Y
24 | Furnish and install all receptacles and specialty receptacles, power outlets, floor boxes, furniture whips, inverters, junction and pull boxes, occupancy sensors, photocell systems, lighting control systems as shown on plans. Coordinate between electrical and architectural plans | Y | [5 empty] | Y |  |  | Y |  |  | Y
25 | Furnish and install all grounding and bonding systems | Y | [5 empty] | Y |  |  | Y |  |  | Y
26 | Furnish and install kitchen hood control panes and associated wiring | Y | [5 empty] | Y |  |  | Y |  |  | Y
27 | Provide low voltage and communication system rough-ins, power and wiring | Y | [5 empty] | Y |  |  | Y |  |  | Y
28 | Provide heavy-duty, corrosion-resistant electrical devices and equipment in the filter room | Y | [5 empty] | Y |  |  | Y |  |  | Y
29 | Furnish and install all work required in electrical rooms per drawings and specifications provided | Y | [5 empty] | Y |  |  | Y |  |  | Y
30 | Provide power connection for owner-furnished UPS | Y | [5 empty] | Y |  |  | Y |  |  | Y
31 | Furnish and Install Surge Protective Device (SPD) | Y | [5 empty] | Y |  |  | Y |  |  | Y
32 | Generator docking station and manual transfer switch per E2.1 and ES.1 | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
33 | * Provide fuel, accessories and tools required to operate equipment for tests | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
34 | * Top off fuel after testing | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
35 | * Include a factory trained specialist to supervise the start-up | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
36 | Provide ATS switches | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
37 | DVP Utility meter | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
38 | CT Cabinet | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
39 | Provide new panels per bid documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
40 | Provide new transformers per bid documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
41 | All conduit at exposed ceilings to be in EMT conduit | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
42 | Provide Lightning Protection System per bid documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
43 | Furnish and install fire alarm complete system including all wiring, conduits, power, devices and accessories | Y | [5 empty] | Y |  |  | Y |  |  | Y
44 |  | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
45 | WIRING DEVICES + HVAC MOTOR CONNECTIONS | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
46 | Provide power connections to Electric Heaters (furnished + installed by Division 23) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
47 | Provide power connections to VRF Equipment (Branch Controllers, Heat Pump/AC split system units furnished + installed by Division 23) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
48 | Provide installation of all VFD units included (VFDs provided by others) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
49 | Provide power and connection to the heat trace system (furnished + installed by others) | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
50 |  | Y | [5 empty] | Y |  |  | Y |  |  | Y
51 | FIRE ALARM | Y | [5 empty] | Y |  |  | Y |  |  | Y
52 | Furnish and install complete fire alarm and signaling system including annunciator panel, control panel, required devices for elevator safety | Y | [5 empty] | Y |  |  | Y |  |  | Y
53 | Connect duct smoke and heat detectors (furnished + installed by Division 23) | Y | [5 empty] | Y |  |  | Y |  |  | Y
54 | Furnish and install wireguards for fire alarm notification appliances | Y | [5 empty] | Y |  |  | Y |  |  | Y
55 | Provide fire alarm system wiring, connections, and integration | Y | [5 empty] | Y |  |  | Y |  |  | Y
56 |  | Y | [5 empty] | Y |  |  | Y |  |  | Y
57 | LIGHTING | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
58 | Provide temporary lighting per OSHA regulations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
59 | Provide relocation of existing devices and light fixtures | Y | [5 empty] | Y |  |  | Y |  |  | Y
60 | Furnish and install emergency and exit lighting systems | Y | [5 empty] | Y |  |  | Y |  |  | Y
61 | Furnish and install beacon strobes
62 | Provide all new light fixtures, including all required lamps, ballasts, trim kits, housing, hangers, and reflectors | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
63 | Warranty period for all items put in polace per specification | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
64 | Replace burned out lamps prior to project turnover | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
65 | Provide all lighting control system per bid documents | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
66 | Furnish and install back boxes and conduit for fire alarm pull stations | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
67
68 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
69 | Provide conductor color coding | Y | [5 empty] | Y |  |  | Y |  |  | Y
70 | Provide core drilling and sleeves for electrical pathways | Y | [5 empty] | Y |  |  | Y |  |  | Y
71 | Provide device coverplates | Y | [5 empty] | Y |  |  | Y |  |  | Y
72 | Provide electrical system design information including load summaries, calculation methods, and equipment power notes. | Y | [5 empty] | Y |  |  | Y |  |  | Y
73 | Provide electrical system identification and labels | Y | [5 empty] | Y |  |  | Y |  |  | Y
74 | Provide room identification signage for electrical rooms | Y | [5 empty] | Y |  |  | Y |  |  | Y
75 | Provide silicone sealant at exterior light fixture back boxes | Y | [5 empty] | Y |  |  | Y |  |  | Y
76 | Provide spare spaces and breakers in panelboards | Y | [5 empty] | Y |  |  | Y |  |  | Y
77 | Provide temporary interconnections for Low Voltage systems | Y | [5 empty] | Y |  |  | Y |  |  | Y
78 | Provide Updated Panel Directories | Y | [5 empty] | Y |  |  | Y |  |  | Y
79 | Hangers & supports for conduit and equipment provided under this scope | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
80 | All rigging & hoisting required for Electrical work. | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
81 | Perform all cutting & core drilling required for Electrical work | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
82 | Fire stopping & sealing of penetrations for Electrical work | Y |  |  |  |  | 0 | Y |  |  | Y |  |  | Y
0
C | Exclusions
1 | Relocating electrical power lines | N
2 | Relocating traffic signal conduits/manholes/handholes | N
3 | Installation of Access Doors | N
4 | Providing VFD's | N
5 | Access Control devices and equipment | N
6 | Roof penetrations/pitch pockets | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## LV
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Robinsons |  |  | Genesys |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Genesys | 270408 | 150000 | 8408.16 | 428816.16 |  | 0
Trade: | 27 - LOW VOLTAGE | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Robinsons | 265415 | 210000 | 9508.3 | 484923.3 |  | 0
Rev/Date: | 2026-01-26 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 265415 |  | Base Bid: | 270408 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Walid Salhab | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 210000 |  | Adjustments: | 150000 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | walid.salhab@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 9508.3 | 2% | Bond: | 8408.16 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | (202) 655 - 6633 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 484923.3 |  | Total Bid: | 428816.16 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 265415 |  |  | 270408
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Structured Cabling, Fiber, Teledata | # | $ |  |  |  | 0
5 | Electronic Security | # | $ |  |  |  | 0
6 | Audio Visual Systems | # | $
7 | Paging, Clock and Intercom System | # | $ | [6 empty] | 91000 |  |  | 65000
8 | DAS System | # | $ | [6 empty] | 119000 |  |  | 85000
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y | [5 empty] | Y |  |  | Y
A | Specifications
1 | Division 01 - General Requirements | Y | [5 empty] | Y |  |  | Y
2 | Division 26 - Electrical (As applied to this bid package) | Y | [5 empty] | Y |  |  | Y
3 | Division 27 - Communications | Y | [5 empty] | Y |  |  | Y
4 | Division 28 - Electronic Safety and Security | Y | [5 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | COMMUNICATIONS
3 | Furnish and install cable runways, trays and support systems in telecom and IT rooms | Y |  |  |  |  | 0 | Y |  |  | Y
4 | Furnish and install all cat-5 and cat-6/6A cabling systems | Y |  |  |  |  | 0 | Y |  |  | Y
5 | Furnish and install cellular module and antennas, communications handholes, outlets, faceplates and termination components | Y |  |  |  |  | 0 | Y |  |  | Y
6 | Furnish and install CORE interlock communications wiring, accossories and required systems | Y |  |  |  |  | 0 | Y |  |  | Y
7 | Furnish and install data/AV components and wiring | Y |  |  |  |  | 0 | Y |  |  | Y
8 | Furnish and install alll structured cabling systems including UTP, STP, fiber and coaxial cables | Y | [5 empty] | Y |  |  | Y
9 | Furnish and isntall interior communications pathways including conduit, sleeves and fire-rated devices | Y | [5 empty] | Y |  |  | Y
10 | Furnish and isntall network switches | Y | [5 empty] | Y |  |  | Y
11 | Furnish and install paging and intercom system per telecom and security floor plans and specifications | Y | [5 empty] | P |  | See above | Y
12 | Furnish and install telecommunications grounding and bonding system | Y | [5 empty] | Y |  |  | Y
13 | furnish and install telecommunication racks, backboards and cable management | Y | [5 empty] | Y |  |  | Y
14 | Furnish and install wall mounted equipment enclosure, underground communications conduit and all other communications pathways, firestopping, grounding and hardware per contract documents | Y | [5 empty] | Y |  |  | Y
15 | Furnish and install wireless access points system, cabling, equipment and accessories | Y | [5 empty] | Y |  |  | Y
16 | Provide dedicated UTP cable for elevator car phone line | Y | [5 empty] | Y |  |  | Y
17 | Provide field-wired connection for modbus communications | Y | [5 empty] | Y |  |  | Y
18 | Provide IT/communications pathways and termination points | Y | [5 empty] | Y |  |  | Y
19 | Provide protective and weather-tight enclosures for devices per specifications | Y | [5 empty] | Y |  |  | Y
20 | Provide signal extension cabling for projectors and other devices (HDMI/USB-C) | Y | [5 empty] | Y |  |  | Y
21 | Provide all work shown required in IT Room 201 per drawings and specifications | Y |  |  |  |  | 0 | Y |  |  | Y
22 |  | Y | [5 empty] | Y |  |  | Y
23 | ELECTRONIC SAFETY AND SECURITY | Y | [5 empty] | Y |  |  | Y
24 | Furnish and install back boxes and conduits for card readers, including card readers and associated accessories | Y | [5 empty] | Y |  |  | Y
25 | Furnish and install complete access control system including card readers, locks and door contacts | Y | [5 empty] | Y |  |  | Y
26 | Furnish and install complete CCTV system including cameras, cables, associated accessories | Y | [5 empty] | Y |  |  | Y
27 | Furnish and install complete intrusion detection and duress/panic system including motion detectors and all associated accessories and equipemnt | Y | [5 empty] | Y |  |  | Y
28 | Furnish and install complete people counting system including equipment and associated accessories | Y | [5 empty] | Y |  |  | Y
29 | Furnish and install electric alarm bell | Y |  |  |  |  | 0 | Y |  |  | Y
30 | Furnish and install multi-conductor cables | Y |  |  |  |  | 0 | Y |  |  | Y
31 | Provide installation of auxiliary system panels, power supplies, and equipment enclosures | Y |  |  |  |  | 0 | Y |  |  | Y
32 | Provide wiring to electrified locksets | Y |  |  |  |  | 0 | Y |  |  | Y
33 |  | Y |  |  |  |  | 0 | Y |  |  | Y
34 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y
35 | Hangers & supports for conduit and equipment provided under this scope | Y |  |  |  |  | 0 | Y |  |  | Y
36 | All rigging & hoisting required for Electrical work. | Y |  |  |  |  | 0 | Y |  |  | Y
37 | Perform all cutting & core drilling required for Electrical work | Y |  |  |  |  | 0 | Y |  |  | Y
38 | Fire stopping & sealing of penetrations for Electrical work | Y |  |  |  |  | 0 | Y |  |  | Y
|  | Y |  |  |  |  | 0
|  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## EARTH
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 31 - EARTHWORK & SITE DEMO&E,S | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Erosion Controls per contract Civil Drawings including C-….. and C… | Y |  |  |  |  | 0
3 | Erosion control devices including but not limited to silt fence, super silt fence, temp dikes and swales, existing inlet protections, etc. and maintenance while on site and removal at the end of the project. | Y |  |  |  |  | 0
4 | Stone Construction entrances with gravel and wash rack , sediment tank and/or water filter bag, surface water pumping and street cleaning. | Y |  |  |  |  | 0
5 | Temporary Sediment Basin and/or Sediment Trap....Work per dwg C.... including required site demolition, temp basin excavation w/offsite disposal, riprap stone outlet, temp 18" ... 24"... DIA. CMP Riser, temp 12" CMP discharge pipe w/Connection to ex. MH or Inlet tructure. (Dewatering of sediment basin shall be by pumping surface water to a geotextile filter bag.....) | Y |  |  |  |  | 0
6 | Protection of existing trees w/Tree protection fences and tree preservation signs | Y |  |  |  |  | 0
7 | Removal of silt from Temp Basin, Sediement traps, backfilling & compaction | Y |  |  |  |  | 0
8 | Site Demolition. | Y |  |  |  |  | 0
9 | Clearing & tree removal per dwg C-…. | Y |  |  |  |  | 0
10 | Site demolition per dwg C-.... key notes .....including the removal of existing trees, shrubs , hardscape material, street curb & onsite curb, ex. planting soil mixes, asphalt, concrete and special sport field paving's w/Subbases, sidewalks, fences chain link & wooden type fence various heights (types like backstop fence), railing, light poles & footing, athletic sport equipment's, score boards, wood & metal stands and benches, concrete & brick walls and retaining walls, concrete steps, knee walls, tennis courts, planters, irrigation system etc. This work requires coordination w/other Contractors like Site Utility Contractor | Y |  |  |  |  | 0
11 | Saw cutting & Traffic Control for ex. street asphalt demolition along Pilgrim Road for new utility work. | Y |  |  |  |  | 0
12 | Salvage existing…….& Demolition of ex. Baases, Pedestal…... per key notes…./C-…… | Y |  |  |  |  | 0
13 | Removal of ex. Utility lines & structure within the limits of new grading operations regarless if it is in cut or fill areas | Y |  |  |  |  | 0
14 | Demolition of ex. Small Bldgs similar to Sheds, Planters, Storage ……. | Y |  |  |  |  | 0
15 | Building & Ex. Structure Demolition | Y |  |  |  |  | 0
16 | Complete Bldg. Demolition of ex......, including basement...Prkg Garage levels___.... & surrounded Concrete Walks, Walls...., perimeter fences etc per MCN Schedule during _____201_. Work includes the removal of ex.concrete Slabs, Footings & Foundations walls etc.... This work also requires coordination w/Support of excavation, Utility & Excavating Contractors | Y |  |  |  |  | 0
17 | Demolition of ex. Other Structures like Swimming Pools, ongrete and or elevated Conc. Decks, ....Building per MCN Schedule during September 2014. Work includes the removal of ex. Footings & Foundations walls. This work also requires coordination w/Utility Contractor when performing utility relocation | Y |  |  |  |  | 0
18 | Demolition of ex. Athletic Office Bldg. Includes the removal of footings, interior steps & walls | Y |  |  |  |  | 0
19 | Demolition of ex. Wood & Metal Exercise Equipment & Storage Bldg. | Y |  |  |  |  | 0
20 | Unclassified General Excavation | Y |  |  |  |  | 0
21 | Strip, stockpile & remove existing grass & topsoil regarless thickness (for Qty assume min 6"…) | Y |  |  |  |  | 0
22 | Base Bid - Unclassified (and /or Classified) Grading Excavation to subgrade elevations for / to ______Elevation…... per site plan C___ and structural dwg S____ and Arquitectureal A____ | Y |  |  |  |  | 0
23 | Excavation to subgrade for ___ Site Hardscapes, Sidewalk, Conc Structure -(similar to conc. stairs), landscaping & lawn area. Also includes excavation w/Layback for ______ and site retaining walls and/or steps w/Knee walls (similar to details on drawings__________) | Y |  |  |  |  | 0
24 | Exterior Layback Excavation including 3' offline and layback on a 1:1 or 1.5:1 angle of repose around..... (per Civil, Structural or Sheeting and shoring on drawings __________) | Y |  |  |  |  | 0
25 | Interior layback Excavation between level ____ and _____ including 3' offline and layback on a 1:1 or 1.5:1 angle of repose around..... Per detail on Structural or Sheeting and shoring drawings __________). Backfilling by Structural conrete contractor. | Y |  |  |  |  | 0
26 | Retaining walls Excavation w/Open cut layback. Work Includes all walls & ret-walls per key notes #1 & 2 / C-104 | Y |  |  |  |  | 0
27 | Grading for hardscapes & Pavers per Civil and Landscape drawings. | Y |  |  |  |  | 0
28 | Access construction ramps with gravel stone and relocation/removal as required | Y |  |  |  |  | 0
29 | As required provide 40' tieback installation bench for ____________Bldg per Sheeting & Shoring dwg. Coordination for sheeting work per….... | Y |  |  |  |  | 0
30 | Removal of rubble and concrete debris left by demolition contractor up to Street Level Elevation ____FT. (If debris are less than this elevation _____ then the excavating contractor shall provide credit for inplace cubic yards as listed in unit price schedule) | Y |  |  |  |  | 0
31 | Removal of rubble and concrete debris left by demolition contractor up to Street Level Elevation ____FT. (If debris are less than this elevation _____ then the excavating contractor shall provide credit for inplace cubic yards as listed in unit price schedule) | Y |  |  |  |  | 0
32 | Removal of perimeter foundation walls in lifts with sheeting and shoring operation | Y |  |  |  |  | 0
33 | Removal of spoils from sheeting/Shoring and/or underpinning including drilled soldier piles, woodlagging, tiebacks & dewatering well spoil and …... | Y |  |  |  |  | 0
34 | Removal and reinstallation of access ramp with gravel stone as required | Y |  |  |  |  | 0
35 | Heel block footing excavation and spoil removal w/Offsite Disposal | Y |  |  |  |  | 0
36 | Excavation for Soldier Pile Removal & Backfill w/Imported CR-6 material | Y |  |  |  |  | 0
37 | Remobilize and re-spread stockpiled topsoil to all areas indicated by Landscape dwgs to depths indicated | Y |  |  |  |  | 0
38 | Removal of misc. man-made obstructions within excavation (tie-back anchors, unchartered foundations, etc | Y |  |  |  |  | 0
39 | [Removal and disposal of rubble fill in basement of demolished building; removal/ disposal of exisitng foundation walls, foundations and slab-on-grade] | Y |  |  |  |  | 0
40 | Removal of miscellaneous man-made obstructions within excavation (tie-back anchors, unchartered foundations, etc) | Y |  |  |  |  | 0
41 | Provide laybacks for excavations not against shoring systems at a [1:1.5] slope | Y |  |  |  |  | 0
42 | Ensure laybacks provided enable safe excavation of foundations by others | Y |  |  |  |  | 0
43 | Stockpiling of suitable excavated material on-site for use as backfill [if site conditions allow] | Y |  |  |  |  | 0
44 | Re-mobilize and backfill perimeter foundation walls after concrete has cured; use suitable imported fill [if unable to stockpile on-site] | Y |  |  |  |  | 0
45 | Backfill of garage ramp on grade after foundation walls have cured | Y |  |  |  |  | 0
46 | Provide & maintain ramp into hole for use by all trades (conc, shoring, piles, etc) | Y |  |  |  |  | 0
47 | Remove and re-locate ramp as needed for sheeting & shoring/lagging operation | Y |  |  |  |  | 0
48 | Refer to Sheeting and Shoring plan dated [XX/XX/XX] for coordination. Include excavation around all internal, corner and crosslot bracing | Y |  |  |  |  | 0
49 | ***Other excavation items??? Vaults, elevator pits, etc*** | Y |  |  |  |  | 0
50 | Remobilize and excavate 4' to allow romoval of soldier beams and lagging by shoring contractor; include off-site disposal and backfill eith imprted CR-6 | Y |  |  |  |  | 0
51 | Rough grading of site to within .2' of new contours indicated; include all [site cuts to fill, disposal of excess material and import of suitable material] as needed | Y |  |  |  |  | 0
52 | Remobilize for fine grading of paved areas to paving subgrade | Y |  |  |  |  | 0
53 | Excavation to subgrade for curb and gutter; backfill after curb and gutter is in place | Y |  |  |  |  | 0
54 |  | Y |  |  |  |  | 0
55 | Erosion Control | Y |  |  |  |  | 0
56 | Refer to Erosion Control plan and include all inlet protections, perimeter silt fence, super silt fence, sediment tank, etc. | Y |  |  |  |  | 0
57 | Include removal of erosion control devices | Y |  |  |  |  | 0
58 | Include maintenance of sediment tank, removal and disposal of silt | Y |  |  |  |  | 0
59 | Provide a Stabilized Construction Entrance | Y |  |  |  |  | 0
60 | Include truck washing station (water connection by MCN) | Y |  |  |  |  | 0
61 |  | Y |  |  |  |  | 0
62 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
63 | Advise duration for mass excavation operation | Y |  |  |  |  | 0
64 | Pricing includes [classified/unclassified] excavation | Y |  |  |  |  | 0
65 | Include rock excavation and Blasting Plan | Y |  |  |  |  | 0
66 | Include identification, removal and disposal of contaminated soils | Y |  |  |  |  | 0
67 | Include traffic control, barricades, signs, trained flagmetn, etc for your work | Y |  |  |  |  | 0
68 | Include all street cleaning required during excavation operation | Y |  |  |  |  | 0
69 | Include dewatering operations for all perched water and rain water for your work | Y |  |  |  |  | 0
70 | Include all hauling, trucking and dump fees | Y |  |  |  |  | 0
71 | Removal & disposal of spoils for other trades to include augered piles, utility work, building/site concrete foundations/pits, elevator jack hole, heel blocks, etc. | Y |  |  |  |  | 0
72 | Provide an adequate bench (40' minimum) for tieback drilling rig | Y |  |  |  |  | 0
73 | Include all mobilizations required for non-sequential and phased work of this scope | Y |  |  |  |  | 0
74 | Hand excavation as required | Y |  |  |  |  | 0
75 | Provide all equipment, material, labor, tools, supervision, etc. | Y |  |  |  |  | 0
76 | Cooperate with Owner's Soil Testing Agency | Y |  |  |  |  | 0
0
C | Exclusions
1 | Structural excavation/backfill of concrete footings and elevator pits | N
2 | Engineering, surveying and cut sheets | N
3 | Ground water dewatering | N
4 | Temporary fence | N
5 | Aggregate subbase for paving and slab on grade | N
6 | HAZ MAT remediation | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 | Foundation excavation - solid rock | # | per CY
2 | Foundation excavation - disintegrated rock | # | per CY
3 | Trench excavation - solid rock | # | per CY
4 | Trench excavation - disintegrated rock | # | per CY
5 | Import suitable fill material | # | per CY
6 | Undercut and dispose of unsuitable material | # | per CY
7 | Spoil removal for other trades | # | per CY
8 | Handling and off-site disposal of contaminated material | # | per ton
9 | Mass rock excavation and off-site disposal - drilling and blasting | # | per CY
10 | Mass rock excavation and off-site disposal - hoe ram | # | per CY
11 | Place and compact structural fill using on-site material | # | per CY
12 | Place and compact structural fill using imported material | # | per CY
13 | Provide and place graded stone size 57 | # | per ton

## Ashalt
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Ruston |  |  | Metro Paving |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Max McManus |  |  | Christian Cordova |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | max.mcmanus@rustonpaving.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Metro Paving |  | 338765 | 6775.3 | 345540.3 |  | 0
Trade: | 32 - ASPHALT | [5 empty] | Phone: |  | 540-216-9677 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Ruston | 244380 | 102547.5 | 6938.55 | 353866.05 |  | 0
Rev/Date: | Date Issued 01-27-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 244380 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Safi Khan | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 102547.5 |  | Adjustments: | 338765 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | safi.khan@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 6938.55 | 2% | Bond: | 6775.3 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-674-5842 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 353866.05 |  | Total Bid: | 345540.3 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 244380
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | New Asphalt full depth | # | $ |  |  |  | 0 | [5 empty] | 222995
5 | New Asphalt Surface Course | # | $ | [9 empty] | 15120
6 | Marking & Striping | # | $ |  |  |  | 0 | N | MCN P | 60000 | N | MCN P | 60000
7 | Signage | # | $ |  |  |  | 0 | N | MCN P | 28000 | N | MCN P | 28000
8 | S Street Utility Cut Restoration | [5 empty] | 0 | P |  | 14547.5 |  |  | 12650
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Asphalt full depth | # | CY |  |  |  | 0
11 | New Asphalt Surface Course | # | CY |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 07 92 00 - Joint Sealants (as applies to this Bid Package) | Y
| 07 18 00 - Traffic Coating | Y
| 32 12 16 - Asphalt Paving | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Asphalt Paving | Y
3 | New Asphalt Pavement - Full depth, including stone base material per detail on CIV0105 | Y
4 | F&I asphalt paving per specs and typical pavement section | Y
5 | F&I Fine grading from subgrade (subgrade provided to Subcontractor at +/-.2 net 0) | Y
6 | Furnish proof rolling of subgrade per specifications | Y
7 | Furnish disposal of loose/waste asphalt off site | Y
8 | Broom sweep asphalt prior to installing surface pavement | Y
9 | Furnish saw cutting of existing pavement to provide a clean edge for tie of new | Y
10 | F&I all Stone Base as required for your work | Y
11 | F&I tack coats per Construction Documents | Y
12 | F&I all ties to existing asphalt | Y
13 | Furnish street sweeping and flushing for daily cleanup as associated with your work | Y
14 | F&I Slope/Swale asphalt paving as necessary to provide proper drainage | Y
15 | Take all the necessary precautionary measures at the zones of careful demolition and construction | Y
16 |  | Y
17 | Striping and Signage: | Y
18 | Provide new striping as indicated on civil drawings | Y
19 | - Fire lane markings at adjacent curb area (as req), per plans and specifications | Y
20 | - Parking | Y
21 | - Handicap Parking Striping | Y
22 | Existing striping can be covered with black paint - where applicable | Y
23 | Provide parking signage inclusive of excavation, spoil removal, foundation, post, and signage | Y
24 | Parking signage as typically required | Y
25 | Mounting of signage. | Y
26 | Number of post mounted signs included | Y
27 | Number of surface mounted signs included | Y
28 |  | Y |  |  |  |  | 0
29 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
30 | Furnish traffic control and flagman for trucks entering and leaving the site for your work | Y
31 | Stockpiling of excess spoils in a locations specified by the Contractor. Spoil removal is by the earthwork subcontractor | Y
32 | Quantiy of spoils to be hauled by Others | Y
33 | Fine grading for the Work from within +/- 0.2’ of design subgrade including stockpiling of any shortfall/excess material at a location onsite specified by the Contractor. Excavation to subgrade is by the earthwork subcontractor. Additional excavation for drainage piping, curbing, field product, etc. for the Work of this Subcontractor is the responsibility of this Subcontractor | Y
34 | Furnish Daily Clean-up and hauling of debris to GC provided Dumpster. | Y |  |  |  |  | 0
35 | Furnish Shop Drawings, Product Data and Submittals | Y |  |  |  |  | 0
0
C | Exclusions
1 | F&I curbs and gutters (By Site Concrete Subcontractor) | N |  |  |  |  | 0
2 | Furnish demo and hauling of existing curbs and pavement (By Earthwork Subcontractor) | N |  |  |  |  | 0
3 |  | N
4 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Asphalt full depth | --->
4 | Marking & Striping | --->
5 | Signage | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Asphalt full depth | --->
9 | Marking & Striping | --->
10 | Signage | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SiteConc
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | AMA Construciton |  |  | Alcoa |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Justin Alexandre |  |  | Rahi |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | justin@amaconstruction.net |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Alcoa | 215760.75 | 1800 | 4351.215 | 221911.965 |  | 0
Trade: | 32 - SITE CONCRETE | [5 empty] | Phone: |  | 202-439-1007 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | AMA Construciton | 299600 | 0 | 5992 | 305592 |  | 0
Rev/Date: | Date Issued 01-27-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 299600 |  | Base Bid: | 215760.75 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Safi Khan | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 1800 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | safi.khan@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 5992 | 2% | Bond: | 4351.215 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-674-5842 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 305592 |  | Total Bid: | 221911.965 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 299600 |  |  | 215760.75
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Flatwork and hardscape | # | $ |  |  |  | 0
5 | Curb & Gutter | # | $ |  |  |  | 0
6 | Remaining concrete work | # | $ |  |  |  | 0
7 | [6 empty] | 0
8 | Key Quantity Breakdown | [5 empty] | 0
9 | Flatwork and hardscape | # | CY |  |  |  | 0
10 | All curbs | # | LF |  |  |  | 0
11 | Spoils to be removed by others | # | CY |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y | [5 empty] | Y |  |  | Y
A | Specifications
| Division 01 - General Requirements | Y | [5 empty] | Y |  |  | Y
| 03 00 00 - Cast-In-Place Concrete (as Applies to this package) | Y | [5 empty] | Y |  |  | Y
| 32 13 14 - Concrete Paving | Y | [5 empty] | Y |  |  | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0 | Y |  |  | Y
2 | Assure to take extra precautions demolition around the historic tree areas. | Y | [5 empty] | Y |  |  | Y
3 | Provide all the flatwork and hardscape in thickness and slopes indicated; including but not limited to: | Y | [5 empty] | Y |  |  | Y
4 | - Install bick rack (supply by others) | Y | [5 empty] | Y |  |  | Y
5 | - Stone base for the Work | Y | [5 empty] | Y |  |  | Y
6 | - Sidewalk/Conc pavement | Y | [5 empty] | Y |  |  | Y
7 | - Pool Deck | Y | [5 empty] | Y |  |  | Y
8 | - Apron | Y | [5 empty] | Y |  |  | Y
9 | - Alley Entrance | Y | [5 empty] | Y |  |  | Y
10 | - Vehicular pavement | Y | [5 empty] | Y |  |  | Y
11 | - Handicap Ramp | Y | [5 empty] | Y |  |  | Y
12 | - Transformer Pad | Y | [5 empty] | Y | no detail, assumed 8" thick |  | Y
13 | - Curb and Gutter | Y | [5 empty] | Y |  |  | Y
14 | - Curb Ramp | Y | [5 empty] | Y |  |  | Y
15 | - Granite Curb | Y | [5 empty] | Y |  |  | Y
16 | - Ramps | Y | [5 empty] | Y |  |  | Y
17 | - Concrete Pavement Restoration | Y | [5 empty] | N | not shown |  | Y
18 | - Footing for the PV Canopy | Y | [5 empty] | N | locations not provided. |  | N | add w/ building Conc
19 | - Footing for the Drinking Fountain | Y | [5 empty] | Y | assumed 18" dia. x 3' depth |  | N | MCN P | 1800
20 | Provide conc curbs and sidewalks per DDOT standards and spec | Y | [5 empty] | Y |  |  | Y
21 | Provide Nosing, Expansion Joint and contraction joints for work as require. | Y | [5 empty] | Y |  |  | Y
22
23 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y |  |  | Y
24 | Include excavation for the Work | Y | [5 empty] | Y |  |  | Y
25 | - Assume rough grade to +/- 0.2' of subgrade | Y | [5 empty] | Y |  |  | Y
26 | - Indicate quanity of spoils to be hauled off by others | Y | [5 empty] | Y |  |  | Y
27 | Layout & grade control from benchmarks, cut sheet & ref Points provided by GC | Y |  |  |  |  | 0 | Y |  |  | Y
28 | Full time superintendent above foremen and foreman | Y |  |  |  |  | 0 | Y |  |  | Y
29 | Expansion joints, dowels as required | Y |  |  |  |  | 0 | Y |  |  | Y
30 | Sales Tax (if material is not deliver onsite) & special permits for this trade & fees | Y |  |  |  |  | 0 | Y |  |  | Y
31 | Saw cutting and patching to match existing | Y |  |  |  |  | 0 | Y |  |  | Y
32 | Traffic Control & Certified Flag Person | Y |  |  |  |  | 0 | Y |  |  | Y
0
C | Exclusions
1 | Site Demolition w/Offsite disposal of ex. Conc. Sidewalk, Pavers, Concrete & Curbs by Excavating Contractor | N
2 | Structural Soil Mix by Landscaping Contractor | N
3 | Balanced rough grading excavation to +/-0.2' within 50' | N
4 | Site Furnishing by Landscaping Contractor | N
5 | Tree Pit Grate conc frame By Misc. Metal Contractor | N
6 | Planting & Soil Mix by Landscaping | N
7 | Stone Cladding & Masonry work | N
8 | Sitework caulking by caulking contractor | N
9 | Misc Metal similat to Light Poles w/Concrete base by Electrical Conctractor | N
10 | Flag Pole Base footing | N
11 | All Larger - Retaining Walls w/Monumental Stairs (sim to _____) by structural concrete contractor | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 |  | --->
4 |  | --->
5 |  | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 |  | --->
9 |  | --->
10 |  | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Fence
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Century Fence |  |  | Long Fence |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Shane Fisher |  |  | Mark |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Long Fence |  | 101822 | 2036.44 | 103858.44 |  | 0
Trade: | 32 - SITE FENCING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Century Fence | 220110 | 0 | 4402.2 | 224512.2 |  | 0
Rev/Date: | Date Issued 01-27-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 220110 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Safi Khan | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 101822 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | safi.khan@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 4402.2 | 2% | Bond: | 2036.44 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-674-5842 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 224512.2 |  | Total Bid: | 103858.44 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 220110
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Decorative Metal Fence | # | $ |  |  |  | 0 | [5 empty] | 44997
5 | Decorative Metal Gate | # | $ |  |  |  | 0 |  |  |  |  | w/ above
6 | Decorative Dumpster Encloser | # | $ |  |  |  | 0 | [5 empty] | 18220
7 | Decorative Wood Screen | # | $ |  |  |  | 0 | [5 empty] | 28728
8 | Fence Relocation | [5 empty] | 0 | [5 empty] | 9877
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Decorative Metal Fence | # | LF |  |  |  | 0
11 | Decorative Metal Gate | # | LF |  |  |  | 0
12 | Decorative Dumpster Encloser | # | LF |  |  |  | 0
13 | Decorative Wood Screen | # | LF |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 03 3000 - Cast-In-Place Concrete (as applicable to this Bid Package) | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Permanent Fencing | Y |  |  |  |  | 0
3 | Fence as indicated, including but not limited to (Refer L1.3): | Y
4 | F&I decorative metal gate, Refer 1/L3.5 | Y
5 | - include concrete footing | Y
6 | - Include Gate frame | Y
7 | - include security mesh | Y
8 | - Panic bar | Y
9 | - Bracket | Y
10 | F&I decorative metal fence BOD [Monumental Iron Works], Refer 2/L3.5 | Y
11 | - include concrete footing | Y
12 | F&I decorative dumpster enclosure BOD [Omega Fence System], Refer 3,4/L3.5 | Y
13 | - include concrete footing | Y
14 | - include latch and cane bolt etc as req | Y
15 | - include horizontal louvers | Y
16 | F&I decorative wood screen, Refer 6,7/L3.1 | Y
17 | - include deep concrete footing | Y
18 | Provide all hardware, hinges and latches as required for a complete installation. | Y
19 | Foundations for fencing, including excavation, stone base, concrete, and backfill | Y
20 | Relocation of batting cage, Refer L1.3 | Y |  |  |  |  | 0
21 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
22 | Finish as indicated | Y |  |  |  |  | 0
23 | Fencing to arrive prefinished, including touch up | Y |  |  |  |  | 0
24 | F&I concrete footers for posts; including excavation for your work | Y |  |  |  |  | 0
25 | Provide all tools, equip, hoisting, etc for your work | Y |  |  |  |  | 0
26 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0
27 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
28 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
29 | Removal w/Offsite disposal & dump fees of debris generated from excavation operations inside of excavating area PROVIDE QTY OF SPOILS ____cy | Y |  |  |  |  | 0
30 | Product data, samples, shop drawings, test reports, certs, etc | Y |  |  |  |  | 0
31 | Mock-ups | Y |  |  |  |  | 0
C | Exclusions
1 | Grounding for fence | N | by Elec
2 | Removal of the Existing fence | N | by earth work
3 | Removal of the Existing Chain link fence | N | by earth work
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 |  | --->
4 |  | --->
5 |  | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 |  | --->
9 |  | --->
10 |  | --->
Allowances
1
2
3
4
Alternates
1 | F&I new sports fence to match existing. Refer to L1.3 or sim | # | [9 empty] | 248587
2 | LSL Lumber in Lieu of LVL Lumber for Engineered Wood Screen. | # | [6 empty] | Deduct: $24,110.00
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Lscape
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Complete |  |  | BeechField |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Tom Sheehan |  |  | Bonnie Pickett |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | Tom.Sheehan@completelandscapingservice.com |  |  | bonnie@beechfieldlandscaping.com |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | BeechField | 180122 | 76718.6 | 5136.812 | 261977.412 |  | 0
Trade: | 32 - LANDSCAPING & SITE FURN | [5 empty] | Phone: |  | 301-218-1800 |  |  | 410-549-1370 |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | Complete | 278805.44 | 0 | 5576.1088 | 284381.5488 |  | 0
Rev/Date: | Date Issued 01-27-2026 | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: | 278805.44 |  | Base Bid: | 180122 |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | Safi Khan | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 76718.6 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | safi.khan@mcnbuild.com | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 5576.1088 | 2% | Bond: | 5136.812 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | 202-674-5842 | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 284381.5488 |  | Total Bid: | 261977.412 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 2 |  |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx |  |  | 278805.44 |  |  | 180122
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Planting | # | $ |  |  |  | 0 |  | Breakdown | [65691] |  | Breakdown | [88380]
5 | Mulch & Seeding | # | $ |  |  |  | 0 |  | Breakdown | [9743] |  | Breakdown | [1350]
6 | Soils | # | $ |  |  |  | 0 |  | Breakdown | [28649] |  | Breakdown | [28080]
7 | Site FF&E | # | $ |  |  |  | 0 |  | Breakdown | [124879] |  | Breakdown | [44660]
8 | Signage | [7 empty] | Breakdown | [21032] |  | see Plug below
9 | Maintenance and Warranty | # | $ | [5 empty] | w/ planting |  |  | w/ planting
10
11 | Key Quantity Breakdown | [5 empty] | 0
12 | Generated Spoils | # | CY |  |  |  | 0
13 | Topsoil | # | SF |  |  |  | 0
14 | Mobilization | # | LF |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 31 2000 - Earthwork (as applies to this Bid Package) | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Plants | Y | [5 empty] | Y |  |  | Y
3 | Tree protection as per schedule. Refer to L1.0 | Y | [5 empty] | Y | Tree protection Fence | [$9,320.00] | Y | Tree protection Fence | 11184
4 | Trees, shrubs, groundcover, ferns, grasses, turf, bulds, vegetation carpet and other plantings as per legend and schedule. Refer L2.1 - L2.2 or sim | Y | [5 empty] | Y | Arborist services | [$2,130] | Y | Arborist services | 2556
5 | Seed | Y | [5 empty] | Y |  |  | Y
6 | Mulch | Y | [5 empty] | Y |  |  | N | Including maintenance on new turf | 11093
7 | - This subcontractor is responsible for bioretention plants and mulch | Y | [5 empty] | Y |  |  | Y
8 | Edging as required | Y | [5 empty] | Y |  |  | Y
9 | Soils | Y | [5 empty] | Y |  |  | Y
10 | Planting soil, including new topsoil and/or amendments per specification, assume the following depths: | Y | [5 empty] | Y |  |  | Y
11 | Seed/sod/lawn - 4" | Y | [5 empty] | Y |  |  | Y
12 | Ground cover - 6" | Y | [5 empty] | Y |  |  | Y
13 | Shrubs 16" - 20" | Y | [5 empty] | Y |  |  | Y
14 | Tree pits - various, ref to details | Y | [5 empty] | Y |  |  | Y
15 | Subcontractor is responsible for excavation +/-0.2' from 4" below finsihed grade. All excavation for plantings and rootballs beyond rough grade elevations stipulated above | Y | [5 empty] | Y |  |  | Y
16 | Scarfying subgrade/planting soil as indicated | Y | [5 empty] | Y |  |  | Y
17 | Include raking and hand work/excavation as required | Y | [5 empty] | Y |  |  | Y
18 | Subcontractor is responsible for haul of their own spoils | Y | [5 empty] | Y |  |  | Y
19 | Subsoil drain, including trenching, piping, and backfill; where appliable | Y | [5 empty] | Y |  |  | Y
20 | Supply & Install Site Furniture, Including But Not Limited To: | Y | [8 empty] | Y
21 | Bench. Ref 2/L3.2 | Y | [5 empty] | Y |  |  | Y
22 | Trash/Recycling Receptacle. REef 2/L3.4 | Y | [5 empty] | Y |  |  | Y
23 | Metal Bollards. Ref 1,6/L3.2 | Y | [5 empty] | Y | Breakdown | [22206] | N | MCN P | 26647.2
24 | Bike Racks | Y | [5 empty] | Y |  |  | Y
25 | Drinking Fountain | Y | [5 empty] | Y |  |  | Y
26 | Signage | Y | [5 empty] | Y |  |  | N | MCN P | 25238.4
27 | Provide all the signage as shown in the drawings and details. Ref L3.3 - L3.4 or sim | Y | [5 empty] | Y |  |  | N | w/above
28 | Include the mounting and footing for the signage | Y | [5 empty] | Y |  |  | N | w/above
29 | Maintenance and Warranty | Y | [5 empty] | Y |  |  | Y
30 | One year maintenance and warranty period, including provision for supplying water | Y |  |  |  |  | 0 | Y |  |  | Y
31 | Maintenance period to start from Final Completion | Y | [5 empty] | Y |  |  | Y
32 | Provide quantity of spoils for removal by othes in section below | Y | [5 empty] | Y |  |  | Y
33 | Existing trees to be included in maintenance | Y | [5 empty] | Y |  |  | Y
34
35 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0 | Y
36 | Air spade as required in Tree Protection Zone | Y
37 | Handwork as required | Y
38 | Air spading as required | Y
39 | Root pruning as required | Y
40 | Hoisting | Y
41 | Trained Flagmen as required | Y
42 | Traffic Control & Certified Flag Person as required for your trade | Y |  |  |  |  | 0
43 | Disposal of all spoils generated by this trade | Y |  |  |  |  | 0
44 | Furnishing & installation of all topsoil for plants as required | Y |  |  |  |  | 0
45 | Add mixtures & fertilizer to Planting soil Mix & topsoil's | Y |  |  |  |  | 0
46 | Soils - Testing including Planting Soil Mix and Topsoil's | Y |  |  |  |  | 0
47 | Layout work | Y |  |  |  |  | 0
48 | Full time superintendent while active | Y |  |  |  |  | 0
49 | Sales Tax (if material is not deliver onsite) & special permits for this trade & fees | Y |  |  |  |  | 0
50 | Replace damaged plants after installations | Y |  |  |  |  | 0
51 | Daily cleanup of all trash and debris resulting from the work and placement in dumpsters provided by the contractor | Y |  |  |  |  | 0
52 | Stockpiling of excess spoils in a locations specificed by the contractor. Soil removal is by the earthwork subcontractor | Y |  |  |  |  | 0
0
C | Exclusions
1 | Rough grading to +/- 0.2' to balance within 50' | N
2 | Conc site work & pavers paving by Conc. Site Work | N
3 | Water Cost | N
5 | Electrical connection to controller (by Electrical) | N
9 | Fences | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 |  | --->
4 |  | --->
5 |  | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 |  | --->
9 |  | --->
10 |  | --->
Allowances
1
2
3
4
Alternates
1 | Relocating Marker Stone, Ref L1.2 or sim | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## WetUtil
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 33 - WET UTILITIES | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
Site fire Pole FDC
2 | Utility Relocation | Y |  |  |  |  | 0
3 | Storm Drain Sewer & Structures Relocation. Including various sizes of HDPE, RCP & PVC Piping etc and new structures similar to various key notes including #_, _, of dwg C-_ _ . Including connections to existing structure & Disconnection & removal from public spcaces (and/or abandonment per DC DDOT, WSSC, WASA, MD SHA Stds) | Y |  |  |  |  | 0
4 | _" & _" Sanitary Sewer & Structures or _" Storm Drain Sewer. Including _" & _" Sanitary Sewer, Water Main, Storm drain Piping and MH's, Cleanouts & MH Flow Diverters etc. per key notes #_, _, .... etc. on dwg C-_ _ profiles on C-_ _ & C-_ _ . Work includes connections to ex. system or structure going to _____ Bldg and __. Also connection to ex. Public Structure on _______ Street. Includes all required paving removal, saw cutting. Traffic controsl and metal plates per DDOT, WASA,WSSC, MD SHA, DC Water Std. Coordinate with Sheeting Contractor refers to dwg S___ (specially at ex. ___Road) and Other Contractor. | Y |  |  |  |  | 0
5 | __" Waterline from existing water meter per note #__/C-_ _ with backflow preventor & vault per __/C-__2) and future connection cap for ___ (note #__/C-__) | Y |  |  |  |  | 0
6 | Utility Demolition - Cutting, Capping, abandon & Removal of existing Utilities lines | Y |  |  |  |  | 0
7 | After competion of utility relocation and new relocated utility (Sewer) lines are in service perform utility demolition w/disconnections in public & private areas w/Removal and/or abandonment (per MD SHA, VDOT, DC Water Stds, WSSA). | Y |  |  |  |  | 0
8 | Existing paving (asphalt & conrete) to be removed - full depth - also removal of ex. concrete to facilitate the removal & installation of new utility lines & structures per ______ Work includes required saw cutting, tarffic control and metal plates as applicable per DC Water Std. | Y |  |  |  |  | 0
9 | Remove ex. _" Water Line, Water Meter & Water Vault per _, _ & _/C-_ _. | Y |  |  |  |  | 0
10 | Ex. storm drain, San Sewer to be capped at public utility and/or private area per #__/C-__ | Y |  |  |  |  | 0
11 | Portion of ex. Storm Line and/or Sanitary Sewer in public space to be abandomned in place and capped at main per _/C-__ per Stds | Y |  |  |  |  | 0
12 | Disconnect ex. Sewer lateral from main & install water Tight bulkhead, abandon & fill w/Grout per similar setai #_/C-__ (Next to ….. at _ Road, St…..) | Y |  |  |  |  | 0
13 |  | Y |  |  |  |  | 0
14 | Water Utilities | Y |  |  |  |  | 0
15 | New _", __" DIP Water Main (W/L "_") and other sizes similar to details #__, _ _ & _ _ etc of dwg C-__ per MD SHA, DC Std | Y |  |  |  |  | 0
16 | New _" Water Meter Vault & installation of wter meter (provided by others) per DDOT DC/WASA Std, WSSC per _/C-__ (Std #...... on drawing C-__) | Y |  |  |  |  | 0
17 | _" DIP W/L to be capped for future connection per key note _/C-____ | Y |  |  |  |  | 0
18 | _" Copper line to …. irrigation system control boxes Per note __/C-__ . | Y |  |  |  |  | 0
19 | Water Connections, gate valves, fitting and thrust block per key notes on C-_ _ and details on C-__ thru C-___ | Y |  |  |  |  | 0
20 | Backflow Prevention valve w/Precast Vault per note #_/C-__ | Y |  |  |  |  | 0
21 | 6"x8" Tee Connection | Y |  |  |  |  | 0
22 | Tee w/Capping connection for 1" & 2" copper lines by others | Y |  |  |  |  | 0
23 | Sanitary Sewerage Utilities | Y |  |  |  |  | 0
24 | __" PVC Sanitary Sewer Lateral per #_ / C-__. | Y |  |  |  |  | 0
25 | __" RCP, HDPE Sanitary Sewer Lateral per #_ / C-__. | Y |  |  |  |  | 0
26 | MH Structures per note __ & __/C-___ | Y |  |  |  |  | 0
27 | Clean Out Structures per note __ & __/C-___ | Y |  |  |  |  | 0
28 | Connections to relocated MH structures per DC Std (DDOT) & Specs ____ | Y |  |  |  |  | 0
29 | Test Pits as required | Y |  |  |  |  | 0
30 |  | Y |  |  |  |  | 0
31 | Storm Drainage Utilities (includes but not limited to:) | Y |  |  |  |  | 0
32 | Temp 15" RCP Storm Pipe from ex. MH #53 to new MH D-42 (not shown) | Y |  |  |  |  | 0
33 | All HDPE, RCPR & PVC Storm Drain Sewer per _____ | Y |  |  |  |  | 0
34 | Storm MH, curn-Inlets, yarad-inlets, MH w/Pedestrian inlets structures & grate type Catch Basins w/safety grate etc per various notes and/or similar to ….. on C-____ and detail _/C-_____ | Y |  |  |  |  | 0
35 | _' x _ _ ' peak diversion MH Storm Filter Structure w/Cartridges per …..C-___ and details on C-____ | Y |  |  |  |  | 0
36 | __" x _ _" Stormgate Vault w/High Flow Bypass per __/C-___ detail on C-___ at ….. | Y |  |  |  |  | 0
37 | Solid Underdrain Collector Piping at the perimeter of ___ , _____ and associated MH's & drain basins structures per # __, ……./ C____ and detail on C-__ and/or L-_____ | Y |  |  |  |  | 0
38 | Gravel w/Filter fabric at top of collector piping at synthetic turf fields per ____ | Y |  |  |  |  | 0
39 | 4" Perforated PVC Storm along _____ per #____ / C-__ | Y |  |  |  |  | 0
40 | 6" Perf PVC wraped in aggragate and fiter fabric per detail ____/C-___ and detail _/C-___ | Y |  |  |  |  | 0
41 | Vertical 4" Perforated PVC wraped in aggregate and fabric at ….per __/C-__ (also per detail _/C-___) | Y |  |  |  |  | 0
42 | Furnish, insatll & connect - trench drain at ….. per #__/C-__. | Y |  |  |  |  | 0
43 | Connection to ex. Storm System as required | Y |  |  |  |  | 0
44 |  | Y |  |  |  |  | 0
45 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
46 | Provide certified flag person and signs, barrels, arrow boards etc. as required | Y |  |  |  |  | 0
47 | Unclassified Excavation | Y |  |  |  |  | 0
48 | All utility work up to 5' of building wall | Y |  |  |  |  | 0
49 | Adjust ex. MH covers, valve boxes, etc. per final new grades. | Y |  |  |  |  | 0
50 | Compliances with MD SHA, VDOT, WSSC, WASA, DC Water & Sewer Service Standards | Y |  |  |  |  | 0
51 | Saw Cutting, excavation, backfilling w/compaction of trenches & around of Utility MH w/acceptable suitable material per MD SHA , VDOT, WSSC, WASA & DDOT and Water Authorities Standards | Y |  |  |  |  | 0
52 | Test pits as necessary w/Handwork as required | Y |  |  |  |  | 0
53 | Surface water pumping | Y |  |  |  |  | 0
54 | Mobilization as required | Y |  |  |  |  | 0
55 | Erosion Control work for utility work for your trade including inlet protection at new inlets | Y |  |  |  |  | 0
56 | Road Plates, temp patching per DC standards | Y |  |  |  |  | 0
57 | Steel plate permit & fees as applicable | Y |  |  |  |  | 0
58 | All valves, casings, fittings casing etc. as required | Y |  |  |  |  | 0
59 | All blocking, thurst blocks, restrains & straps as required | Y |  |  |  |  | 0
60 | All test & inspections per jurisdiction regulations | Y |  |  |  |  | 0
61 | Removal w/Offsite disposal & dump fees of debris generated from demo of ex. utility pipe, structures & street paving outside of excavating area PROVIDE QTY OF SPOILS ____cy | Y |  |  |  |  | 0
62 | Backfilling of trenches with offsite approved material in in public right of way | Y |  |  |  |  | 0
63 | Necessary pumping & temp diversion pipes as required | Y |  |  |  |  | 0
0
C | Exclusions
1 | Surveying & as built drawings | N
2 | Utilities within 5' of Bldg. | N
3 | Handling & disposal of Contaminated Material | N
4 | Special Backfill similar to topsoil, Seeding & Sod... etc. | N
5 | 1" & 1-1/2" Copper lines | N
6 | Perm Patch at Roads & Other Perm Paving | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## DryUtil
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 33 - DRY UTILITIES | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | PEPCO Dry Utilities - By Richter & Associates dated ______ | Y |  |  |  |  | 0
3 | F&I Secondary | Y |  |  |  |  | 0
4 | Onsite, ductbank, manholes, transformer vaults, and bus holes, from property line to switchgear | Y |  |  |  |  | 0
5 | Onsite PEPCO tops | Y |  |  |  |  | 0
6 | Mule line for PEPCO | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Provide certified flag person and signs, barrels, arrow boards etc. as required | Y |  |  |  |  | 0
10 | Unclassified Excavation | Y |  |  |  |  | 0
11 | All utility work up to 5' of building wall | Y |  |  |  |  | 0
12 | Adjust ex. MH covers, valve boxes, etc. per final new grades. | Y |  |  |  |  | 0
13 | Compliances with MD SHA, VDOT, WSSC, WASA, DC Water & Sewer Service Standards | Y |  |  |  |  | 0
14 | Saw Cutting, excavation, backfilling w/compaction of trenches & around of Utility MH w/acceptable suitable material per MD SHA , VDOT, WSSC, WASA & DDOT and Water Authorities Standards | Y |  |  |  |  | 0
15 | Test pits as necessary w/Handwork as required | Y |  |  |  |  | 0
16 | Surface water pumping | Y |  |  |  |  | 0
17 | Mobilization as required | Y |  |  |  |  | 0
18 | Erosion Control work for utility work for your trade including inlet protection at new inlets | Y |  |  |  |  | 0
19 | Road Plates, temp patching per DC standards | Y |  |  |  |  | 0
20 | Steel plate permit & fees as applicable | Y |  |  |  |  | 0
21 | All valves, casings, fittings casing etc. as required | Y |  |  |  |  | 0
22 | Grouting of all dry utility sleeves after feeder install. | Y |  |  |  |  | 0
23 | All test & inspections per jurisdiction regulations | Y |  |  |  |  | 0
24 | Removal w/Offsite disposal & dump fees of debris generated from demo of ex. utility pipe, structures & street paving outside of excavating area PROVIDE QTY OF SPOILS ____cy | Y |  |  |  |  | 0
25 | Backfilling of trenches with offsite approved material in in public right of way | Y |  |  |  |  | 0
26 |  | Y |  |  |  |  | 0
27 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Site Lighting and Conduits | N | By Elec |  |  |  | 0
2 | F&I Site Light Fixtures | N | By Elec |  |  |  | 0
3 | F&I Site Lighting Conduit and base | N | By Elec |  |  |  | 0
4 | F&I Relocation of conduit | N | By Elec |  |  |  | 0
5 | Repeter/Responsder/Booster | N | By Elec |  |  |  | 0
6 | Duct bank, bases, and manholes for four (4) DC standard street lights allowance | N | By Elec |  |  |  | 0
7 | Conduit and boxes (pathways) for security wiring allowance | N | By Elec |  |  |  | 0
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Geotherm
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 33 - GEOTHERMAL | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Geothermal Wells | Y |  |  |  |  | 0
3 | Drill and install ___Ea [1.25, 1.5, 1.75, or 2"] diameter geothermal loops to a depth of ____feet. Referene sheets ___ of ___ | Y |  |  |  |  | 0
4 | Pipes, fitting, and manifold | Y |  |  |  |  | 0
5 | PVC casings as required | Y |  |  |  |  | 0
6 | Mechanical flanged connections | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Hangers & supports for piping and equipment provided under this scope | Y |  |  |  |  | 0
10 | All rigging & hoisting required for Geothermal work. | Y |  |  |  |  | 0
11 | Comply with specifications for coordinated drawings | Y |  |  |  |  | 0
12 | Pressure testing | Y |  |  |  |  | 0
13 | Tracer wires for geothermal work | Y |  |  |  |  | 0
14 | Complete flushing of system | Y |  |  |  |  | 0
15 | Layout for openings | Y |  |  |  |  | 0
16 | Removal w/Offsite disposal & dump fees of debris generated from drilling operations inside of excavating area PROVIDE QTY OF SPOILS ____cy | Y |  |  |  |  | 0
17 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Off-site removal of spoils | N | By Excav
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## FinalClean
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary |  | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | Bidder 1 |  | 0 | 0 | 0 |  | 0
Trade: | 01 - FINAL CLEANING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [6 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | FULL SCOPE |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [6 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [6 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [6 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [6 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [6 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | 1 |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Provide (1) rough clean, (1) final clean, and (1) touch up clean of for 49 units | Y |  |  |  |  | 0
3 | Provide rough clean and final clean of finished common areas (lobby, offices, etc.) | Y |  |  |  |  | 0
4 | Conduct cleaning and waste-removal operations to comply with local laws and ordinances and federal and local environmental and antipollution regulations. | Y |  |  |  |  | 0
5 | Clean each surface or unit to condition expected in an average commercial building cleaning and maintenance program. | Y |  |  |  |  | 0
6 | Comply with all manufacturer's written instructions. | Y |  |  |  |  | 0
7 | Remove excess lubrication, paint and mortar droppings and any other foreign substances | Y |  |  |  |  | 0
8 | Mop all areas and remove all dust from these areas for future finishes | Y |  |  |  |  | 0
9 | Clean intetior windows | Y |  |  |  |  | 0
10 | Clean exterior windows with lifts as required | Y |  |  |  |  | 0
11 | Wipe down all hand rails, railings, and clean stairs | Y |  |  |  |  | 0
12 | Mop and buff all tile per manufacturer requirements | Y |  |  |  |  | 0
13 | Clean all interior glass and wipe down all mullions | Y |  |  |  |  | 0
14 | Clean all areas used during construction | Y |  |  |  |  | 0
15 | Wipe surfaces of mechanical and electrical equipment | Y |  |  |  |  | 0
16 | Clean all plumbing fixtures to a sanitary condition, free of stains | Y |  |  |  |  | 0
17 | Vacuum all carpet surfaces | Y |  |  |  |  | 0
18 | Clean all finishes installed in the project scope | Y |  |  |  |  | 0
19 | Clean all exposed surfaces installed in the project scope | Y |  |  |  |  | 0
20 | Cleaning of all construction areas to make space ready for occupancy | Y |  |  |  |  | 0
21 | Remove your excess materials/debris to MCN's dumpster on a daily basis | Y |  |  |  |  | 0
22 | Final clean all furnishings and accessories installed in the project scope. | Y |  |  |  |  | 0
23 | Wipe down all doors and door hardwares | Y |  |  |  |  | 0
24 | Clean all light fixtures | Y |  |  |  |  | 0
25 | Final clean all furniture, televisions, millwork items, and accessories installed in the project scope. | Y |  |  |  |  | 0
26 | Final clean all items per manufacturer requirements or suggested cleaning methods | Y |  |  |  |  | 0
27 | Include the cleaning of all Parking Levels | Y |  |  |  |  | 0
28 | Provide two cleanings for back of house common areas. | Y |  |  |  |  | 0
29 | Provide cleaning of all rooms, pipes, light fixtures, ductwork, etc. in the garage level rooms, garage parking areas, etc. | Y |  |  |  |  | 0
30 | Sweep paved areas broom clean. Remove petrochemical spills, stains, and other foreign deposits | Y |  |  |  |  | 0
31 | Remove snow and ice to provide safe access to building | Y |  |  |  |  | 0
32 | MCN Allowance | N |  |  |  |  | 0
33 | Unit Punch Out | Allow. |  |  |  |  | 0
34 |  | Y |  |  |  |  | 0
35 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
36 | Provide all mat'ls, labor, equipment, tools, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
37 | Clean up to MCN dumpster | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## NA
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 12 - FF&E | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Window Washing Equipment | Y |  |  |  |  | 0
3 | Furnish and deliver roof-mounted safety tie back anchors [verify quantities] | Y |  |  |  |  | 0
4 | Furnish and deliver roof-mounted davit anchors [verify quantities] | Y |  |  |  |  | 0
5 | Furnish and deliver davit arms [verify quantities] | Y |  |  |  |  | 0
6 | Furnish and deliver window washing platform and accessories (if spec'd) | Y |  |  |  |  | 0
7 | ***Other window washing equipment*** | Y |  |  |  |  | 0
8 | Verify quantities/layout shown meet code/OSHA requirements; advise if conflict | Y |  |  |  |  | 0
9 | System designed to meet performance criteria outlined | Y |  |  |  |  | 0
10 | Visit site after installation to perform testing & inspection (provide add price) | Y |  |  |  |  | 0
11 |  | Y |  |  |  |  | 0
12 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
13 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
14 | Warranty per spec | Y |  |  |  |  | 0
0
C | Exclusions
1 | Unloading and installation (provide an add price) | N | by concrete/steel
2 | Flashing of anchors | N | by roofing
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Provide an add price to install anchors | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Version History
Date | Version | Change

## SpecMatrix
|  | project |  | Integrated Exterior Mock-Ups-ENA | Water Distribution - Brent ES | Cast-in-Place Concrete - Margaret Brent | Polished Concrete Finishing-ENA | Cast Underlayment-ENA | Unit Masonry Mortaring and Grouting-ENA | Unit Masonry-ENA | Cast Stone Masonry-ENA | Fluoropolymer Finish-ENA | Structural Steel Framing - Margaret Brent | Steel Joist Framing - Margaret Brent | Steel Decking - Margaret Brent | Metal Fabrications-ENA | Ornamental Handrails and Railings-ENA | Rough Carpentry-ENA | Sheathing-ENA | Finish Carpentry-ENA | Architectural Woodwork-ENA | Waterproofing-ENA | Thermal Insulation-ENA | Air Barriers-ENA | PVC Roofing-ENA | Sheet Metal Flashing and Trim-ENA | Applied Fireproofing-ENA | Firestopping-ENA | Joint Sealants-ENA | Hollow Metal Doors and Frames-ENA | Flush Wood Doors-ENA | Access Doors and Panels-ENA | Coiling Doors and Grilles-ENA | Overhead Coiling Fire Curtain-ENA | Folding Fire Doors-ENA | FRP Aluminum Framed Entrance Doors-ENA | Aluminum Framed Interior Storefront-ENA | Metal Framed Skylights-ENA | Glazing-ENA | Louvers and Vents-ENA | Gypsum Board-ENA | Tiling-ENA | Acoustical Ceilings-ENA | Linear Wood Ceilings-ENA | Wood Athletic Flooring-ENA | Resilient Flooring-ENA | Resilient Athletic Flooring-ENA | Resinous Matrix Terrazzo Flooring-ENA | Carpeting-ENA | Wall Coverings-ENA | FRP Panels-ENA | Acoustical Panels-ENA | Painting and Coating-ENA | Visual Display Surfaces-ENA | Signage-ENA | Toilet Compartments-ENA | Cubicle Curtains and Track-ENA | Operable Partitions-ENA | Wall and Door Protections-ENA | Toilet Accessories-ENA | Fire Protection Specialties-ENA | Metal Lockers-ENA | Prefabricated Entrance Canopies-ENA | Electric Vehicle Charging Station-ENA | Fall Arrest Systems-ENA | Residential Appliances-ENA | Foodservice Equipment - Brent ES | Kilns-ENA | Theater and Stage Equipment-ENA | Folding and Portable Stages-ENA | Athletic Equipment-ENA | Waste Compactors-ENA | Window Shades-ENA | Music Education Storage Casework-ENA | Residential Casework-ENA | Laboratory Casework-ENA | Entrance Floor Mats and Frames-ENA | Furniture-ENA | Telescoping Stands-ENA | Electric Traction Elevators-ENA | Mechanical Index | General Provisions - Mechanical | Scope of the Mechanical Work | Shop Drawings, Descriptive Literature, Maintenance Manuals, Parts Lists, Special Keys and Tools | Coordination Among Trades, Systems Interfacing and Connection of Equipment Furnished by Others | Commissioning of HVAC | Fire Protection System | PLUMBING | HVAC | ELECTRICAL | Telecom Rooms and Pathways | Conduit, Raceways and Boxes for Audiovisual Systems | Telephone and Data Systems | Projection Screens | Audiovisual and Sound Systems | Intercom and Clock | Integrated IP Based Safety & Intercommunications Systems & Clocks | Bi-Directional Amplifier Testing | Electronic Safety and Security | Access Control | Fire Alarm System | Building Intrusion Detection | Two Way Emergency Communications System | Site Clearing - Brent ES | Earth Moving - Brent ES | Dewatering - Brent ES | Asphalt Paving - Brent ES | Concrete Paving - Brent ES | Concrete Paving Joint Sealants - Brent ES | Common Works Results for Utilities - Brent ES | Storm Utility Drainage Piping - Brent ES
ESTIMATOR | CSI Division | BID PACKAGES |  | 014339 | 025100 | 033000 | 033543 | 035400 | 040514 | 042000 | 047200 | 050515 | 051200 | 052100 | 053100 | 055000 | 057305 | 061000 | 061600 | 062000 | 064000 | 071000 | 072100 | 072700 | 075400 | 076200 | 078100 | 078400 | 079200 | 081113 | 081416 | 083100 | 083300 | 083320 | 083514 | 084113 | 084115 | 086300 | 088000 | 089000 | 092900 | 093000 | 095100 | 095426 | 096466 | 096500 | 096566 | 096625 | 096800 | 097200 | 097700 | 098415 | 099000 | 101100 | 101400 | 102113 | 102123 | 102226 | 102600 | 102813 | 104400 | 105113 | 107323 | 111213 | 112430 | 113013 | 114000 | 115710 | 116100 | 116123 | 116600 | 118227 | 122400 | 123520 | 123530 | 123553 | 124813 | 125000 | 126600 | 142100 | 200000 | 200100 | 200200 | 200300 | 200500 | 200800 | 210100 | DIVISION 22 | DIVISION 23 | DIVISION 26 | 270500 | 270533 | 271000 | 274113 | 275000 | 275100 | 275123 | 275319 | 280000 | 281000 | 283100 | 283111 | 284800 | 311000 | 312000 | 312319 | 321216 | 321313 | 321373 | 330500 | 334100
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INT | # of Trades | Estimator
| KP | 0 | Korey Price (Lead)
| MM | 0 | Mada Makke
| GL | 0 | Geordie Liard
| MK | 0 | Scott Holsclaw
| SK | 0 | Safi Khan
| na | 0 | tbd
| na | 0 | tbd
| na | 0 | tbd
| NT | 0 | Nija Thomas
| JC | 0 | James Crowle
| OPS | 0 | Operations
Drawing Flip
| 0900-1000 | JC | Div 07, 08
| 1000-1100 | SH | Div 21, 22, 23, 26, 27, 28, 33: Dry Utility
| 1100-1200 | GL | Div 05, 10, 11, 12, 14
| 1300-1330 | SK | Div 09
| 1330-1500 | MM | Div 03, 31, 32, 33
| 1500-1600 | NT | Div 04, 06, DFHW
| 1600-1700 | OPS | GCs & GRs, Schedule
Surveying
Final Cleaning
Mock-Ups
Cast-in-Place Concrete
Polished Concrete
Cast Underlayment
Masonry and Cast Stone
Structural Steel
Misc Metals
Exterior Railings
Millwork & Finish Carpentry, incl running trim
Waterproofing
Roofing
Caulking
Air Barriers
Fireproofing
Doors, Frames & Hardware
Special Doors
Glass & Glazing
Fixed Aluminum Louvers
Drywall and Ceilings
Carpet / Resilient / LVT Flooring
Tile
Paint & Wall Covering
Wood Gymnasium Flooring
Terrazzo
Toilet Accessories & Compartments
Fire Extinguishers & Cabinets
Visual Display Surfaces
Cubicle Curtains
Operable Partitions
Signage
Wall and Door Protection
Lockers
Canopies
Equipment - Residential Appliances
Equipment - Window Washing
Equipment - Foodservice
Equipment - Lab (Kilns)
Equipment - Lighting & Stage
Equipment - Athletic
Equipment - Trash Compactor
Furnishings - Manufactured Casework
Furnishings - Window Treatment
Furnishings - Entrance Mats
Furnishings - FF&E
Conveying Equipment
Fire Protection
Plumbing
HVAC
Electrical and Fire Alarm
Low Voltage
Earthwork & Site Prep
Geopiers
Asphalt & Pavement Markings
Concrete Sitework & Unit Pavers
Landscaping & Site Furnishings
Utilities - Wet
Utilities - Dry

## Alternates
Client | DPR & DGS |  | Total GSF: | 20000 |  | Bid Date: | 2025-01-01
Project | Jelleff Recreation Center
Location | 3265 S St NW, Washington, DC 20007 |  |  |  |  | Revision: | V0
Architect | DLR Group |  | Weeks: | 78
Engineer | Various |  | Months: | 18
Back to Bid Sheet
|  |  | ALT 1: | ALT 2: | ALT 3: | ALT 4: | ALT 5: | ALT 6: | ALT 7: | ALT 8: | ALT 9: | ALT 10: | ALT 11: | ALT 12: | ALT 13: | ALT 14: | ALT 15: | ALT 16: | ALT 17: | ALT 18: | ALT 19: | ALT 20:
| Trade |  | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript | Descript
GENERAL REQUIREMENTS
01 - FINAL CLEANING
01 - SURVEY
02 - DEMOLITION
02 - ABATEMENT
03 - CONCRETE
03 - GYP UNDERLAYMENT
03 - PRECAST
04 - MASONRY
04 - STONE
05 - SS & MM
05 - MISC METALS
05 - EXTERIOR RAILINGS
06 - WOOD FRAMING
06 - FINISH CARPENTRY
06 - MILLWORK
07 - WP & AB
07 - EIFS/STUCCO
07 - AIR BARRIER
07 - FIREPROOFING
07 - EXTERIOR PANELS
07 - METAL PANELS
07 - ROOFING
07 - JOINT SEALANTS
08 - DOORS, FRAMES, HARDWARE
08 - SPECIAL DOORS
08 - GLASS & GLAZING
08 - ALUM & GLASS
08 - INT GLASS
09 - DRYWALL & CEILINGS
09 - TILE
09 - TERRAZZO
09 - CARPET, RESILIENT, RUBBER FLOORING
09 - PAINT & WALL COVERING
10 - TOILET ACCESSORIES
10 - TOILET PARTITIONS
10 - SIGNAGE
10 - SPECIALTIES (Visual Display Units, TA's FEC's, Lockers, op partitions,matts)
10 - LOCKERS
12 - FF&E
11 - Kitchen Equipment
11 - ATHELTIC EQUIPMENT
12 - RESIDENTIAL CABINETS
12 - COUNTERTOPS
12 - WINDOW TREATMENTS
14 - ELEVATORS
21 - FIRE PROTECTION
22 - PLUMBING
23 - HVAC
26 - ELECTRICAL
27 - LOW VOLTAGE
31 - SUPPORT OF EXCAVATION
31 - EARTHWORK & SITE DEMO&E,S
31 - DEEP FOUNDATIONS
31 - DEWATERING
32 - ASPHALT
32 - SEGMENTAL WALLS
32 - SITE CONCRETE
32 - PAVERS
32 - SITE FENCING
32 - SITE FURNISHINGS
32 - LANDSCAPING & SITE FURN
33 - WET UTILITIES
33 - DRY UTILITIES
33 - GEOTHERMAL
TEMPLATE
| Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | PERSONNEL GENERAL CONDITIONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | GENERAL CONDITIONS-NON PERSONNEL
linked -> | PUBLIC SPACE IMPROVEMENTS (BY OWNER)
linked -> | ESCALATION
linked -> | PERFORMANCE & PAYMENT BOND
linked -> | #ERROR!
linked -> | #ERROR!
linked -> | #ERROR!
linked -> | #ERROR!
| #ERROR! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #ERROR! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #ERROR! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | #ERROR! | #ERROR! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CONSTURCTION COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
linked -> | GC/CM Fee | 4125% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | ALT 1: | ALT 2: | ALT 3: | ALT 4: | ALT 5: | ALT 6: | ALT 7: | ALT 8: | ALT 9: | ALT 10: | ALT 11: | ALT 12: | ALT 13: | ALT 14: | ALT 15: | ALT 16: | ALT 17: | ALT 18: | ALT 19: | ALT 20:
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Survey
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 01 - SURVEY | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Surveying & Layout | Y |  |  |  |  | 0
3 | Vertical & Horizontal Controls | Y |  |  |  |  | 0
4 | Initial Set Up - Control Lines - Benchmarks - Property Corners | Y |  |  |  |  | 0
5 | Limits of Disturbance | Y |  |  |  |  | 0
6 | Erosion Control lines | Y |  |  |  |  | 0
7 | Utility Relocation: | Y |  |  |  |  | 0
8 | Storm Drain Relocation | Y |  |  |  |  | 0
9 | Sanitary Sewer Relocation | Y |  |  |  |  | 0
10 | Water Distribution Service Relocation | Y |  |  |  |  | 0
11 | Temp Roadway Work | Y |  |  |  |  | 0
12 | Temp Road | Y |  |  |  |  | 0
13 | Temp Parking Lot | Y |  |  |  |  | 0
14 | Sheeting & Shoring layout - for Soldier Piles and etc.. | Y |  |  |  |  | 0
15 | Mass Grading Excavation - Survey/Layout as follow in 50' x 50' Grid Cut | Y |  |  |  |  | 0
16 | Phase 1 Grading Excavation ……..., Bldg Excv……..., | Y |  |  |  |  | 0
17 | Phase 2 Grading Excavation ……..., Exterior Site Excav.- Hardscapes similar to sidwalks, Ret-Walls, plazas etc ……. | Y |  |  |  |  | 0
18 | New Utility Work: | Y |  |  |  |  | 0
19 | Storm Drain w/Structures | Y |  |  |  |  | 0
20 | Sanitary Sewer & Structures | Y |  |  |  |  | 0
21 | Water Main and Connection to ex. Water Line, Fire Hydrants, Meter Vault etc.…. | Y |  |  |  |  | 0
22 | Site Concrete Flat Work | Y |  |  |  |  | 0
23 | Conc Curb & Gutter, Head Curb, Landscaping Curb, Perimeter Flush Conc Curb at different Filelds.. | Y |  |  |  |  | 0
24 | Conc Trench Darins | Y |  |  |  |  | 0
25 | Onsite & Offsite Conc Sidewalks and new Pavers - Walkway work | Y |  |  |  |  | 0
26 | ADA Handicap Ramps | Y |  |  |  |  | 0
27 | Granite Curbs w/Brick Gutter & Conc Base & Aggregates at Streets | Y |  |  |  |  | 0
28 |  | Y |  |  |  |  | 0
29 | Survey & Layout for structures: | Y |  |  |  |  | 0
30 | Retaining walls | Y |  |  |  |  | 0
31 | Stairs (at several locations…..) | Y |  |  |  |  | 0
32 | Ramps | Y |  |  |  |  | 0
33 | Property Corners of: | Y |  |  |  |  | 0
34 | Bldgs | Y |  |  |  |  | 0
35 | Dry Utility survey - Electrical conduit & Light Poles | Y |  |  |  |  | 0
36 | Wall Check Foundations | Y |  |  |  |  | 0
37 | Control Lines on Slabs | Y |  |  |  |  | 0
38 | AS Built: | Y |  |  |  |  | 0
39 | Total job including …..Bldg, Utility Lines, Asphalt & Concrete Paved areas….etc. | Y |  |  |  |  | 0
40 |  | Y |  |  |  |  | 0
41 | Movement Monitoring Set Up | Y |  |  |  |  | 0
42 | Sheeting & Shoring layout & Stakeout for SOE Piles | Y |  |  |  |  | 0
43 | Sheeting Monitoring $_________/Week @ _____Weeks =======> | Y |  |  |  |  | 0
44 | Bldg Wall Check surveys | Y |  |  |  |  | 0
45 | Below Grade | Y |  |  |  |  | 0
46 | At Grade | Y |  |  |  |  | 0
47 | Façade | Y |  |  |  |  | 0
48 | AS Built - Total job including ….. | Y |  |  |  |  | 0
49 | As Built - Bldg Height | Y |  |  |  |  | 0
50 | Overall as built drawings including utilities, paved areas w/Asphalt & Concrete - Pavers | Y |  |  |  |  | 0
51 | Documentation | Y |  |  |  |  | 0
52 | Misc. Cost & Meeting | Y |  |  |  |  | 0
53 |  | Y |  |  |  |  | 0
54 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
55 |  | Y |  |  |  |  | 0
56 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Gyp
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 03 - GYP UNDERLAYMENT | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Provide gypsum underlayment at all living units including closets and utility rooms over wood subflooring | Y |  |  |  |  | 0
3 | Provide gypsum underlayment at utility/mechanical rooms, amenity areas and corridors over wood subflooring | Y |  |  |  |  | 0
4 | Complete all subfloor preparation necessary to receive gypsum underlayment | Y |  |  |  |  | 0
5 | Sub para 2.01.B: BOD: Maxxon; Gyp-Crete 2000/3.2k or USG Levelrock 2500 | Y |  |  |  |  | 0
6 | [MCN recommends min 2500 psi] | Y |  |  |  |  | 0
7 | Sub para 2.01.C: BOD: Maxxon; Acoustimat II or USG Levelrock SRM-25 | Y |  |  |  |  | 0
8 | Under all hard flooring surfaces over wood framing | Y |  |  |  |  | 0
9 | A702 - 1" FLOOR TOPPING MIXTURE | Y |  |  |  |  | 0
10 | A702 - 1/4" SOUND MAT | Y |  |  |  |  | 0
11 |  | Y |  |  |  |  | 0
12 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
13 | Include [#] mobilizations [use RSF/15,000] | Y |  |  |  |  | 0
14 | Include additional [# mobilizations OR additional mobilizations as directed by MCN] for prepour at tubs and dead spaces | Y |  |  |  |  | 0
15 | [MCN to provide approximate gypcrete schedule] | Y |  |  |  |  | 0
16 | Provide bond breaker at all walls to separate gypcrete from GWB to avoid capillary action of moisture into GWB | Y |  |  |  |  | 0
17 | Furnish sealer to be installed by FLOORING subcontractor | Y |  |  |  |  | 0
18 | Provide "stops" or flashings at open edges | Y |  |  |  |  | 0
19 | Tape and fill any holes in floors allowing material to run through to the next level of work | Y |  |  |  |  | 0
20 | Ensure that material is floated beneath the tub and tub / shower units thereby completing the rated floor assembly | Y |  |  |  |  | 0
21 | Provide all mat'ls, labor, equipment, tools, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
22 | Layout from GC control, benchmarks | Y |  |  |  |  | 0
23 | Protection and clean up of adjacent surfaces | Y |  |  |  |  | 0
24 | Clean up to MCN dumpster | Y |  |  |  |  | 0
25 | Shop drawings, submittals, product data, mix designs, test reports, certs, etc | Y |  |  |  |  | 0
26 | Mock-up [if specified] | Y |  |  |  |  | 0
27 | Testing [if specified] | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Precast
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 03 - PRECAST | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish and erect all precast as shown on drawings to include double tee precast floor system, inverted t beams, columns, beams, shearwalls, light walls, panels and stairs and landings. | Y |  |  |  |  | 0
3 | All precast concrete shall be designed in accordance with the drawings and specifications. Precast concrete shall be fabricated and erected to tolerances [as specified OR as in PCI's manual] | Y |  |  |  |  | 0
4 | Provide shop drawings, structural design, structural design calculations, material test data certified by a PE registered in the [Maryland, DC, Virginia] - Include connection details, column and wall base details, splice details, rebar etc. | Y |  |  |  |  | 0
5 | Provide [primed, zinc plated, hot dipped galvanized, SST] anchor bolts and steel plate embeds to be cast into foundations and walls by concrete subcontractor. | Y |  |  |  |  | 0
6 | Provide and install [primed, zinc plated, hot dipped galvanized, SST] anchors, dowels and accessories cast in to precast unit. | Y |  |  |  |  | 0
7 | Provide all necessary erection and connection hardware including steel shims, bearing pads and all welding. | Y |  |  |  |  | 0
8 | Install embeds provided by others for misc metals set in precast | Y |  |  |  |  | 0
9 | Provide and install dovetail slots at 24" oc at masonry walls | Y |  |  |  |  | 0
10 | Install all conduits in walls for the electrical trade lights and outlets as indicated on the electrical drawings furnished by the electrical contractor. | Y |  |  |  |  | 0
11 | Provide sleeves thru each double tee for other trades to run conduit, piping etc. | Y |  |  |  |  | 0
12 | Provide all grouting for your scope of work. | Y |  |  |  |  | 0
13 | Provide concrete washes and pour strips at deck perimeter, at shear walls, at and over girders, stair landings and elevator towers (including chord steel if applicable) | Y |  |  |  |  | 0
14 | Nosings at precast stairs | Y |  |  |  |  | 0
15 | Finish/color of interior precast components to be [strucutral gray concrete with cast finish OR other] | Y |  |  |  |  | 0
16 | Finish/color of exposed perimeter exterior precast components including spandresl, columns and walls to be [standard buff concrete OR other - with a light/moderate/heavy sandblast finish OR other] | Y |  |  |  |  | 0
17 | Apply sealer to precast units following sand blasting | Y |  |  |  |  | 0
18 | Provide and install temporary rails at all precast stairs | Y |  |  |  |  | 0
19 |  | Y |  |  |  |  | 0
20 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
21 | Provide all mat'ls, labor, equipment, tools, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
22 | Layout from GC control, benchmarks | Y |  |  |  |  | 0
23 | Clean up to MCN dumpster | Y |  |  |  |  | 0
24 | Leave precast in a clean condition - spot clean as needed | Y |  |  |  |  | 0
25 | Shop drawings, submittals, product data, mix designs, test reports, certs, etc | Y |  |  |  |  | 0
26 | Mock-up | Y |  |  |  |  | 0
27 |  | Y |  |  |  |  | 0
28 | LEED Issues: | Y |  |  |  |  | 0
29 | Fabrication of precast within 500-mile radius | Y |  |  |  |  | 0
30 | Fly ash/newcem content in concrete mix design | Y |  |  |  |  | 0
31 | 99% recycled content for reinforcing steel | Y |  |  |  |  | 0
32 | Sorting of debris for recycling | Y |  |  |  |  | 0
33 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Field poured concrete foundations, basement walls or strucutral concrete walls | N | by concrete
2 | Cast stone | N | by Masonry or Cast Stone
3 | Caulking of precast to precast joints | N | by Caulking
4 | Expansion joint covers/fillers | N | by Expansion Joint
5 | Fees for use of Tower Crane | N | added by GC
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Stone
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 04 - STONE | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish and install all stone types (granite, limestone, marble, etc) indicated to sizes, dimensions, profiles, lines and grades indicated: | Y |  |  |  |  | 0
3 | [ST-X: Type of stone]: Exterior stone paving (coordinate w/site concrete) | Y |  |  |  |  | 0
4 | [ST-X: Type of stone]: Exterior granite water table at base of building | Y |  |  |  |  | 0
5 | [ST-X: Type of stone]: Exterior stone façade cladding | Y |  |  |  |  | 0
6 | [ST-X: Type of stone]: Interior thickset stone flooring and base | Y |  |  |  |  | 0
7 | [ST-X: Type of stone]: Interior stone wall cladding | Y |  |  |  |  | 0
8 | [ST-X: Type of stone]: Granite vanities, aprons, fascias & backsplashes (coordinate with tile) | Y |  |  |  |  | 0
9 | [ST-X: Type of stone]: Furnish only stone that is "glazed-in" to curtainwall systems; include freight charges to glazier's shop | Y |  |  |  |  | 0
10 | [ST-X: Type of stone]: Furnish only stone that is cast into precast; include freight charges to precaster's shop | Y |  |  |  |  | 0
11 | Accessories to include metal strips in stone flooring | Y |  |  |  |  | 0
12 |  | Y |  |  |  |  | 0
13 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
14 | Finish as indicated | Y |  |  |  |  | 0
15 | Furnish & install all SS clips, anchors, dowels, pins, etc req'd to install stone to back-up; plaster spot veneer panels | Y |  |  |  |  | 0
16 | Sand and/or cement mortar setting beds for paving | Y |  |  |  |  | 0
17 | Grouting of stone joints | Y |  |  |  |  | 0
18 | Minor Surface prep as needed | Y |  |  |  |  | 0
19 | Field cutting of stone to fit site conditions, or field measurements prior to fab | Y |  |  |  |  | 0
20 | Provide cut-outs in stone for other trades such as light fixtures, elevator signals, security devices, fire department connections, sinks, soap dispensers, etc. | Y |  |  |  |  | 0
21 | Control joints spaced per spec | Y |  |  |  |  | 0
22 | Provide all tools, equip, scaffolding, swing stages, lifts, hoisting, etc for your work | Y |  |  |  |  | 0
23 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0
24 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
25 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
26 | Perform final wash down of stone to leave in clean condition | Y |  |  |  |  | 0
27 | Product data, samples, shop drawings, test reports, certs, etc | Y |  |  |  |  | 0
28 | Mock-ups | Y |  |  |  |  | 0
29 | Provide extra stock per specs for each stone type | Y |  |  |  |  | 0
30 |  | Y |  |  |  |  | 0
31 | LEED Issues: | Y |  |  |  |  | 0
32 | Stone quarried from within 500-mile radius | Y |  |  |  |  | 0
33 | 99% recycled content for attachment hardware | Y |  |  |  |  | 0
34 | Sorting of debris for recycling | Y |  |  |  |  | 0
35 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Mass demolition | N | by demo
2 | Granite curbs | N | by site concrete
3 | Concrete sub-base | N | by site concrete
4 | Plywood substrates; wood blocking | N | by carpentry
5 | Caulking | N | by caulk
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## MiscMetal
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 05 - MISC METALS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Include bent plate or screed angles at edges of metal deck | Y |  |  |  |  | 0
3 | Include all miscellaneous deck support angles | Y |  |  |  |  | 0
4 | Include miscellaneous closures/fillers at gaps in deck prior to concrete pour | Y |  |  |  |  | 0
5 | Elevator sill angles | Y |  |  |  |  | 0
6 | Elevator pit ladders | Y |  |  |  |  | 0
7 | Embedded corner guards in garage and loading dock | Y |  |  |  |  | 0
8 | Pipe guards | Y |  |  |  |  | 0
9 | Steel bollards | Y |  |  |  |  | 0
10 | Clip angle bracing at tops of CMU partitions | Y |  |  |  |  | 0
11 | Steel frames at Overhead doors | Y |  |  |  |  | 0
12 | Vanity support framing | Y |  |  |  |  | 0
13 | Spandrel frames and/or relieving angles at slab edges | Y |  |  |  |  | 0
14 | Loose lintels | Y |  |  |  |  | 0
15 | Stair nosings at concrete stairs | Y |  |  |  |  | 0
16 | Roof ladders | Y |  |  |  |  | 0
17 | Trench grate covers and embedded frames | Y |  |  |  |  | 0
18 | Elevator sump pit grating and embedded frames | Y |  |  |  |  | 0
19 |  | Y |  |  |  |  | 0
20 | Metal pan stairs | Y |  |  |  |  | 0
21 | Checkered metal plate stairs | Y |  |  |  |  | 0
22 | Include all support steel, hangers, anchors etc for complete assemblies | Y |  |  |  |  | 0
23 | Balustrades and handrails at Egress Stairs | Y |  |  |  |  | 0
24 | Include security gates | Y |  |  |  |  | 0
25 | Balustrades and handrails at miscellaneous stairs and ramps | Y |  |  |  |  | 0
26 |  | Y |  |  |  |  | 0
27 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
28 | Include PE calcs & design for connections | Y |  |  |  |  | 0
29 | Provide calcs/PE stamp for stair and railing designs; meet performance req'mts | Y |  |  |  |  | 0
30 | Provide all material, tools, equipment, hoisting, supervision req'd for your work | Y |  |  |  |  | 0
31 | Shop fab holes in steel for connections & for penetrations shown for other trades | Y |  |  |  |  | 0
32 | Bare steel if fireproofed and at connection points; galvanized if exposed to weather, in cavity wall or embedded, shop prime balance of steel | Y |  |  |  |  | 0
33 | Perform all welded and bolted connections; moment connections | Y |  |  |  |  | 0
34 | Grinding of welds & touch up finishes after connections are made | Y |  |  |  |  | 0
35 | Provide temporary bracing, guys during erection as needed | Y |  |  |  |  | 0
36 | Furnish & deliver all embeds to include anchor bolts, weld plates/angles, etc | Y |  |  |  |  | 0
37 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
38 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
39 | Shop dwgs, samples, product data, certs, test reports, etc | Y |  |  |  |  | 0
40 | Perform all welded & bolted connections | Y |  |  |  |  | 0
41 | Provide all fasteners and misc steel for complete assemblies | Y |  |  |  |  | 0
42 | Furnish all embedded items relating to your work (weld plates/angles, anchor bolts, sleeves, etc) | Y |  |  |  |  | 0
43 | Grout railing posts into sleeves, or core drill if sleeves are not furnished | Y |  |  |  |  | 0
44 | Perform field measurements, or modify in field as needed | Y |  |  |  |  | 0
45 | Galvanize if exposed to weather, in wall cavity or embedded; shop prime balance | Y |  |  |  |  | 0
46 | Touch up finishes where damaged by welding, handling | Y |  |  |  |  | 0
47 |  | Y |  |  |  |  | 0
48 | LEED Issues: | Y |  |  |  |  | 0
49 | Use of materials from within 500-mile radius | Y |  |  |  |  | 0
50 | 99% recycled content for reinforcement | Y |  |  |  |  | 0
51 | Sorting of debris for recycling | Y |  |  |  |  | 0
52 | EGC documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Testing and Inspection | No | by Owner
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Rails
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 05 - EXTERIOR RAILINGS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Aluminum balcony railings | Y |  |  |  |  | 0
3 | Scope the specified railing post + rail materials | Y |  |  |  |  | 0
4 | Some railing subcontractors specialize in aluminum railings only (Atlantic Aluminum, Carfaro, RGS), and do not provide steel and/or stainless steel - Hercules Custom Iron is a good choice for all railings of all materials | Y |  |  |  |  | 0
5 | If the railings are steel and/or stainless steel the misc metal and/or ornamental subctonractors are more likely to pick up the railings, although you will have to point them in that direction | Y |  |  |  |  | 0
6 | [List the IBC Code that governs the project - significant changes were made in the 2009 + 2012 Codes] | Y |  |  |  |  | 0
7 | Scope the size + spacing of the posts (check drawings + specs for conflicts) | Y |  |  |  |  | 0
8 | Scope the number of hoirzontal rails (2-line, 3-line, etc) - check drawings + specs for conflicts | Y |  |  |  |  | 0
9 | Scope the profile of the top rail - this is often proprietary | Y |  |  |  |  | 0
10 | Scope the infill between horizontal rails (vertical pickets, mesh infill, etc) | Y |  |  |  |  | 0
11 | Scope the type of post mounting to the structure | Y |  |  |  |  | 0
12 | Typical railing manufacturer's will want to mount their posts to the top of slab | Y |  |  |  |  | 0
13 | Cantilevered post mountings (to the outside face of slab) can add significant costs as the installers will now have to have access to the outside of the building from lifts and/or swingstages | Y |  |  |  |  | 0
14 | Scope the spedified finish | Y |  |  |  |  | 0
15 | AAMA 2605 finishes are NOT appropriate for aluminum railings as these finishes are soft and easily scratched - AAMA 2603 + AAMA 2604 are both apprpriate aluminum railing finishes | Y |  |  |  |  | 0
16 | Investigate how the ends of the railings are to be anchored | Y |  |  |  |  | 0
17 | If the ends are posts attached to the slab then the railing sub will be the only sub invovled | Y |  |  |  |  | 0
18 | If the railing ends are attached to the wall then blocking will need to be added into the wall (scope blocking with Framer or Drywall depending upon wall construction) and an appropriate detail through the exterior finish provided by the Architect | Y |  |  |  |  | 0
19 |  | Y |  |  |  |  | 0
20 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
21 | Provide all material, tools, equipment, hoisting, supervision req'd for your work | Y |  |  |  |  | 0
22 | Perform all welded & bolted connections | Y |  |  |  |  | 0
23 | Provide all fasteners and misc steel for complete assemblies | Y |  |  |  |  | 0
24 | Provide calcs/PE stamp for stair and railing designs; meet performance req'mts | Y |  |  |  |  | 0
25 | Furnish all embedded items relating to your work (weld plates/angles, anchor bolts, sleeves, etc) | Y |  |  |  |  | 0
26 | Grout railing posts into sleeves, or core drill if sleeves are not furnished | Y |  |  |  |  | 0
27 | Perform field measurements, or modify in field as needed | Y |  |  |  |  | 0
28 | Provide finishes as indicated | Y |  |  |  |  | 0
29 | Shop dwgs, submittals, product data, test reports, certs, etc | Y |  |  |  |  | 0
30 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
31 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
32 |  | Y |  |  |  |  | 0
33 | LEED Issues: | Y |  |  |  |  | 0
34 | Fabrication within 500-mile radius | Y |  |  |  |  | 0
35 | High recycled content for steel | Y |  |  |  |  | 0
36 | Sorting of debris for recycling | Y |  |  |  |  | 0
37 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Miscellaneous metals items | N | by metals
2 | Metal strips in stone/terrazzo flooring | N | by stone
3 | Ornamental metal trim in millwork paneling; reception desk | N | by millwork
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## FbrGls
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Pillar |  |  | Edon Corp |  |  | Stromberg Architectural |  |  | Denoto Precast |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 06 - FIBER REINFORCED PLASTICS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Fiberglass | Y |  |  |  |  | 0
3 | Furnish and deliver (FOB jobsite) all fiberglass façade elements | Y |  |  |  |  | 0
4 | Fabricate with molds to the sizes, dimensions, profiles indicated | Y |  |  |  |  | 0
5 | Color and finish per spec | Y |  |  |  |  | 0
6 | Include back-up framing/internal reinforment designed & engineered to withstand loads and allow a "panelized" installation to building framing | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Shop dwgs, samples, product data, certs, test reports, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Wood blocking and plywood | N | by Carpentry
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Provide an add price to erect fiberglass (include unloading, equipment, hoisting, supervision, clean up, etc) | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## DeepFnd
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 31 - DEEP FOUNDATIONS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Scope | Y |  |  |  |  | 0
3 | Scope | Y |  |  |  |  | 0
4 | Scope | Y |  |  |  |  | 0
5 | Scope | Y |  |  |  |  | 0
6 | Scope | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## DeWater
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 31 - DEWATERING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Dewatering | Y |  |  |  |  | 0
3 | Design and engineer dewatering system to maintain ground water level a min. of 4' below the deepest footing or elevator pit to permit dry, stable subgrades | Y |  |  |  |  | 0
4 | Include augered deep wells, well points or vacuum wells with sumersible pumps, electric cables, PVC pipe, slotted screen, pea gravel, control boxes with audible alarm and all above ground well head fittings | Y |  |  |  |  | 0
5 | Include discharge pipes from wells to the centralized discharge location | Y |  |  |  |  | 0
6 | Include on grade weatherproof cables from wells strapped to discharge pipes | Y |  |  |  |  | 0
7 | If wells are inside the excavation, coordinate with excavation to lower the wellheads, discharge pipes and electric cables at each completed level | Y |  |  |  |  | 0
8 | Include loader service for gravel installation and drilling operation | Y |  |  |  |  | 0
9 | Include accessories such as bentonite plug for vacuum wells, throttle valve and check valve at effluent line | Y |  |  |  |  | 0
10 | Layout and furnish piezometers and flow measuring devices to monitor performance; provide one hand-held piezometer and a graduated cord with a min. length equal to the deepest well plus 20% | Y |  |  |  |  | 0
11 | Include delivery and installation of all equipment; including applicable taxes | Y |  |  |  |  | 0
12 | Include additional pumps and parts as stand-by equipment | Y |  |  |  |  | 0
13 | Installation and pumping one month prior to start of excavation | Y |  |  |  |  | 0
14 | Iron bacteria treatment as required | Y |  |  |  |  | 0
15 | Include all air filter media required for duration of dewatering operation | Y |  |  |  |  | 0
16 | Testing of wells | Y |  |  |  |  | 0
17 | Include rental charges until concrete is to grade | Y |  |  |  |  | 0
18 | Set up daily pumping report log and submit initial report for long-term pumping | Y |  |  |  |  | 0
19 | Periodically review the log maintained by MCN personnel | Y |  |  |  |  | 0
20 | Remobilize to remove equipment from jobsite | Y |  |  |  |  | 0
21 | Backfill of wells | Y |  |  |  |  | 0
22 | Advise of duration to provide a complete dewatering system | Y |  |  |  |  | 0
23 | Advise of rental period included in bid | Y |  |  |  |  | 0
24 | Advise of estimate for total discharge volume based on soil report | Y |  |  |  |  | 0
25 |  | Y |  |  |  |  | 0
26 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
27 |  | Y |  |  |  |  | 0
28 |  | Y |  |  |  |  | 0
29 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | Electrical distribution panel, connection and disconnection | N
2 | Field Engineering, surveying and cut sheets | N
3 | Spoil removal from drilling operation | N
4 | Water disposal fees | N
5 | Contaminated water treatment | N
6 | Protective measures for wells and pipe | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SegWall
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 32 - SEGMENTAL WALLS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish & install all segmented retaining wall to sizes, shapes, lines & grades indicated: | Y |  |  |  |  | 0
3 | ****site walls A | Y |  |  |  |  | 0
4 | ****site walls B | Y |  |  |  |  | 0
5 | Include all special shapes and bond patterns as shown | Y |  |  |  |  | 0
6 | Excavation from SOG subgrade for all wall footings | Y |  |  |  |  | 0
7 | Bench excavations per OSHA requirements | Y |  |  |  |  | 0
8 | Backfill and compaction to SOG subgrade after pour | Y |  |  |  |  | 0
9 | Furnish and install all reinforcing bars (cut to length, bent) | Y |  |  |  |  | 0
10 | Furnish and install all thru-wall membrane flashing w/end dams & mortar net | Y |  |  |  |  | 0
11 | Include weep holes as shown | Y |  |  |  |  | 0
12 |  | Y |  |  |  |  | 0
13 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
14 | Excavation, backfill and compaction as required for your work | Y |  |  |  |  | 0
15 | Field cutting of stone to fit site conditions, or field measurements prior to fab | Y |  |  |  |  | 0
16 | Control joints spaced per spec | Y |  |  |  |  | 0
17 | Provide all tools, equip, hoisting, etc for your work | Y |  |  |  |  | 0
18 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0
19 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
20 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
21 | Perform final wash down of stone to leave in clean condition | Y |  |  |  |  | 0
22 | Product data, samples, shop drawings, test reports, certs, etc | Y |  |  |  |  | 0
23 | Provide all structural components | Y |  |  |  |  | 0
24 | Leveling pads | Y |  |  |  |  | 0
25 | Geogrid | Y |  |  |  |  | 0
26 | Drain-tile, incl drain tile piping | Y |  |  |  |  | 0
27 | Mock-ups | Y |  |  |  |  | 0
28 | Maintain and protect all survey and layout points provided by others. | Y |  |  |  |  | 0
29 | All necessary materials, accessories, components, sleeves, etc. | Y |  |  |  |  | 0
30 | All necessary close out documentation, incl but not limited to red-lined, as-built drawings and warranties. | Y |  |  |  |  | 0
0
C | Exclusions
1 | Concrete retaining walls | N
2 | Offsite fill | N
3 | Removal of unsuitable soils off site. | N
4 | Benchmarks and off sets | N
5 | Fence installation and modular retaining walls | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Pavers
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 32 - PAVERS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Furnish and install all paver types (granite, precast concrete, brick, etc) indicated to sizes, dimensions, profiles, lines and grades indicated: | Y |  |  |  |  | 0
3 | [PAV-X: Type of stone]: Exterior stone paving (coordinate w/site concrete) | Y |  |  |  |  | 0
4 | [PAV-X: Type of stone]: Exterior stone paving (coordinate w/site concrete) | Y |  |  |  |  | 0
5 | [PAV-X: Type of stone]: Exterior stone paving (coordinate w/site concrete) | Y |  |  |  |  | 0
6 | Accessories to include metal strips in UNIT PAVERS | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Finish as indicated | Y |  |  |  |  | 0
10 | Sand and/or cement mortar setting beds for paving | Y |  |  |  |  | 0
11 | Grouting of stone joints | Y |  |  |  |  | 0
12 | Field cutting of stone to fit site conditions, or field measurements prior to fab | Y |  |  |  |  | 0
13 | Control joints spaced per spec | Y |  |  |  |  | 0
14 | Provide all tools, equip, hoisting, etc for your work | Y |  |  |  |  | 0
15 | Protect work of other trades from damage by your operations | Y |  |  |  |  | 0
16 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
17 | Clean up debris and dispose in MCN dumpster | Y |  |  |  |  | 0
18 | Perform final wash down of stone to leave in clean condition | Y |  |  |  |  | 0
19 | Product data, samples, shop drawings, test reports, certs, etc | Y |  |  |  |  | 0
20 | Mock-ups | Y |  |  |  |  | 0
21 | Provide extra stock per specs for each stone type | Y |  |  |  |  | 0
22 |  | Y |  |  |  |  | 0
23 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 | F&I concrete sub base for granite/unit pavers (By Site Concrete) | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SiteFurn
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 32 - SITE FURNISHINGS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Site Furnishing Scope | Y |  |  |  |  | 0
3 | Bike Racks (Inverted U Bike Racks by Fuction First Inc.) per dwg L-__ at Street Level,/Courtyard and detail 6_/L-__ …….QTY______EA | Y |  |  |  |  | 0
4 | Benches (6' / 8' Bench by ______) at Street / courtyard per dwgs L-_ and detail _/L__ …….QTY______EA (Concrete Footing by Conc Site Work Contractor) | Y |  |  |  |  | 0
5 | Fiber Glass - Precast Planters. F&I Glass Fiber and /or Reinforced Conc Planters by ___" Sizes __" SQ. __"DIA. and _' X _' as shown on L-__and detail _/L-__. Work also includes ….. | Y |  |  |  |  | 0
6 | Tree Grate w/Frame Work per _/L-__and details _/L-__. Work includes F & I Metal Grate & Frame by …. | Y |  |  |  |  | 0
7 | 36"Gallon Litter Receptacles per dwg note __/L-__ and detail __/L-__. Includes F&I Victor Stanley type Ironside S-42 Trash Receptacles | Y |  |  |  |  | 0
8 | Metal Edging as required per detail _/L___ | Y |  |  |  |  | 0
9 | Supply two extra ___trash receptacles (Specs Sect __/12 ____) | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
11 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
12 | Include all mat'l, tools, equipment, hoisting/rigging, supervision, etc for this work | Y |  |  |  |  | 0
13 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
14 | Clean up to MCN dumpster | Y |  |  |  |  | 0
15 | Shop dwgs, samples, product data, certs, test reports, manuals, etc | Y |  |  |  |  | 0
16 | Warranties per spec | Y |  |  |  |  | 0
17 |  | Y |  |  |  |  | 0
18 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Abatement
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 02 - ABATEMENT | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Scope | Y |  |  |  |  | 0
3 | Scope | Y |  |  |  |  | 0
4 | Scope | Y |  |  |  |  | 0
5 | Scope | Y |  |  |  |  | 0
6 | Scope | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## ResCab
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 12 - RESIDENTIAL CABINETS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Residential Casework | Y |  |  |  |  | 0
3 | Furnish and deliver (FOB jobsite) residential cabinetry for all units: | Y |  |  |  |  | 0
4 | Include unloading and uncrating to units; clean up to MCN dumpster | Y |  |  |  |  | 0
5 | Kitchen base cabinets | Y |  |  |  |  | 0
6 | ***[36" or 42"] kitchen wall cabinets*** | Y |  |  |  |  | 0
7 | Bathroom base cabinets | Y |  |  |  |  | 0
8 | ***Other cabinetry*** (wet bars, pantries, medicine cabinets) | Y |  |  |  |  | 0
9 | ***[Custom or standard (3")] cabinet modules | Y |  |  |  |  | 0
10 | ***[Framed or frameless] cabinets*** | Y |  |  |  |  | 0
11 | ***[Full overlay, partial overlay or inset] cabinets & drawer fronts as specified*** | Y |  |  |  |  | 0
12 | ***[Self closing or soft closing] drawer guides if specified*** | Y |  |  |  |  | 0
13 | ***Self closing hinges if specified*** | Y |  |  |  |  | 0
14 | Allow for phased delivery to jobsite by floor | Y |  |  |  |  | 0
15 |  | Y |  |  |  |  | 0
16 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
17 | Use of specified manufacturers and materials | Y |  |  |  |  | 0
18 | Provide cut-outs/grommets for plumbing/electrical req'ments as needed | Y |  |  |  |  | 0
19 | Include all cabinetry hardware and misc items including glazed panels, keyed locks, pulls, concealed hinges, catches, shelving, etc | Y |  |  |  |  | 0
20 | Include all anchors and fasteners for this work | Y |  |  |  |  | 0
21 | Obtain field measurements prior to fabrication | Y |  |  |  |  | 0
22 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0
23 |  | Y |  |  |  |  | 0
24 | LEED Issues: | Y |  |  |  |  | 0
25 | FSC-certified lumber and veneers | Y |  |  |  |  | 0
26 | Plywood/substrates free of urea formaldehyde | Y |  |  |  |  | 0
27 | Use of low VOC adhesives, sealants and finishes | Y |  |  |  |  | 0
28 | Sorting of debris for recycling | Y |  |  |  |  | 0
29 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Furnishing of stone countertops (provide an add price if quoting) | N | by countertops
2 | In-wall blocking | N | by carpentry/drywall
3 | Protection of finished work | N | by MCN
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 | Provide an add price to install all cabinetry | # |  |  |  |  | 0
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Counter
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 12 - COUNTERTOPS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Residential Countertops | Y |  |  |  |  | 0
3 | [2cm or 3cm] countertops at Unit kitchens at non-MPDU Units [granite, quartz, corian, other] | Y |  |  |  |  | 0
4 | **2cm countertops may require plywood substrate ** | Y |  |  |  |  | 0
5 | **List scheduled material & color** | Y |  |  |  |  | 0
6 | [2cm or 3 cm] countertops at Unit bathroom vanities at non-MPDU Units [granite, quartz, corian, other] | Y |  |  |  |  | 0
7 | **List scheduled material & color** | Y |  |  |  |  | 0
8 | Countertops at MPDU units [granite, quartz, plam, cultured marble, other] | Y |  |  |  |  | 0
9 | **If plam the countertops will be provided by CABINETS** | Y |  |  |  |  | 0
10 | **List scheduled material & color** | Y |  |  |  |  | 0
11 | Furnish sinks at countertops - provide manuf, model and size - Provide BREAKOUT COST | Y |  |  |  |  | 0
12 | Install sinks at countertops - Provide BREAKOUT COST | Y |  |  |  |  | 0
13 | Provide premium (if applicable) to Install sinks if not provided by this contract | Y |  |  |  |  | 0
14 |  | Y |  |  |  |  | 0
15 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
16 | Shop dwgs, samples, product data, certs, test reports, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Wood blocking and plywood | N | by carpentry
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## WT
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 12 - WINDOW TREATMENTS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Horizontal Louver Blinds | Y |  |  |  |  | 0
3 | Furnish and install [describe] HORIZONTAL blinds at all window and pation doors of residential units. | Y |  |  |  |  | 0
4 | Furnish and install [describe] VERTICAL blinds at all sliding doors of residential units. | Y |  |  |  |  | 0
5 | Attach head channel to [window mullion/blind pocket] | Y |  |  |  |  | 0
6 | Do not provide blinds at windows facing [Main Lobby, Retail space] | Y |  |  |  |  | 0
7 | Accessories to include lift cord, tilting rod, mounting brackets, anchors, etc. | Y |  |  |  |  | 0
8 | Include extra stock | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
11 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
12 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
13 | Clean up to MCN dumpster | Y |  |  |  |  | 0
14 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Aluminum blind pocket extrusions | N | by glass/glazing
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SOE
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 31 - SUPPORT OF EXCAVATION | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | [Full height, on-line or Partial height, off-line] sheeting & shoring at perimeter of basement foundation walls | Y |  |  |  |  | 0
3 | Design and engineering of system to meet 20H, 25H or 30H loading | Y |  |  |  |  | 0
4 | Include all driven soldier piles to a min. depth of 10' below bottom of footing | Y |  |  |  |  | 0
5 | Include all lagging to slab subgrade | Y |  |  |  |  | 0
6 | Hand excavate from soldier pile flange to install lagging | Y |  |  |  |  | 0
7 | Include tie-back operation; drilling, grouting and stressing | Y |  |  |  |  | 0
8 | Assume 40' bench provided by excavator for tie back installation at each level | Y |  |  |  |  | 0
9 | Include all internal rakers, corner & crosslot bracing necessary | Y |  |  |  |  | 0
10 | Include heel blocks necessary for rakers; excavation by others (provide Spoil Conc Heel Footing Qty_______CY | Y |  |  |  |  | 0
11 | Remobilize after foundation walls are poured to remove all tie-back anchors and bracings; cut off all tie backs not cast into the wall | Y |  |  |  |  | 0
12 | Remobilize and remove top 4' of soldier beams & lagging; excavation by other | Y |  |  |  |  | 0
13 | Provide [underpinning/bracket piling) of adjacent buildings [identify locations | Y |  |  |  |  | 0
14 | Include hand excavated underpinning pits and lagging Provide Qty CY of Spoils | Y |  |  |  |  | 0
15 | Include grouting of underpinning to existing foundation | Y |  |  |  |  | 0
16 | Include regular monitoring of all vertical and lateral movements of sheeting; submit records for review | Y |  |  |  |  | 0
17 | Include perimeter safety rail of angle iron and cable with top lagging board raised to serve as a toe board | Y |  |  |  |  | 0
18 |  | Y |  |  |  |  | 0
19 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
20 | Advise of underpinning/tie back spoil quantity to be disposed of by others | Y |  |  |  |  | 0
21 | Advise of number of concrete wall & floor penetrations to be infilled due to rakers | Y |  |  |  |  | 0
22 | Acknowledge Geo-tech report dated [XX/XX/XX]; incorporate data into pricing | Y |  |  |  |  | 0
23 | Sheeting and Shoring Permit drawings with design engineering/calcs by PE | Y |  |  |  |  | 0
24 | On-line sheeting pile location tolerance of 0" to -3" from outside face of wall. | Y |  |  |  |  | 0
25 | If soldier beam encroaches on wall, sheeting contractor shall block back lagging to allowa full wall thickness between soldier piles at no additional cost | Y |  |  |  |  | 0
26 | Allow for thickness of waterproofing drainage material | Y |  |  |  |  | 0
27 | Ensure no excessive gaps between lagging or abnormal transitions between pile flange and lagging that might void the waterproofing warranty | Y |  |  |  |  | 0
28 | Coordinate with excavator for ramp installation, relocation and remov | Y |  |  |  |  | 0
29 | Include test pits as necessary for your work | Y |  |  |  |  | 0
30 | Include performance tests on tie-backs as specified | Y |  |  |  |  | 0
31 | Verify that adjacent existing structures and utilities are not in conflict with proposed sheeting/tie-back | Y |  |  |  |  | 0
32 | Notify MCN of any surveying or utility work required before sheeting operation | Y |  |  |  |  | 0
33 | Provide all equipment, material, labor, tools, supervision, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Field engineering, surveying and cut sheet | N | By surveying
2 | Spoil removal from underpinning and tie-back drillin | N | By earthwork
3 | Sheeting/Shoring Monitoring | N | By Surveying
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Terrazzo
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 09 - TERRAZZO | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Terrazzo | Y |  |  |  |  | 0
3 | Furnish and install portland cement terrazzo flooring shown on the plans and Finish Schedule | Y |  |  |  |  | 0
4 | Mix to include stone chips and coloring additives as specified | Y |  |  |  |  | 0
5 | Include sand setting bed, isolation membrane and concrete underbed with wire mesh reinforcing | Y |  |  |  |  | 0
6 | Include zinc divider strips anchored to underbed & set to the finish floor elevation | Y |  |  |  |  | 0
7 | Include all troweling, rolling and finishing of terrazzo (including add'l chips) | Y |  |  |  |  | 0
8 | Include curing compound | Y |  |  |  |  | 0
9 | Include floor sealer | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
11 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
12 | Include all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
13 | Include minor surface prep | Y |  |  |  |  | 0
14 | Clean terrazzo after installation | Y |  |  |  |  | 0
15 | Include Kraft paper floor protection after installation | Y |  |  |  |  | 0
16 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
17 | Clean up to MCN dumpster | Y |  |  |  |  | 0
18 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0
19 | Mock-up per spec | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## TA
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 10 - TOILET ACCESSORIES | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Toilet Accessories | Y |  |  |  |  | 0
3 | Furnish and Install the following toilet accessories: | Y |  |  |  |  | 0
4 | RESIDENTIAL TOILET ACCESSORIES | Y |  |  |  |  | 0
5 | Toilet tissue dispensers [verify quantities] | Y |  |  |  |  | 0
6 | Combination towel dispenser/waste receptacles [verify quantities] | Y |  |  |  |  | 0
7 | 36" Grab Bars [verify quantities] | Y |  |  |  |  | 0
8 | 42" Grab Bars [verify quantities] | Y |  |  |  |  | 0
9 | Sanitary napkin dispensers [verify quantities] | Y |  |  |  |  | 0
10 | Sanitary napkin disposal units [verify quantities] | Y |  |  |  |  | 0
11 | Utility shelf [verify quantities] | Y |  |  |  |  | 0
12 | Stainless steel-framed mirrors [verify quantities] | Y |  |  |  |  | 0
13 | Soap dispensers [verify quantities] | Y |  |  |  |  | 0
14 | Seat cover dispensers [verify quantities] | Y |  |  |  |  | 0
15 | Robe hooks [verify quantities] | Y |  |  |  |  | 0
16 | Mop and broom holder with shelf [verify quantities] | Y |  |  |  |  | 0
17 | Shower curtain and rod [verify quantities] | Y |  |  |  |  | 0
18 | Soap dish [verify quantities] | Y |  |  |  |  | 0
19 | Shower Rod [verify quantities] | Y |  |  |  |  | 0
20 | Towel bar [verify quantities] | Y |  |  |  |  | 0
21 | ***Other toilet accessories*** | Y |  |  |  |  | 0
22 | ***Other toilet accessories*** | Y |  |  |  |  | 0
23 | PUBLIC TOILET ROOM ACCESSORIES | Y |  |  |  |  | 0
24 | Toilet tissue dispensers [verify quantities] | Y |  |  |  |  | 0
25 | Combination towel dispenser/waste receptacles [verify quantities] | Y |  |  |  |  | 0
26 | Paper towel dispensers [verify quantities] | Y |  |  |  |  | 0
27 | 36" Grab Bars [verify quantities] | Y |  |  |  |  | 0
28 | 42" Grab Bars [verify quantities] | Y |  |  |  |  | 0
29 | Sanitary napkin dispensers [verify quantities] | Y |  |  |  |  | 0
30 | Sanitary napkin disposal units [verify quantities] | Y |  |  |  |  | 0
31 | Utility shelf [verify quantities] | Y |  |  |  |  | 0
32 | Stainless steel-framed mirrors [verify quantities] | Y |  |  |  |  | 0
33 | Soap dispensers [verify quantities] | Y |  |  |  |  | 0
34 | Seat cover dispensers [verify quantities] | Y |  |  |  |  | 0
35 | Robe hooks [verify quantities] | Y |  |  |  |  | 0
36 | Mop and broom holder with shelf [verify quantities] | Y |  |  |  |  | 0
37 | Shower curtain and rod [verify quantities] | Y |  |  |  |  | 0
38 | ***Other toilet accessories*** | Y |  |  |  |  | 0
39 | ***Other toilet accessories*** | Y |  |  |  |  | 0
40 | Include all mounting anchors, fasteners, keys, etc | Y |  |  |  |  | 0
41 |  | Y |  |  |  |  | 0
42 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
43 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
44 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
45 | Clean up to MCN dumpster | Y |  |  |  |  | 0
46 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## TPart
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 10 - TOILET PARTITIONS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Toilet Partitions | Y |  |  |  |  | 0
3 | Furnish and Install all [ceiling/floor]-mounted, [steel/stainless steel/phenolic] toilet partitions and wall-mounted urinal screens | Y |  |  |  |  | 0
4 | ***List specific locations*** | Y |  |  |  |  | 0
5 | Include all brackets, fittings, trim pieces, door hardware, coat hooks, mounting hardware, fasteners, etc | Y |  |  |  |  | 0
6 | Color and finish as specified | Y |  |  |  |  | 0
7 | Perform necessary adjustments | Y |  |  |  |  | 0
8 |  | Y |  |  |  |  | 0
9 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
10 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
11 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
12 | Clean up to MCN dumpster | Y |  |  |  |  | 0
13 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Overhead support bracing and/or structure | N | by misc metals
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Lockers
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 10 - LOCKERS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Lockers | Y |  |  |  |  | 0
3 | Furnish & install [qty, x-tier, size, baked enamel steel] lockers as indicated in Locker Rooms | Y |  |  |  |  | 0
4 | Include louvered vents, hinges, door handles/latches, ID plates, hooks, coat rods, shelves, sloping tops, trim, filler panels, anchors, fasteners and other related accessories | Y |  |  |  |  | 0
5 | Furnish & install [laminated maple] locker benches on steel pedestals | Y |  |  |  |  | 0
6 | Include clear sealer finish with lacquer coat on top surface | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Include all mat'l, labor, tools, equipment, hoisting, supervision, etc for your work | Y |  |  |  |  | 0
10 | Assume free use of GC's material hoist | Y |  |  |  |  | 0
11 | Clean up to MCN dumpster | Y |  |  |  |  | 0
12 | Shop dwgs, samples, product data, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## WoodFram
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 06 - WOOD FRAMING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | All items are Furnished and Installed Unless Noted Otherwise | Y |  |  |  |  | 0
3 | Wood framing as required for a complete and structurally sound building (including roof, exterior wall, and floor sheathing) | Y |  |  |  |  | 0
4 | PROVIDE BREAKOUT PRICING TO FURNISH ALL LOOSE LUMBER MATERIAL ONLY | Y |  |  |  |  | 0
5 | Floor, corridor and roof trusses | Y |  |  |  |  | 0
6 | Shear panels, shear blocking, and shear trusses as indicated | Y |  |  |  |  | 0
7 | Draftstopping - [detail material and where to provide] | Y |  |  |  |  | 0
8 | Install all access doors in draftstopping (Furnished by others) | Y |  |  |  |  | 0
9 | Fasteners & hardware (except hardware cast in concrete) | Y |  |  |  |  | 0
10 | All metal connectors & fasteners in contact with pressure treated wood shall be hot-dipped galvanized | Y |  |  |  |  | 0
11 | Furnish and install all flashings and sill pans intetgral with framing [provide detail reference or description of location] | Y |  |  |  |  | 0
12 | Furnish and install sill sealer beneath the bottom plate on all perimeter walls | Y |  |  |  |  | 0
13 | Install all steel beams, steel columns, and microlam beams | Y |  |  |  |  | 0
14 | Housewrap (Tyvek) on exterior walls to be installed per manufacturer’s instructions. If wind pulls wrap off, the framer is to re-install at his expense for both labor and materials to wrap windows per manufacturer and field manager’s instructions as to be water tight. No wood shall be exposed | Y |  |  |  |  | 0
15 | Furnish and install self-adhered membrane flashing at window & door perimeters | Y |  |  |  |  | 0
16 | Install all windows (Furnished by others) | Y |  |  |  |  | 0
17 | - Furnish and install sill flashing for windows | Y |  |  |  |  | 0
18 | Install all exterior doors/frames including sliders (Furnished by others) | Y |  |  |  |  | 0
19 | Install brick ties (furnished by others)(Screws provided by the carpenter) | Y |  |  |  |  | 0
20 | Furnish and install all caulking for your installations | Y |  |  |  |  | 0
21 | All blocking, bracing, and bridging at roof offsets and for nailing siding and step flashing | Y |  |  |  |  | 0
22 | All blocking / framing for all trey ceilings, vaulted ceilings, and cathedral ceilings | Y |  |  |  |  | 0
23 | All in-wall blocking for stair rails, wall mounted cabinets / millwork and toilet accessories | Y |  |  |  |  | 0
24 | All blocking / framing for medicine cabinets, attic fans, attic access, attic stairs, and skylights where necessary | Y |  |  |  |  | 0
25 | All blocking / framing necessary for the proper installation and functioning of the plumbing, electrical, and HVAC systems and fixtures | Y |  |  |  |  | 0
26 | Install all wood framed stair components | Y |  |  |  |  | 0
27 | Perimeter safety handrails | Y |  |  |  |  | 0
28 |  | Y |  |  |  |  | 0
29 | Site: [if applicable, provide descriptions and detail references] | Y |  |  |  |  | 0
30 |  | Y |  |  |  |  | 0
31 | Cranes & hoisting for the work above [PROVIDE BREAKOUT PRICING] | Y |  |  |  |  | 0
32 |  | Y |  |  |  |  | 0
33 | Additional Items: | Y |  |  |  |  | 0
34 | Installation of HM doors, frames and hardware within and leading to Ameninty / Common areas | Y |  |  |  |  | 0
35 | Installation of wood doors and hardware within and leading to Amenity / Common areas | Y |  |  |  |  | 0
36 | Install elevator cab protection [PROVIDE BREAKOUT PRICING] | Y |  |  |  |  | 0
37 | Install one (1) added layer of sheathing beneath all kitchen base cabinets [PROVIDE BREAKOUT PRICING] | Y |  |  |  |  | 0
38 | Furnish and install all hardie siding and trim [PROVIDE BREAKOUT PRICING) | Y |  |  |  |  | 0
39 | Furnish and install Brick mold at exterior doors in brick | Y |  |  |  |  | 0
40 | Vinyl soffits | Y |  |  |  |  | 0
41 |  | Y |  |  |  |  | 0
42 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
43 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
44 | Perform all necessary field cutting of lumber/plywood | Y |  |  |  |  | 0
45 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
46 | Clean up to MCN dumpster | Y |  |  |  |  | 0
47 |  | Y |  |  |  |  | 0
48 | LEED Issues: | Y |  |  |  |  | 0
49 | FSC-certified lumber | Y |  |  |  |  | 0
50 | No CCA pressure treatment for lumber | Y |  |  |  |  | 0
51 | Plywood/substrates free of urea formaldehyde | Y |  |  |  |  | 0
52 | Low VOC adhesives | Y |  |  |  |  | 0
53 | Sorting of debris for recycling | Y |  |  |  |  | 0
54 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Dumpsters | N | by GC
2 | Covered walkways | N | by GC
2 | Temporary partitions | N | by GC
3 | Floor protection | N | by GC
3 | Running wood trim (list: wood base, shoe moulding, window sills/aprons, entry door trim, casings, crown mouldings, chair rails, etc) | N | by Trim
4 | Wood or wire shelving | N | by Trim
4 | Install pre-hung interior unit doors and hardware | N | by Trim
5 | Install unit entry doors, frames and hardware | N | by Trim
5 | Blocking occurring outside of walls for millwork items | N | by Millwork
6 | Installation of glazed aluminum storefront framing | N | by Glass
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Trim
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 06 - FINISH CARPENTRY | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | [Solid Wood trim] or [Finger Jointed Pine (FJP) trim] or [MDF trim] | Y |  |  |  |  | 0
3 | [List profile #s if specified / scheduled] | Y |  |  |  |  | 0
4 | Cut to fit as required by site conditions; include mitering | Y |  |  |  |  | 0
5 | Common Areas / Corridors / Amenity Spaces | Y |  |  |  |  | 0
6 | Base | Y |  |  |  |  | 0
7 | Shoe molding (if no wood flooring) | Y |  |  |  |  | 0
8 | Interior window stools | Y |  |  |  |  | 0
9 | Apron at interior window stools | Y |  |  |  |  | 0
10 | Window casings | Y |  |  |  |  | 0
11 | Unit entry door trim (corridor side) | Y |  |  |  |  | 0
12 | Trim at cased openings | Y |  |  |  |  | 0
13 | Casing under counter tops | Y |  |  |  |  | 0
14 | Chair rail | Y |  |  |  |  | 0
15 | Wainscotting | Y |  |  |  |  | 0
16 | Crown moulding | Y |  |  |  |  | 0
17 | Primed wood shelving, brackets and coat rods | Y |  |  |  |  | 0
18 | Units | Y |  |  |  |  | 0
19 | Base | Y |  |  |  |  | 0
20 | Shoe molding (if no wood flooring) | Y |  |  |  |  | 0
21 | Interior window stools | Y |  |  |  |  | 0
22 | Apron at interior window stools | Y |  |  |  |  | 0
23 | Window casings | Y |  |  |  |  | 0
24 | Unit entry door trim (unit side) | Y |  |  |  |  | 0
25 | Door casing / trim at prehung interior unit doors | Y |  |  |  |  | 0
26 | Wood frame at cased openings | Y |  |  |  |  | 0
27 | Trim at cased openings | Y |  |  |  |  | 0
28 | Casing under counter tops | Y |  |  |  |  | 0
29 | Chair rail | Y |  |  |  |  | 0
30 | Wainscotting | Y |  |  |  |  | 0
31 | Crown moulding | Y |  |  |  |  | 0
32 | Primed wood shelving, brackets and coat rods | Y |  |  |  |  | 0
33 |  | Y |  |  |  |  | 0
34 | Additional Items: [PROVIDE BREAKOUT PRICING FOR EACH ITEM BELOW] | Y |  |  |  |  | 0
35 | FURNISH ONLY Unit interior pre-hung doors | Y |  |  |  |  | 0
36 | Receive, stock, distribute, install - Common Area / Amenity interior wood doors & hardware as well as interior HM doors, frames & hardware | Y |  |  |  |  | 0
37 | Receive, stock, distribute, install - Unit entry doors, frames & hardware | Y |  |  |  |  | 0
38 | Receive, stock, distribute, install - Unit interior pre-hung doors & hardware | Y |  |  |  |  | 0
39 | Receive, stock, distribute, install - Unit bathroom toilet accessories | Y |  |  |  |  | 0
40 | Receive, stock, distribute, install - Common Area toilet accessories | Y |  |  |  |  | 0
41 | Receive, stock, distribute, install - Common Area fire extinguishers and cabinets | Y |  |  |  |  | 0
42 | Receive, stock, distribute, install - Postal specialties | Y |  |  |  |  | 0
43 | Receive, stock, distribute, install - Wire shelving | Y |  |  |  |  | 0
44 | Receive, stock, distribute, install - Bike racks in storage area / Garage (exterior bike racks installed by others) | Y |  |  |  |  | 0
45 |  | Y |  |  |  |  | 0
46 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
47 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
48 | Perform all necessary field cutting of lumber/plywood | Y |  |  |  |  | 0
49 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
50 | Clean up to MCN dumpster | Y |  |  |  |  | 0
51 |  | Y |  |  |  |  | 0
52 | LEED Issues: | Y |  |  |  |  | 0
53 | FSC-certified lumber | Y |  |  |  |  | 0
54 | No CCA pressure treatment for lumber | Y |  |  |  |  | 0
55 | Plywood/substrates free of urea formaldehyde | Y |  |  |  |  | 0
56 | Low VOC adhesives | Y |  |  |  |  | 0
57 | Sorting of debris for recycling | Y |  |  |  |  | 0
58 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Finished/veneered millwork (not paint grade) | N | by millwork
2 | In-wall blocking | N | by rough carpentry
3 | Shoe mouldings to match wood floor | N | by wood floor
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Insulation - Residential
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - BUILDING INSULATION | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Thermal Insulation | Y |  |  |  |  | 0
3 | Insulation in Wood Framed Areas (provide breakout pricing) | Y |  |  |  |  | 0
4 | [R-13] [Batt] insulation within 4" wall | Y |  |  |  |  | 0
5 | [R-19] [Batt] insulation within 6" wall | Y |  |  |  |  | 0
6 | Insulate window and door headers | Y |  |  |  |  | 0
7 | [R-30] [Batt] or spray foam insulation within roof trusses | Y |  |  |  |  | 0
8 | Insulation within parapet walls above roof line | Y |  |  |  |  | 0
9 | Insulation within corridor walls | Y |  |  |  |  | 0
10 | Insulation within Unit separation walls | Y |  |  |  |  | 0
11 | Batt insulation within roof trusses | Y |  |  |  |  | 0
12 | Batt insulation within attic spaces [could be R-49 if IBC 2012] | Y |  |  |  |  | 0
13 | Attic venting (4" strip to hold insulation off of roof sheathing to allow air flow around insulation and not trap moisture) | Y |  |  |  |  | 0
14 | Batt insulation within trusses between floors | Y |  |  |  |  | 0
15 | [Batt or cellulose or spray foam] within cantilevered floor framing | Y |  |  |  |  | 0
16 | [Batt or cellulose or spray foam] within metal framed corridor walls | Y |  |  |  |  | 0
17 | [Batt or cellulose or spray foam] within metal framed perimeter walls | Y |  |  |  |  | 0
18 | [Batt or cellulose or spray foam] insulation above suspended ceilings in garage | Y |  |  |  |  | 0
19 | [Batt or cellulose or spray foam] insulation stick-pinned on underside of slab above garage / retail | Y |  |  |  |  | 0
20 | Air infiltration package at exterior walls | Y |  |  |  |  | 0
21 | Seal sill plate to subfloor sheathing at exterior walls | Y |  |  |  |  | 0
22 | Seal all framing on Unit side of exterior sheathing | Y |  |  |  |  | 0
23 | Seal gaps between double or more studs in exterior walls | Y |  |  |  |  | 0
24 | Seal around perimeter of MEP penetrations through exterior sheathing | Y |  |  |  |  | 0
25 | Low expanding foam on interior side of openings in exterior walls between window/door frames and rough opening framing | Y |  |  |  |  | 0
26 | Air infiltration package at Unit separation and corridor walls to comply with 2012 IECC requirements [if required] | Y |  |  |  |  | 0
27 | Seal sill plate to subfloor sheathing at corridor walls | Y |  |  |  |  | 0
28 | Seal all framing on Unit side of corridor wall sheathing | Y |  |  |  |  | 0
29 | Seal gaps between double or more studs in walls | Y |  |  |  |  | 0
30 | Seal around perimeter of MEP penetrations through wall sheathing | Y |  |  |  |  | 0
31 | Low expanding foam on Unit side of door openings in walls between door frames and rough opening framing | Y |  |  |  |  | 0
32 | Tenting of sprinklers within attic and insulated interstitial spaces | Y |  |  |  |  | 0
33 | Fill void/dead spaces between wood framing with non-combustible insulation | Y |  |  |  |  | 0
34 | Blown Insulation | Y |  |  |  |  | 0
35 | Exterior Walls: Blown insulation pneumatically placed into wall spaces through access holes. | Y |  |  |  |  | 0
36 | Ceiling: Loose insulation pneumatically placed and poured into joist spaces through access holes. | Y |  |  |  |  | 0
37 | Insulation and ventilation baffles. | Y |  |  |  |  | 0
38 | Provide continuity of thermal barrier at building enclosure elements ​​, in conjunction with Section 07 2100​​. | Y |  |  |  |  | 0
39 | Provide blown insulation in attic, exterior walls, and ceiling as indicated on drawings. R-38 minimum | Y |  |  |  |  | 0
40 |  | Y |  |  |  |  | 0
41 | Provide Breakout Pricing for Insulation in Wood Framed Areas | ---> |  |  |  |  | 0
42 | Provide Breakout Pricing for Insulation in Metal Framed Areas | ---> |  |  |  |  | 0
43 | Provide Breakout Pricing for Insulation at Garage Ceiling | ---> |  |  |  |  | 0
44 |  | Y |  |  |  |  | 0
45 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
46 | Provide all material, labor, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
47 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
48 | Clean up debris to MCN dumpster | Y |  |  |  |  | 0
49 | Shop dwgs, samples, product data, certs, test reports, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Sheet metal copings and flashings | N | By roofing
2 | Studs, drywall and sheathing | N | By drywall
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## AVB
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - AIR BARRIER | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Air barrier sheet or fluid-applied membrane on all Concrete or CMU substrates. | Y |  |  |  |  | 0
3 | Include primers, transition strips, termination strips, sealants, and adhesives to provide a complete system | Y |  |  |  |  | 0
4 | Warranty requirements | Y |  |  |  |  | 0
5 |  | Y |  |  |  |  | 0
6 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
7 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
8 | Advise if use of mason's scaffold will be required | Y |  |  |  |  | 0
9 | Accessories to include primers, mastics, adhesives, tapes, joint seals/gels, flashings, transitions strips, sealants, etc | Y |  |  |  |  | 0
10 | Minor surface prep, filler, dampening/rinsing as needed | Y |  |  |  |  | 0
11 | Termination bars as req'd | Y |  |  |  |  | 0
12 | Flashing/sealing of penetrations | Y |  |  |  |  | 0
13 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
14 | Clean up to MCN dumpster | Y |  |  |  |  | 0
15 | Shop dwgs, samples, product data, certs, etc | Y |  |  |  |  | 0
16 | Materials for site mockup | Y |  |  |  |  | 0
17 | AABA certificaton, if specified | Y |  |  |  |  | 0
18 |  | Y |  |  |  |  | 0
19 | LEED Issues: | Y |  |  |  |  | 0
20 | Formaldehyde and heavy metal free VOC compliant coatings and sealants | Y |  |  |  |  | 0
21 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 | Wood blocking | N | By carpentry
2 | Roofing (provide separate price if bidding this scope) | N | By roofing
3 | Below slab vapor retarders | N | by concrete
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## SAFP
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - FIREPROOFING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Spray Fireproofing | Y |  |  |  |  | 0
2 | Spray fireproofing per [IBC Building Construction Type ??]: | Y |  |  |  |  | 0
3 | 2 hour structural frame (columns, bracing & beams - ref Structurals) | Y |  |  |  |  | 0
3 | 1 hour roof frame (beams, joists - ref Structurals) | Y |  |  |  |  | 0
4 | Assume restrained stuctural classification [unless otherwise noted; QUALIFY] | Y |  |  |  |  | 0
4 | Apply surface sealer to fireproofing in plenum spaces [if spec'd] | Y |  |  |  |  | 0
5 | Warranties per spec [Material and Workmanship] | Y |  |  |  |  | 0
5 |  | Y |  |  |  |  | 0
6 | Intumescent Fireproofing | Y |  |  |  |  | 0
6 | Apply intumescent coatings in thicknesses to achieve req'd rating where shown: | Y |  |  |  |  | 0
7 | ***List specific locations of intumescent coatings*** | Y |  |  |  |  | 0
7 | ***List specific locations of intumescent coatings*** | Y |  |  |  |  | 0
8 | ***List specific locations of intumescent coatings*** | Y |  |  |  |  | 0
8 |  | Y |  |  |  |  | 0
9 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Provide all material, labor, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
10 | Advise of rate per day for patching of damaged fireproofing [GC Add] | Y |  |  |  |  | 0
10 | Advise of cost for additional mobilizations | Y |  |  |  |  | 0
11 | Minor surface preparation | Y |  |  |  |  | 0
11 | Clean up debris/overspray to MCN dumpster | Y |  |  |  |  | 0
12 | Shop dwgs, submittals, product data, certs, test reports, etc | Y |  |  |  |  | 0
12 |  | Y |  |  |  |  | 0
13 | LEED Issues: | Y |  |  |  |  | 0
13 | Cafco Blazeshield II fireproofing product | Y |  |  |  |  | 0
14 | LEED documentation | Y |  |  |  |  | 0
14 |  | Y |  |  |  |  | 0
15 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## EIFS
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - EIFS/STUCCO | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | EIFS system to include base coat, reinforcing mesh and finish coat on 2" rigid insulation at the following locations: | Y |  |  |  |  | 0
3 | Penthouse walls and screen walls at [list location] | Y |  |  |  |  | 0
4 | ***Other locations*** | Y |  |  |  |  | 0
5 | ***Other locations*** | Y |  |  |  |  | 0
6 | Include finish as specified | Y |  |  |  |  | 0
7 | Include reveals as shown | Y |  |  |  |  | 0
8 | Include special shapes of formed insulation to sizes, dimensions & profiles shown | Y |  |  |  |  | 0
9 | Include drip edge flashings at base of system & heads of openings in the system | Y |  |  |  |  | 0
10 | System meets performance criteria outlined | Y |  |  |  |  | 0
11 | Warranties per spec [Material and Workmanship] | Y |  |  |  |  | 0
12 | Mock-up requirements per spec | Y |  |  |  |  | 0
13 |  | Y |  |  |  |  | 0
14 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
15 | Provide all material, labor, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
16 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
17 | Clean up debris to MCN dumpster | Y |  |  |  |  | 0
18 | Shop dwgs, samples, product data, certs, test reports, etc | Y |  |  |  |  | 0
0
C | Exclusions
1 | Sheet metal copings and flashings | N | by roofing
2 | Studs, drywall and sheathing | N | by drywall
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## ExtPanel
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 07 - EXTERIOR PANELS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | All Hardi-Siding, Hardie trim, Hardie panel as indicated [Unfinished, smooth finish, color tbd] | Y |  |  |  |  | 0
3 | Brick mold at exterior doors in brick | Y |  |  |  |  | 0
4 | Vinyl soffits | Y |  |  |  |  | 0
5 | All aluminum flashing within your systems [reference details] | Y |  |  |  |  | 0
6 | Caulking within your system and to adjacent materials | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 | Provide all material, tools, equipment, hoisting, supervision, etc for this work | Y |  |  |  |  | 0
10 | Include all anchors and fasteners for this work | Y |  |  |  |  | 0
11 | Furnish anchor bolts for sill plates for installation into conc/masonry by others | Y |  |  |  |  | 0
12 | Perform all necessary field cutting of lumber/plywood | Y |  |  |  |  | 0
13 | Layout from GC control lines and benchmarks | Y |  |  |  |  | 0
14 | Clean up to MCN dumpster | Y |  |  |  |  | 0
15 |  | Y |  |  |  |  | 0
16 | LEED Issues: | Y |  |  |  |  | 0
17 | FSC-certified lumber | Y |  |  |  |  | 0
18 | No CCA pressure treatment for lumber | Y |  |  |  |  | 0
19 | Plywood/substrates free of urea formaldehyde | Y |  |  |  |  | 0
20 | Low VOC adhesives | Y |  |  |  |  | 0
21 | Sorting of debris for recycling | Y |  |  |  |  | 0
22 | LEED documentation | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## Glz
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 08 - GLASS & GLAZING | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Scope | Y |  |  |  |  | 0
3 | Scope | Y |  |  |  |  | 0
4 | Scope | Y |  |  |  |  | 0
5 | Scope | Y |  |  |  |  | 0
6 | Scope | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #

## IntGlass
Project: | Jelleff Recreation Center | [5 empty] | Subcontractor: |  | Bidder 1 |  |  | Bidder 2 |  |  | Bidder 3 |  |  | Bidder 4 |  |  | Bidder 5 |  |  | Bidder 6 |  |  | Bidder 7 |  | Bid Summary | Base | Adj | Bond | Total | Cert % | Total $
Bid Date: | 2026-02-01 |  |  | Return to Bid Sheet |  |  | Contact: |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  | MCN |  |  |  | 0
[7 empty] | Email: |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  |  | Email |  | 1 | [5 empty] | 0
Trade: | 08 - INT GLASS | [5 empty] | Phone: |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  |  | Number |  | 2 | [5 empty] | 0
Rev/Date: | Date Issued MM-DD-YYYY | Bidder: | [6 empty] | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO |  | Level Scope? | NO | 3 | [5 empty] | 0
[9 empty] | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  |  | Base Bid: |  | 4 | [5 empty] | 0
Contact: | MCN Estimator Name | Contact: |  |  | ¦ MCN Budget |  | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 |  | Adjustments: | 0 | 5 | [5 empty] | 0
Email: | MCN email | Email: |  | 2% | ¦ Bond |  | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 2% | Bond: | 0 | 6 | [5 empty] | 0
Phone: | MCN Cell | Phone: |  |  | ----- | --------> | 0 |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level |  | Total Bid: | not level | 7 | [5 empty] | 0
HIDE | Rank |  | HIDE | HIDE |  | HIDE | RANK |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE |  |  | INCOMPLETE
MCN Budget
Scope Items to include, but not necessarily limted to the following: |  | Desired Scope | Response / Comment | QTY | UOM | $ /UOM | COST | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment | Y/N/P | Note | Adjustment
Section 1 - General
1 | Acknowledge receipt and completition of the Building Connected General Bid Form with list of Drawings, Specs, Reports, Exhibits, Instructions to Bidders, RFIs and Bid Notices as applicable, Schedule, Logistics plan, and other information required for Bid | Y
Section 2 - Bid Breakdown
1 | Base Bid | # | $ | xxx | xx | xxx | xxx
2 | [6 empty] | 0
3 | Key Cost Breakdown | [5 empty] | 0
4 | Building | # | $ |  |  |  | 0
5 | Garage | # | $ |  |  |  | 0
6 | Site | # | $ |  |  |  | 0
7 | Demolition | # | $ |  |  |  | 0
8 | [6 empty] | 0
9 | Key Quantity Breakdown | [5 empty] | 0
10 | Stuff | # | CY |  |  |  | 0
11 | Thing | # | SF |  |  |  | 0
12 | Stuff 2 | # | LF |  |  |  | 0
13 | Item | # | EA |  |  |  | 0
0
Section 3 - Scope of Work
| Furnish and Install All Items UON | Y
A | Specifications
| Division 01 - General Requirements | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section | Y
| 00 00 00 - Spec Section (as applicable to this Bid Package) | Y
| Geotech Report ID # by Engineer dated YYYY-MM-DD | Y
B | Inclusions
1 | SPECIFIC SCOPE ITEMS | Y |  |  |  |  | 0
2 | Scope | Y |  |  |  |  | 0
3 | Scope | Y |  |  |  |  | 0
4 | Scope | Y |  |  |  |  | 0
5 | Scope | Y |  |  |  |  | 0
6 | Scope | Y |  |  |  |  | 0
7 |  | Y |  |  |  |  | 0
8 | STANDARD / GENERAL SCOPE | Y |  |  |  |  | 0
9 |  | Y |  |  |  |  | 0
10 |  | Y |  |  |  |  | 0
0
C | Exclusions
1 |  | N
2 |  | N
3 |  | N
4 |  | N
5 |  | N
6 |  | N
7 |  | N
8 |  | N
D | Schedule
1 | Meet MCN Schedule | Y
2 | Advise of Durations
3 | Activity 1 | --->
4 | Activity 2 | --->
5 | Activity 3 | --->
6 | Duration for Submittals and Shop Drawings | --->
7 | Advise of Lead Times:
8 | Material 1 | --->
9 | Material 2 | --->
10 | Material 3 | --->
Allowances
1
2
3
4
Alternates
1 |  | #
2 |  | #
3 |  | #
4 |  | #
#
Unit Prices
1 |  | #
2 |  | #
3 |  | #
4 |  | #